## MEF format (Annex 1) (hidden)
CFAVC Project Implementation Schedule Based on 3 OUTPUTS
|  |  |  | Status | 15/01/21 | [8 empty] | Months | 12 | Total | 60
ACTIVITY/Implementing Agency |  | Assigned Weight | Progress 2020 | Actual Progress | [7 empty] | Weighted progress | [7 empty] | Actual Progress against AWP 2020
|  |  |  | 30/03/20 | 30/06/20 | 15/08/20 | 15/09/20 | 15/10/20 | 15/11/20 | 15/12/20 | 31/12/20 | 30/03/20 | 30/06/20 | 15/08/20 | 15/09/20 | 15/10/20 | 15/11/20 | 15/12/20 | 31/12/20 | 30/03/20 | 30/06/20 | 15/08/20 | 15/09/20 | 15/10/20 | 15/11/20 | 15/12/20 | 31/12/20
1 | Establish project PMU & PRC | 0.5% | 0.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5%
2 | Recruitment of Consultants | 0.5% | 0.35% | 60% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 0.3% | 0.35% | 0.35% | 0.35% | 0.35% | 0.35% | 0.35% | 0.35%
3 | PMU Operation | 4% | 0.8% | 3.75% | 7.5% | 10% | 12.15% | 14.5% | 20% | 20% | 25% | 0.15% | 0.3% | 0.45% | 0.475% | 0.58% | 0.8% | 0.8% | 1% | 25% | 50% | 65% | 72.5% | 80% | 87% | 95% | 100%
4 | Social Safeguards and Resettlement | 2% | 0.034% | 0.5% | 1% | 1.2% | 1.2% | 1.3% | 1.6% | 1.6% | 1.6% | 0.01% | 0.02% | 0.02% | 0.03% | 0.03% | 0.032% | 0.032% | 0.032% | 10% | 20% | 25% | 30% | 35% | 50% | 55% | 65%
5 | Environmental Management | 1.5% | 0.025% | 0.5% | 1% | 1.2% | 1.2% | 1.3% | 1.6% | 1.6% | 1.6% | 0.0075% | 0.015% | 0.015% | 0.015% | 0.02% | 0.024% | 0.024% | 0.024% | 25% | 50% | 60% | 65% | 72% | 75% | 80% | 85%
6 | Gender | 1.5% | 0.03% | 1% | 1.5% | 1.6% | 1.7% | 1.9% | 2% | 2% | 2% | 0.015% | 0.0225% | 0.03% | 0.03% | 0.03% | 0.03% | 0.03% | 0.03% | 10% | 25% | 30% | 35% | 40% | 50% | 55% | 60%
7 | Implementation of Output 1 - MAFF | 27% | 3.79% | 0.04854% | 0.3397% | 0.3464% | 8.981% | 8.983% | #VALUE! | #VALUE! | #VALUE! | 0.3398% | 2.378% | 2.425% | 2.425% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.215% | 12.15% | 13.03% | 13.09% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
8 | Implementation of Output 1 - MOWRAM | 13.5% | 1.28% | 0.01614% | 0.06626% | 0.1053% | 6.239% | 7.923% | #VALUE! | #VALUE! | #VALUE! | 0.1291% | 0.5301% | 0.8422% | 1.07% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.44% | 11.81% | 17.71% | 24.02% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
9 | Implementation of Output 1 - MRD | 13.5% | 1.82% | 0.02848% | 0.08974% | 0.1141% | 7.608% | 9.009% | #VALUE! | #VALUE! | #VALUE! | 0.2563% | 0.8076% | 1.027% | 1.216% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6.29% | 20.9% | 27.95% | 33.14% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
10 | Implementation of Output 1 - Unassigned | 4.5% | 0.02% | 0% | 0.001755% | 0.003755% | 0.8345% | 0.8345% | #VALUE! | #VALUE! | #VALUE! | 0% | 0.01755% | 0.03755% | 0.03755% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | 0% | 7.09% | 7.09% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
11 | Implementation of Output 2 - MAFF | 12.6% | 2.23% | 0.07699% | 0.1239% | 0.1273% | 11.11% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.8469% | 1.363% | 1.4% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 7.938% | 22.88% | #VALUE! | 41.12% | #VALUE! | #VALUE! | #VALUE! | #VALUE!
12 | Implementation of Output 2 - MOWRAM | 5.4% | 0.64% | 0.003403% | 0.0673% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.04083% | 0.8076% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6.2% | 5% | 5.5% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
13 | Implementation of Output 3 - MAFF | 13.5% | 2.87% | 0.06829% | 0.1198% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.8877% | 1.557% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOTAL | 100% | 14.39% | [8 empty] | 3.483% | 5.569% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## OVER VIEW (Annex 2) (hidden)
Figure 1 : CFAVC Project Implementation Schedule Based on 3 OUTPUTS
Output and Activities |  | Assigned weight | Progress 2020 | Actual Progress Overall 2021 (%) | [7 empty] | Weighted Progress Overall 2021 % | [7 empty] | Actual Progress AWP 2021 (%) | [7 empty] | UPDATED OVERALL PROGRESS (%)
|  |  |  | QR1 | QR2 | 15/08/20 | 15/09/20 | 15/10/20 | 15/11/20 | 15.12/20 | 31/12/20 | QR1 | QR2 | 15/08/20 | 15/09/20 | 15/10/20 | 15/11/20 | 15/12/20 | 31/12/20 | QR1 | QR2 | 15/08/20 | 15/09/20 | 15/10.20 | 15/11/20 | 15/12/20 | 31/12/20 | QR1 | QR2 | 15/08/20 | 15/09/20 | 15/10.20 | 15/11/20 | 15/12/20 | 31/12/20
Output 1 – Critical Agribusiness Value Chain Infrastructure Improved and made Climate-Resilient
1.a | 27 Irrigation and water management systems rehabilitated and made climate-friendly | 15 | 1.508 | 0.86074 | 3.534 | 5.6147 | 7.1304 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.12911 | 0.5301 | 0.84221 | 1.0696 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.4444 | 11.8139 | 17.7062 | 24.0236 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.b | 800 On-farm rainwater harvesting ponds commissioned (incl. 15 drip irrigation) | 5 | 0.207 | 0 | 0.35104 | 0.75104 | 0.75104 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0.017552 | 0.037552 | 0.037552 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 3.3438 | 7.0938 | 7.0938 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.c | At least 250 Km Farm roads upgraded to climate resilient standards to improve Connectivity to Cooperatives and Markets | 15 | 2.107 | 1.7087 | 5.3843 | 6.8472 | 8.108 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.25631 | 0.80765 | 1.0271 | 1.2162 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6.2866 | 20.9031 | 27.9495 | 33.1397 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.d | 80 Agricultural cooperatives have integrated adaptation measures in postharvest infrastructural investments | 15 | 2.334 | 0.5625 | 8.5 | 8.5 | 8.5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.084375 | 1.275 | 1.275 | 1.275 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.25 | 34 | 34 | 34 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.e | Crop product quality and safety testing infrastructure in National Agriculture Laboratory upgraded | 5 | 0.75 | 4 | 10 | 10 | 10 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.2 | 0.5 | 0.5 | 0.5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4 | 10 | 10 | 10 | 10 | #VALUE! | #VALUE! | #VALUE!
1.f1 | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) | 5 | 0.379 | 0.67087 | 5.975 | 6.5 | 6.5033 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.033544 | 0.29875 | 0.325 | 0.32517 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.105 | 1.0356 | 4.038 | 4.118 | 6 | #VALUE! | #VALUE! | #VALUE!
1.f2 | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) | 5 | 0.363 | 0.4375 | 6.0792 | 6.5 | 6.5067 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.021875 | 0.30396 | 0.325 | 0.32533 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.504 | 3.5712 | 4.076 | 4.236 | 5.5 | #VALUE! | #VALUE! | #VALUE!
| sub-total Output 1 | 65 | 7.648 | [8 empty] | 0.72521 | 3.733 | 4.3318 | 4.7488 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1.9776 | 10.9051 | 13.2087 | 23.3222 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Output 2 – Climate-smart Agriculture and Agribusiness Promoted
2.a | 3 Additional climate-resilient varieties of rice and maize released | 5 | 0.313 | 1.8125 | 3.25 | 3.25 | 3.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.090625 | 0.1625 | 0.1625 | 0.1625 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4.25 | 9 | 9 | 9 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4.25 | 9 | 9 | 9 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2.b | 40,000 Farmers trained in Climate-smart Agriculture and agribusiness development skills | 5 | 0.82 | 10.125 | 11.25 | 11.25 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.50625 | 0.5625 | 0.5625 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 13.5 | 15 | 15 | 18 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 13.5 | 15 | 15 | 18 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2.c.1 | 27 FWUCS of FWUGS made operational | 3 | 0.363 | 1.3611 | 6.4815 | 6.8519 | 6.8519 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.040833 | 0.19444 | 0.20556 | 0.20556 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.4 | 9 | 10 | 10 | 10 | #VALUE! | #VALUE! | #VALUE! | 2.4 | 9 | 10 | 10 | 10 | #VALUE! | #VALUE! | #VALUE!
2.c.2 | 500 FWUCS of FWUGS, developed capacity to operate and maintain their irrigation schemes | 3 | 0.3 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | 1 | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | 1 | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2.d.1 | 4 Agricultural development centers made fully operational to provide agribusiness services | 2 | 0.527 | 10 | 18.75 | 20 | 20 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.2 | 0.375 | 0.4 | 0.4 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 17.5 | 30 | #VALUE! | 56.5 | 56.5 | #VALUE! | #VALUE! | #VALUE! | 17.5 | 30 | #VALUE! | 56.5 | 56.5 | #VALUE! | #VALUE! | #VALUE!
2.d.2 | 4 Engineering workshops made fully operational to provide agribusiness services | 2 | 0.606 | 2.5 | 13.125 | 13.75 | 21.75 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0.05 | 0.2625 | 0.275 | 0.435 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | 52.5 | 55 | 79 | 79 | #VALUE! | #VALUE! | #VALUE! | 10 | 52.5 | 55 | 79 | 79 | #VALUE! | #VALUE! | #VALUE!
| sub-total Output 2 | 20 | 2.929 |  |  | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0.88771 | 1.5569 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 11.53 | 23.3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 11.53 | 23.3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Output 3 – Enabling Environment for Climate-Friendly Agribusiness Enhanced
3.a | Climate-smart and gender-responsive Agribusiness Policies for target commodities including a PPP framework formulated | 2 | 0.38 | 9.5 | 7.75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0.19 | 0.155 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 14 | 14.5 | 14.5 | 18 | #REF! | #REF! | #REF!
3.b | Cambodia good Agricultural practice for tropical fruit endorsed as national standard | 2 | 0.29 | 0 | 0 | 9 | 10 | 10 | #REF! | #REF! | #REF! | 0 | 0 | 0.18 | 0.2 | 0.2 | #REF! | #REF! | #REF! | 0 | 0 | 18 | 20 | 20 | #REF! | #REF! | #REF!
3.c | Cambodia Good Agricultural practice for organic fertilizers endorsed as national standard | 2 | 0.23 | 5 | 0 | 0 | 4 | #REF! | #REF! | #REF! | #REF! | 0.1 | 0 | 0 | 0.08 | #REF! | #REF! | #REF! | #REF! | 10 | 0 | 0 | 8 | 10 | #REF! | #REF! | #REF!
3.d | 50 Staff from financial institutions trained in CSA and green finance (30% are women) | 2 | 0.109 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
3.e | 30 agribusinesses trained in green finance and CSA (30% are women) | 2 | 0.09 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF!
3.f | 20,000 Households provided with information on climate risk-sharing instruments (100% are women) | 2 | 0.09 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF!
3.g | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | 3 | 0.208 | 4.35 | 4.125 | 6.6 | 6.6 | 6.6 | #REF! | #REF! | #REF! | 0.1305 | 0.12375 | 0.198 | 0.198 | 0.198 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 26.4 | #REF! | #REF! | #REF!
| sub-total Output 3 | 15 | 1.397 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0.4205 | 0.27875 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL |  | 100 | 11.974 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.0334 | 5.5687 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
OUTPUT 1 | Output 1 MAFF | 30 | 3.826 | 5.6709 | 30.5542 | 31.5 | 31.51 | #VALUE! | #VALUE! | #VALUE! |  | 0.33979 | 2.3777 | 2.425 | 2.4255 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.2147 | 12.1517 | 13.0285 | 13.0885 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Output 1 MOWRAM | 15 | 1.508 | 0.86074 | 3.534 | 5.6147 | 7.1304 | #VALUE! | #VALUE! | #VALUE! |  | 0.12911 | 0.5301 | 0.84221 | 1.0696 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.4444 | 11.8139 | 17.7062 | 24.0236 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Output 1 MRD | 15 | 2.107 | 1.7087 | 5.3843 | 6.8472 | 8.108 | #VALUE! | #VALUE! | #VALUE! |  | 0.25631 | 0.80765 | 1.0271 | 1.2162 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6.2866 | 20.9031 | 27.9495 | 33.1397 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Output 1 Unassigned | 5 | 0.207 | 0 | 0.35104 | 0.75104 | 0.75104 | #VALUE! | #VALUE! | #VALUE! |  | 0 | 0.017552 | 0.037552 | 0.037552 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2.25 | 34 | 34 | 34 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| TOTAL - Output 1 | 65 | 7.648 | [8 empty] | 0.72521 | 3.733 | 4.3318 | 4.7488 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.299 | 19.7172 | 23.1711 | 26.0629 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
OUTPUT 2 | Output 2 MAFF | 14 | 2.266 | 24.4375 | 46.375 | 48.25 | 0 | #VALUE! | #VALUE! | #VALUE! |  | 0.84688 | 1.3625 | 1.4 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 7.9375 | 22.875 | #VALUE! | 41.125 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Output 2 MOWRAM | 6 | 0.663 | 1.3611 | 6.4815 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | 0.040833 | 0.19444 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6.2 | 5 | 5.5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| TOTAL - Output 2 | 20 | 2.929 | [8 empty] | 0.88771 | 1.5569 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 7.0687 | 13.9375 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
OUTPUT 3 MAFF |  | 15 | 1.397 | 3.1417 | 4.125 | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0.4205 | 0.27875 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL - Output 1 + 2 + 3 |  | 100 | 11.974 | [8 empty] | 2.0334 | 5.5687 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[20 empty] | 2.1443 | 12.8162 | 15.0612 | 16.9409 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[20 empty] | 1.4138 | 2.7875 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[20 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Instruction
Instruction to use
CFAVC Project's Physical Progress Database System (PPDS)
No | Applied Colors on the Indicators | Recommendations
1 |  | Primary Indicators
2 |  | Second Indicators
3 |  | Supporting Indicators
4 |  | All indicators are locked, except the blank columns for the data entry.
5 |  | Fill information
6 |  | Drop Down List
The CFAVC's Physical Progress Database System (PPDS) has its three Implementing Agents include MAFF, MoRAM, MRD, and MEF, which financially supported by the ADB as ADB Loans No.3661/8348-CAM and Grant 0579-CAM, in the four target provinces of KPC, TbK, TAK, and KAM and it is effectively from 28 March 2019 through 31 March 2025, which is implemented by CS1, CS2, CS3, CS4, and CS5. The indicators and its outputs have been specified precisely in the sheets of, Output 1, Output 2, Output 3, and DMF's Performant Indicators. This CFAVC's PPDS is developed and managed by the CFAVC's M&E Unit, which is split up into different PPDS include the CS2's PPDS, MoRAM's PPDS, MRD's PPDS, and those PPDS will be online data entry respectively.
Objectives, 1. To have clear and precised indicators' information, include Indicators names, Definition, Baseline, Target, Progress, Variances explanation, etc.; 2. To have clear roles and responsibilities in Data Managements; 3. To have Data Availability; 4. To have Data Integrity; 5. To have Data Security; 6. To have Data Independence; 7. To contribute the quality interim narrative reports; 8. To satisfy the donors.
Indicators and Outputs Information, The CFAVC's Project has 19 Performant Monitoring Indicators to be tracked, which categorized into One Outcome, and three Outputs as follows, 1. Outcome has 3 Outcome Indicators (Sheet of DMF Performant Indicators); 2. Output 1 has 6 Output Indicators (Sheet of DMF Performant Indicators); 3. Output 2 has 4 Output Indicators (Sheet of DMF Performant Indicators); 4. Output 3 has 6 Output Indicators (Sheet of DMF Performant Indicators). Beside these above 19 indicators, the Project also has 14 additional Gender Social Dimension's Performant Indicators are tracked (Sheet of DMF Performant Indicators). All these indicators and its progress needs to submit as the PPMS Semi-annual monitoring report to ADB, firstly in 30 July of the current fiscal year, and secondly in 30 January of the next fiscal year. Under Outputs levels, there are 8 main activities under the output 1; 6 main activities under output 2; and 7 main activities under output 3 as seen in picture below. For the routine tracking of the CFAVC DFM's Indicators progress, the project has prepared the monthly outputs progressed tracking (as seen in the sheets of, Output 1, Output 2, Output 3 of this file), which called "Physical Progress Databases", which implemented by e.Gen company, MoWRAM, & MRD. After the monthly data entry of Activities progress of the 3 Outputs, by the relevant CSs, then the DMF Performant Indicators progress have been automatically links to the Sheets of, 1. DFM Progress, 2. IAs Progress (Implementing Agencies), 3. MEF Progress(Ministry of Economic and Finance), as well as the Progress of DMF Performant Indicators but its narrative progress and the explanation of the reasons of its respective variation will be completed by the responsible CSs.
Below are some main Activities of each Output,
The process of PPDS Management, The PPDS is set up and based under the CFAVC's M&E Unit/CS1, which comprises of all CFAVC's indicators of all relevant Consultant Services Groups (CSs) as CS1, CS2, CS3, CS4, and CS5. All project's PPDS's indicators are split up by respective CS group for the whole project's life, which are monitored as its monthly, quarterly, semesterly, and annually. The responsible focal points of each CS group needs to do the data entry of their respective indicators' progress into the sheets of, Output 1, Output 2, and Output 3 in a monthly base. For the security reasons, all information of all sheets of this PPDS are locked, except the columns of Data entry as Target, and Actual progress of the current month only, especially for the sheets of, Output 1, Output 2, and Output 3.
During the current month of the data entry, and for the security reasons, the previous information as Target and Actual Progress are locked. The progresses of sheets of, 1. DMF Progress, 2. IAs Progress, and 3. MEF Progress are locked for all information because the CSs' focal points don't need to touch those information and they are automatically generated its respective progress from those sheets of, Output 1, Output 2, and Output 3. The PPDS is stored online and its monthly progress updated must be completed on 25th of each current month by the CSs' focal points. The application of the PPDS is trained to all relevant CSs' staff properly for consistent understanding and its applied.
The Measurement scales, Each indicator has its respective Definition, Baseline, Target, Sub-Weight, The progress of each monthly indicator is calculated as its formulation below, Monthly Weight Progress (%) = [(Monthly Actual Progress/Total Target) * its Sub-Weight] The progress monitoring focus on the Monthly weighted Progress, and its interim cumulative weighted progress.
Abbreviation of all provinces in Cambodia, 1. PNP - Phnom Penh; 2. KPT - Kampong Thom; 3. PVH - Preah Vihear; 4. KRT - Kratie; 5. STR - Steung Treng; 6. OMC - Odor Meanchey; 7. KKG - Koh Kong; 8. KPC - Kampong Cham; 9. MDK - Mondulkiri; 10. RAT - Rattanakiri; 11. PUR - Pursat; 12. BAT - Battambang; 13. BMC - Banteay Meanchey; 14. KPS - Kampong Speu; 15. SRP - Siem Reap; 16. KCN - Kampong Chnang; 17. KAM - Kampot; 18. KDL - Kandal; 19. PVG - Prey Veng; 20. SHV - Shihanuk Ville; 21. SVR - Svay Rieng; 22. TAK - Takeo; 23. KEP - Kep; 24. PLN - Pailin; 25. TBK - Tbong Khmum.
Any questions related to the use of CFAVC's PPDS, please contact to Dr. Vothana Prum, National Monitoring & Evaluation Expert, CFAVC Project. H/P: 078/069 80 37 38, Email: prumvothana12@gmail.com
Note on C5: User: Ex. 2b. 40,000 farmers (of whom 16,000 are women) trained in CSA and Agribusiness Development Skills (ADS), of which 50% are SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0). Hence, 1- Primary indicator is "40,000 farmers trained in CSA and ADS", while 2- Secondary Indicator is "of which 50% are SRP compliant with direct links to millers and exporters.

## DMF PI Links Physical Prog.S1
CFAVC PROJECT's DMF PERFORMANCE INDICATORS TRACKING SYSTEM
No. of indicators | M&E Indicator Codes | PAM's DMF Indicators Codes | MAFF's indicator Codes | DMF Performant Milestones/Indicators | Beneficiaries (HHs) | Beneficiaries (People) | Definitions |  | Methods for Tracking | Time line | CS#/ Units | Ministries | Unit | Baseline | Target | [8 empty] | Achievement in 2020 |  |  | First Six-Monthly Cumulative Progress in 2021 |  |  |  | Second Six-Monthly Cumulative Progress in 2021 |  |  |  | Cummulative Progress Tracking to date in 2020 - 2021
[8 empty] | Consultants | [15 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Total Assign Target (%) | Total Actual Achieved | Overall DMF Weight Progress (%) | Indicators Narrative Progress | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress
[15 empty] | Total | Assigned Weight (%) | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | [11 empty] | Total Target | Total Actual Achieved | % Weight Progress
| OC |  |  | Outcome, Productive and resource efficient agribusiness value chains developed in project areas | 49800 | 309680 | [9 empty] | 100 | [8 empty] | 2.0032 | 11.8291 | 25 | 4.1232 | 0.25443 |  | 25 | 6.7143 | 0.35893 |  |  | 12.8407 | 12.4425
1 | OC.1 | a. |  | By 2026 a. At least 15% increase in yields (2017 baseline: rice 2.7 tons, maize 4 tons, cassava 20 tons and mango 15 tons/ha). |  |  |  |  | a. MAFF agricultural census |  | CS 2 | MAFF | % |  | 15% | [12 empty] | MTR |  |  |  | MTR
| OC.1.a.1 |  |  | Rice (per ha) | [6 empty] | CS 2 | MAFF | Tone/Ha | 2.7 | 3.105 |  | 0 | 2.7 | 2.8013 | 2.9025 | 3.0038 | 3.105
| OC.1.a.2 |  |  | Maize (per ha) | [6 empty] | CS 2 | MAFF | Tone/Ha | 4 | 4.6 |  | 0 | 4 | 4.15 | 4.3 | 4.45 | 4.6
| OC.1.a.3 |  |  | Cassava (per ha) | [6 empty] | CS 2 | MAFF | Tone/Ha | 20 | 23 |  | 0 | 20 | 20.75 | 21.5 | 22.25 | 23
| OC.1.a.3 |  |  | Mango (per ha) | [6 empty] | CS 2 | MAFF | Tone/Ha | 15 | 17.25 |  | 0 | 15 | 15.5625 | 16.125 | 16.6875 | 17.25
2 | OC.2 | b. |  | By 2026 b. GHG emissions reduced by 240,000 tons of CO2 (2017 baseline: 0 tons reduced due to the project). |  |  | Base on the biogas utilization calculation. |  | b. UNFCCC reports |  |  |  | Tone | 0 | 240000 |  | 0 | 0 | 0 | 80000 | 80000 | 80000 | [5 empty] | MTR |  |  |  | MTR
3 | OC3 | c. |  | By 2026 c. At least 50 agribusinesses become more resource efficient in terms of water savings (5-10% efficiencies); energy savings (20%); and reduction in post-harvest losses (10%) (2017 baseline: 0). |  |  |  |  | c. PPMS reports |  | CS 2 | MAFF | % | 0 | 50 |  | 0 | 0 | 0 | 5 | 20 | 25 | [5 empty] | MTR |  |  |  | MTR
| OC3.C.1 |  |  | Water saving (5-10% efficient) | [6 empty] | CS 2 | MAFF | % | 0 | 10 |  | 0 |  | 2.5 | 5 | 7.5 | 10
| OC3.C.2 |  |  | Energy saving (20%) |  |  | Focus on the biogas utilization. |  |  |  | CS 2 | MAFF | % | 0 | 20 |  | 0 |  | 5 | 10 | 15 | 20
| OC3.C.3 |  |  | Post harvesting losses (10%) | [6 empty] | CS 2 | MAFF | % | 0 | 10 |  | 0 |  | 2.5 | 5 | 7.5 | 10
| OP.1 |  |  | Outputs. 1. Critical agribusiness value chain infrastructure improved and made climate resilient | 29800 | 220500 | [9 empty] | 65 | [9 empty] | 7.4776 | 16.25 | 1.5727 | 0.16523 |  | 16.25 | 2.0911 | 0.21276 |  |  | 3.6638 | 7.8556
4 | OP.1.1 | 1.a. |  | 1a. 27 irrigation and water management systems targeting 15,000 ha and 25,000 households (with at least 50,000 women) rehabilitated and made climate resilient (2017 baseline: 0). | 25000 | 5000 | Add next |  | PPMS annual reports |  | CS 1 | MOWRAM | Woman | 0 | 27 | 15 | 2019: 0; 2020: 10; 2021: 9 | 10 | 10.06 | 1.509 | 3.75 | 0.30667 | 0.046001 |  | 3.75 | 0.30852 | 0.046278 |  | 17.5 | 10.6752 | 1.6013
| OP.1.1a.1 |  |  | 27 irrigation and water management systems | [6 empty] | CS 1 | MOWRAM | Irrigation System | 0 | 27 |  | 2019: 0; 2020: 10; 2021: 9; 2022: 8 | 10 | 17.1936 | 0.2065
| OP.1.1a.2 |  |  | 27 irrigation and water management systems targeting 15,000 ha | [6 empty] | CS 1 | MOWRAM | Ha | 0 | 15000 |  | 2019: 0; 2020: 4050; 2021: 5333; 2022: 5617 | 4050 | 1399.5 | 1.866
| OP.1.1a.3 |  | No PP | 27 irrigation and water management systems targeting 25,000 households | [6 empty] | CS 1 | MOWRAM | Household | 0 | 25000 |  | 2019: 0
5 | OP.1.2 | 1b. |  | 1b. 800 on-farm rainwater harvesting ponds commissioned (2017 baseline: 0). |  | 50000 | Add next |  | PPMS annual reports |  | CS 2 | MAFF | Pond | 0 | 800 | 5 | 0 | 80 | 280 | 290 | 150 | 0 |  |  | 4.13 | 0.2065 | 1.25 | 0.01125 | 0.0005625 |  | 1.25 | 0.01125 | 0.0005625 |  | 2.5 | 4.1525 | 0.20763
6 | OP.1.3 | 1c. |  | 1c. At least 250 km of farm road networks upgraded to climate standards to improve connectivity of farms to cooperatives and markets (2017 baseline: 0). |  |  | Add next |  | MRD annual report |  | CS 1 | MRD | Km | 0 | 250 | 15 | 2019: 0; 2020: 67.95; 2021: 100.1; 2022: 81.95 |  | 14.05 | 2.1075 | 3.75 | 0.25403 | 0.038104 |  | 3.75 | 0.50882 | 0.076322 |  | 7.5 | 14.8128 | 2.2219
7 | OP.1.4 | 1d. |  | 1d. 80 agricultural cooperatives* integrated adaptation measures in post-harvest infrastructure investments (2017 baseline: 5). | 4800 | 24000 | Add next | Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | AC | 5 | 80 | 15 | 0 | 20 | 35 | 25 | 0 | 0 |  |  | 15.06 | 2.259 | 3.75 | 0.39866 | 0.059798 |  | 3.75 | 0.40698 | 0.061048 |  | 7.5 | 15.8656 | 2.3798
8 | OP.1.5 | 1e. |  | 1e. Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples (2017 baseline: 700) and generate service income more than $75,000 (2017 baseline: $0). |  | 1500 | Add next | Vong Sophorn/ Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF |  |  |  | 5 | [8 empty] | 16 | 0.8 | 1.25 | 0.234 | 0.0117 |  | 1.25 | 0.31919 | 0.015959 |  | 2.5 | 16.5532 | 0.82766
| OP.1.5.1e.1 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples |  |  |  |  | PPMS annual reports |  | CS 2 | MAFF | Sample | 700 | 1500 |  | 0 | 0 | 0 | 900 | 1100 | 1500
| OP.1.5.1e.2 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded generate service income more than $75,000 |  |  |  |  | PPMS annual reports |  | CS 2 | MAFF | USD | 0 | 75000 |  | 0 | 0 | 0 | 45000 | 55000 | 75000
9 | OP.1.6 | 1f. |  | 1f. 12,000 additional biodigesters and 6,000 compost huts made operational, benefiting at least 80,000 persons, including at least 50% women, due to better household air quality (2017 baseline beneficiaries: 11,468 persons, including 5,721 women). |  |  | Add next | Phuong Dara | PPMS annual reports |  | CS 2 | MAFF | [14 empty] | 2.5 | 0.36808 | 0.0090658 |  |  |  | 0.012592
| OP.1.6.1f.1 | 1f.1 |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  | 80000 |  |  | Physical Progress |  | CS 2 | MAFF | Biodigesters | No BL | 12000 | 4 | 0 | 500 | 2500 | 4000 | 3500 | 1500 |  |  | 7.07 | 0.2828 | 1 | 0.036731 | 0.0014692 |  | 1 | 0.039964 | 0.0015986 |  | 2 | 7.1467 | 0.28587
|  |  |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) | [6 empty] | CS 2 | MAFF | Person | 11468 | 80000 |  | 0 | 3333.3333 | 16666.6667 | 26666.6667 | 23333.3333 | 10000
| OP.1.6.1f.2 | 1f.2 |  | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  | 20000 |  |  | Physical Progress |  | CS 2 | MAFF | Compost hut | No BL | 6000 | 4 | 0 | 250 | 1250 | 1600 | 1600 | 1300 |  |  | 7.47 | 0.2988 | 1 | 0.048482 | 0.0019393 |  | 1 | 0.053315 | 0.0021326 |  | 2 | 7.5718 | 0.30287
|  |  |  | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) | [6 empty] | CS 2 | MAFF | Person | 11468 | 20000 |  | 0 | 833.3333 | 4166.6667 | 5333.3333 | 5333.3333 | 4333.3333
| OP.1.6.1f.3 | 1f.3 |  | 20,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  | 40000 |  | Phuong Dara | Physical Progress |  | CS 2 | MAFF |  | No BL | 20000 | 2 | 0 | 2500 | 5000 | 9500 | 3000 | 0 |  |  | 0.7 | 0.014 | 0.5 | 0.28286 | 0.0056573 |  | 0.5 | 0.44305 | 0.008861 |  | 1 | 1.4259 | 0.028518
| OP.1.6.1f.3 | 1f.3.1 |  | 20,000 people trained on biodigester use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed | [6 empty] | CS 2 | MAFF | Person | 11468 | 20000 |  | 0 | 1250 | 2500 | 4750 | 1500 | 0
| OP.1.6.1f.8 | 1f.3.2 |  | 20,000 people trained on compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed | [6 empty] | CS 2 | MAFF | Woman | 11468 | 20000 |  | 0 | 1250 | 2500 | 4750 | 1500 | 0
| OP.2 |  |  | Outputs. 2. Climate smart agriculture and agribusiness promoted | 0 | 69100 | [9 empty] | 20 | [8 empty] | 2.0032 | 2.9565 | 5 | 1.6198 | 0.069481 |  | 5 | 2.5011 | 0.10116 |  |  | 6.1241 | 3.1271
10 | OP.2.1 | 2a. |  | 2a. Three additional climate resilient varieties of rice and maize released (2017 baseline: 0). |  | 100 | Add next | Heng Sophat | PPMS annual reports |  | CS 2 | MAFF | Variety | 0 | 3 | 5 | 0 | 0 | 0 | 3 | 0 | 0 |  |  | 6.25 | 0.3125 | 1.25 | 0.071304 | 0.0051694 |  | 1.25 | 0.098267 | 0.0065175 |  | 2.5 | 6.4196 | 0.32419
| OP.2.1.2a.1 |  |  | Three additional climate resilient varieties of rice released | [6 empty] | CS 2 | MAFF | Variety | 0 | 2 |  | 0 | 0 | 0 | 2 | 0 | 0
| OP.2.1.2a.2 |  |  | Three additional climate resilient varieties of maize released | [6 empty] | CS 2 | MAFF | Variety | 0 | 1 |  | 0 | 0 | 0 | 1 | 0 | 0
11 | OP.2.2 | 2b. |  | 2b. 40,000 farmers (of whom 16,000 are women) trained in CSA and agribusiness development skills, of which 50% are SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0). |  | 68500 | Add next | Pon Han | PPMS annual reports |  | CS 2 | MAFF |  | No BL | 40000 | 5 | 0 | 2500 | 10000 | 9500 | 9000 | 9000 |  |  | 16.98 | 0.849 | 1.25 | 0.15196 | 0.0090512 |  | 1.25 | 0.54554 | 0.02873 |  | 2.5 | 17.6775 | 0.88678
| OP.2.2.2b.1 |  |  | farmers (of whom 16,000 are women) trained in CSA | [8 empty] | Person | No BL | 20000 |  | 0 | 501 | 5000 | 5000 | 5000 | 4499
| OP.2.2.2b.2 |  |  | farmers (of whom 16,000 are women) trained in Agribusiness Development Skills (ADS) | [8 empty] | Person | No BL | 20000 |  | 0 | 250 | 4937.5 | 4937.5 | 4937.5 | 4937.5
| OP.2.2.2b.3 |  |  | farmers are trained on SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0) | [8 empty] | Person | 0 | 20000 |  | 0 | 875 | 4781.25 | 4781.25 | 4781.25 | 4781.25
|  |  |  | farmers are trained on CAMGAP compliant | [9 empty] | No BL | 500 |  | 0 | 250 | 250 | 0 | 0 | 0
|  |  |  | 20% of total 40,000 farmers are trained on Agricultural farm Machinery | [9 empty] | No BL | 8000 |  | 0 | 496 | 2376 | 2000 | 2000 | 1128
12 | OP.2.3 | 2c. |  | 2c. 27 FWUCs/FWUGs made operational and 500 FWUC/FWUG members (of which 30% women) developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM |  |  | Add next | Soeur Sophorn | PPMS annual reports |  | CS 2 | MAFF | FWUC | 0 | [12 empty] | 1.5 | 0.42655 | 0.031901 |  |  |  | 0.036216
| OP.2.3.2c.1 | 2C1 |  | 27 FWUCs/FWUGs made operational and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM |  |  |  | Soeur Sophorn - CS2 |  |  | CS 2 | MAFF | FWUC | 0 | 27 | 3 | 0 | 10 | 8 | 9 | 0 | 0 |  |  | 12.1 | 0.363 | 0.75 | 0.26155 | 0.019151 |  | 0.75 | 0.37671 | 0.022605 |  | 1.5 | 12.7383 | 0.40476
| OP.2.3.2c.2 | 2C2 |  | 500 FWUC/FWUG members developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). |  | 500 |  |  |  |  | CS 2 | MAFF | Person | 0 | 500 | 3 | 0 | 100 | 100 | 100 | 100 | 100 |  |  | 10 | 0.3 | 0.75 | 0.165 | 0.01275 |  | 0.75 | 0.1937 | 0.013611 |  | 1.5 | 10.3587 | 0.32636
13 | OP.2.4 | 2d. |  | 2d. 4 provincial agricultural development centers and 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  | Add next | Phai Sok Heng | PPMS annual reports |  | CS 2 | MAFF |  | 0 | 8 |  |  | 6 | 6 | 2 | 0 | 0 |  |  |  |  | 1 | 0.97 | 0.02336 |  |  | 1.2869 | 0.029698
| OP.2.4.2d.1 | 2d1 |  | 4 provincial agricultural development centers made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | PADC | 0 | 4 | 2 | 2019: 0; 2020: 3; 2022: 1 |  | 26.3 | 0.526 | 0.5 | 0.45175 | 0.011265 |  | 0.5 | 0.57202 | 0.01367 |  | 1 | 27.3238 | 0.55094
| OP.2.4.2d.2 | 2d2 |  | 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | Workshop | 0 | 4 | 2 | 2019: 0; 2020: 3; 2022: 1 |  | 30.3 | 0.606 | 0.5 | 0.51825 | 0.012095 |  | 0.5 | 0.71488 | 0.016028 |  | 1 | 31.5331 | 0.63412
| OP.3 |  |  | 3. Enabling environment for climate friendly agribusiness enhanced | 20000 | 20080 | [9 empty] | 15 | [9 empty] | 1.395 | 7.5 | 0.93075 | 0.019715 |  | 7.5 | 2.1221 | 0.045007 |  |  | 3.0528 | 1.4597
14 | OP.3.1.a | 3a. |  | 3a. Climate-smart and gender-responsive agribusiness policy for target commodities, including a PPP framework focusing on agribusinesses formulated (2017 baseline: 0).** |  |  | Add next | Hoeung Hun / Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | Policy |  | 6 | 2 | 0 | 0 | 1.9 | 1.9 | 1.6 | 0.5 |  |  | 19 | 0.38 | 0.5 | 0.37325 | 0.007465 |  | 0.5 | 0.7225 | 0.01445 |  | 1 | 20.0957 | 0.40192
| OP.3.1.3a.1 |  |  | Agribusiness and Gender responsive policy | [6 empty] | CS 2 | MAFF | Policy | 0 | 1 |  | 2019: 0; 2021: 0.4; 2022: 0.4; 2023: 0.1
| OP.3.1.3a.2 |  |  | CSA Policy | [6 empty] | CS 2 | MAFF | Policy | 0 | 1 |  | 0 |  | 0.3 | 0.3 | 0.3 | 0.1
| OP.3.1.3a.3 |  |  | Agro-Industry Policy | [6 empty] | CS 2 | MAFF | Policy | 0 | 1 |  | 0 |  | 0.3 | 0.3 | 0.3 | 0.1
| OP.3.1.3a.4 |  |  | Contract Farming Inclusive Agribusiness Policy | [6 empty] | CS 2 | MAFF | Policy | 0 | 1 |  | 0 |  | 0.3 | 0.3 | 0.3 | 0.1
| OP.3.1.3a.5 |  |  | Proclamation/Prakas Supporting AC’s Law | [6 empty] | CS 2 | MAFF | Policy | 0 | 1 |  | 0 |  | 0.3 | 0.3 | 0.3 | 0.1
| OP.3.1.3a.6 |  |  | PPP-Initiative Agribusiness Policy | [6 empty] | CS 2 | MAFF | Policy | 0 | 1 |  | 0 |  | 0.3 | 0.3 | 0.3 | 0.1
15 | OP.3.2 | 3b. |  | 3b. CAMGAP for tropical fruit and organic fertilizers endorsed as national standard for tropical fruit and organic fertilizers (2017 baseline: 0). |  |  | Add next | Hoeung Hun / Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | Standard | 0 | 2 | 2 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2 |  |  | 14.5 | 0.29 | 0.5 | 0.095 | 0.0019 |  | 0.5 | 0.21743 | 0.0043485 |  | 1 | 14.8124 | 0.29625
| OP.3.3b.1 |  |  | CAMGAP for tropical fruit endorsed as national standard for tropical fruit (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | Standard | 0 | 1 |  | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1
| OP.3.3b.2 |  |  | CAMGAP for organic fertilizers endorsed as national standard for organic fertilizers (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | Standard | 0 | 1 |  | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1
16 | OP.3.3 | 3c. |  | 3c. 50 staff, including 30% women, from financial institutions trained in CSA and green finance (2017 baseline: 0). |  | 50 | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF | Person | 0 | 50 | 2 | 0 | 0 | 15 | 20 | 15 | 0 |  |  | 11.5 | 0.23 | 0.5 | 0.3 | 0.006 |  | 0.5 | 0.5123 | 0.010246 |  | 1 | 12.3123 | 0.24625
| OP.3.3C.1 |  |  | 50 staff, including 30% women, from financial institutions trained in CSA (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | Person | 0 | 25 |  | 0 | 0 | 7.5 | 10 | 7.5 | 0
| OP.3.3C.2 |  |  | 50 staff, including 30% women, from financial institutions trained in Green finance (2017 baseline:0). | [6 empty] | CS 2 | MAFF | Person | 0 | 25 |  | 0 | 0 | 7.5 | 10 | 7.5 | 0
17 | OP.3.4 | 3d. |  | 3d. 30 agribusinesses, including 30% women-led and/or owned,*** trained on green finance and CSA (2017 baseline: 0). |  | 30 | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF |  |  | 30 | 2 | 0 | 0 | 10 | 10 | 10 | 0 |  |  | 5.4 | 0.108 | 0.5 | 0.036 | 0.00072 |  | 0.5 | 0.19835 | 0.003967 |  | 1 | 5.6344 | 0.11269
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on Green finance (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | Person | 0 | 15 |  | 0 | 0 | 5 | 5 | 5 | 0
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on CSA (2017 baseline: 0). | [6 empty] | CS 2 | MAFF | Woman | 0 | 15 |  | 0 | 0 | 5 | 5 | 5 | 0
18 | OP.3.5 | 3e. |  | 3e. 20,000 households, including 20,000 women, provided with information on climate risk sharing instruments (2017 baseline: 0). | 20000 | 20000 | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | Household | 0 | 20000 | 2 | 0 | 0 | 5500 | 6000 | 6000 | 2500 |  |  | 4.5 | 0.09 | 0.5 | 0.009 | 0.00018 |  | 0.5 | 0.2074 | 0.004148 |  | 1 | 4.7164 | 0.094328
19 | OP.3.6 | 3f. |  | 3f. ICT platform for climate friendly agribusiness established in Kampong Cham province (2017 baseline: 0). |  |  | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | ICT Platform | 0 | 1 | 2 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  |  | 4.5 | 0.09 | 0.5 | 0.0075 | 0.00015 |  | 0.5 | 0.0075 | 0.00015 |  | 1 | 4.515 | 0.0903
| OP.3.7 | 3g | No DMF | Supporting Climate Risk Management through Information and Communication Technologies (ICT) |  |  | Add next | [5 empty] | ICT Platform |  | 1 | 3 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  |  | 6.9 | 0.207 | 0.75 | 0.11 | 0.0033 |  | 0.75 | 0.25657 | 0.0076973
[29 empty] | #DIV/0! |  | 0 |  | #DIV/0!
GENDER AND SOCIAL DIMENSIONS
Output 1: Critical agribusiness value chain infrastructure improved and made climate resilient
Gender Objectives. 1.1 Ensure critical agribusiness value chain infrastructure is responsive to the needs of women and men
20 |  | 1.1.1 |  | 1.1.1 (i) Women are 40% of participants– aggregate basis (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3; 30% female participation in similar activities currently); (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y4 |  |  |  | No BL | [12 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  | 1.1.1.i |  | (i) Women are 40% of participants– aggregate basis (point of reference: female population: | [6 empty] | CS 1 | MAFF | % | No BL | 40 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (i) Women are 54% of participants in subproject 1; | [6 empty] | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 47% of participants in subproject 2 | [6 empty] | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 48% of participants in subproject 3 | [6 empty] | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 30% female participation in similar activities currently); | [6 empty] | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  |  |  | 0
|  | 1.1.1.ii |  | (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems | [6 empty] | CS 1 | MAFF | Person | No BL | 50000 | [11 empty] | 0 |  |  |  | 0
Gender Objectives. 1.2. Enhance income generating opportunities for women
21 |  | 1.2.1 |  | 1.2.1 At least 25% of workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y6 | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by skilled and type of work. | [6 empty] | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by unskilled and type of work. | [6 empty] | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  |  |  | 0
|  |  |  | Workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) | [6 empty] | CS 1 | MAFF | % | No BL | 17-46 | [11 empty] | 0 |  |  |  | 0
22 |  | 1.2.2 |  | 1.2.2 At least 30% women FWUC members developed capacity to operate and maintain irrigation schemes. |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
Gender Objectives. 1.3 Increase the uptake of biodigesters
23 |  | 1.3.1 |  | 1.3.1 At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y4 | CS 1 | MAFF | [14 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). | [6 empty] | CS 1 | MAFF | Woman | 5721 | 40000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters installed (baseline: 5,721 women). | [6 empty] | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of compost huts installed (baseline: 5,721 women). | [6 empty] | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 |  |  |  | 0
24 |  | 1.3.2 |  | 1.3.2 Number and percentage of women active agents. |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y4 | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | Number of women active agents. |  |  | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | Percentage of women active agents. |  |  | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 |  |  |  | 0
Output 2: Climate smart agriculture and agribusiness promoted
Gender Objectives. 2.1 Strengthen women farmers’ (individual and member of cooperatives) involvement along climate- friendly agribusiness value chains
25 |  | 2.1.1 |  | 2.1.1 Number and % of women farmers involved |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF |  | No BL | [12 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | Number of women farmers involved |  |  | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | % of women farmers involved |  |  | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 |  |  |  | 0
26 |  | 2.1.2 |  | For 2.1.2 (1) and (3): Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA and agribusiness development skills (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3 with almost all of them farming; 30% female participation in similar activities currently). |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | [16 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA . | [6 empty] | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in Agribusiness Development Skills | [6 empty] | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 54% of total participants in subproject 1 | [6 empty] | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 47% of total participants in subproject 2 | [6 empty] | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 48% of total participants in subproject 3 | [6 empty] | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 |  |  |  | 0
|  |  |  | 30% female participation in similar activities currently | [6 empty] | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  |  |  | 0
27 |  |  |  | For 2.1.2 (2): (i) Number and percentage of women farmers trained in each event; (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y5 | [16 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (i) Number of women farmers trained in each event(baseline: 0). | [6 empty] | CS 1 | MAFF | Woman | 0 | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Percentage of women farmers trained in each event(baseline: 0). | [6 empty] | CS 1 | MAFF | % | 0 | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). | [6 empty] | CS 1 | MAFF | % | 0 | 40 | [11 empty] | 0 |  |  |  | 0
28 |  |  |  | 2.1.3 (i) Number and type of activities conducted; (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. |  |  | Focus on Agricultural Cooperatives with a majority of female members | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y2 |  |  |  | No BL | [12 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted; | [6 empty] | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. | [6 empty] | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
Gender Objectives. 2.2 Ensure female staff benefit from capacity- building activities related to climate- friendly agribusiness value chains
29 |  | 2.2.1 |  | 2.2.1 25% at national level and 20% at local levels women participants (aggregate basis). |  |  | Add next | Kol Prapey / Peter J. |  | Q1 Y2 – Q4 Y6 | CS 1 |  |  | No BL | [12 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | 25% at national level of women participants (aggregate basis). | [6 empty] | CS 1 | MAFF | Woman | No BL | 25 | [11 empty] | 0 |  |  |  | 0
|  |  |  | 20% at local levels of women participants (aggregate basis). | [6 empty] | CS 1 | MAFF | Woman | No BL | 20 | [11 empty] | 0 |  |  |  | 0
Output 3: Enabling environment for climate friendly agribusiness enhanced
Gender Objectives 3.1. Institutionalize gender mainstreaming in the climate- friendly agribusiness value chains sector
30 |  | 3.1.1 |  | 3.1.1 Report prepared with clear recommendations based on detailed gender analysis of the 4 value chains. (Baseline: 0) |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q3 Y1 | CS 1 | MAFF | Report | 0 | 10 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
31 |  | 3.1.2 |  | 3.1.2 Key recommendations from gender analysis of 4 targeted value chains integrated in the Agribusiness Policy ( CSA Policy, Agro-Industry Policy, Contract Farming Inclusive Agribusiness Policy, Proclamation/Prakas Supporting AC’s Law, PPP-Initiative Agribusiness Policy). (Baseline: NA) |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q2 Y3 | CS 1 | MAFF | Recommendation | No BL | 10 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
32 |  | 3.1.3 |  | 3.1.3 Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; number of people trained disaggregated by sex. (Baseline: 0) |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | [14 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; (Baseline: 0) |  |  | To be determined during the reporting period, while the session completed. | [5 empty] | Session | 0 | # | [11 empty] | 0 |  |  |  | 0
|  |  |  | Number of people trained disaggregated by sex on gender equality in climate-friendly agribusiness value chains; (Baseline:0) |  |  | To be determined during the reporting period, while the session completed. | [5 empty] | Person | 0 | # | [11 empty] | 0 |  |  |  | 0
33 |  | 3.1.4 |  | 3.1.4 MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), the AC and the WFN are aware of the GAP activities |  |  | To be determined during the reporting period. | Kol Prapey / Peter J. | Project Recoding | Q2 Y2 – Q4 Y7 | CS 1 | MAFF | % | No BL | # | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
Gender Objectives 3.2 Enhance access to green finance for women involved in agribusiness value chains
34 |  | 3.2.1 |  | 3.2.1 (i)Number and type of activities conducted; (ii) types of communication channels and materials used; (iii) 15 female staff in financial institutions trained in CSA lending and green finance (or 30% of total staff trained are women); (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on green finance and CSA; (v) 20,000 women provided with information on climate risk sharing instruments. |  |  | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | CS 1 | MAFF |  | No BL | # | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted on climate risk sharing instruments. |  |  |  |  | Project Interim Recoding |  |  |  | Activity | No BL | # | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (ii) Types of communication channels and materials used on climate risk sharing instruments. |  |  |  |  | Project Recoding |  |  |  | Channel | No BL | # | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in CSA lending are women); |  |  |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in Green finance (or 30% of total staff trained) are women; |  |  |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  | 0% |  | 0
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on Green finance;. |  |  |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on CSA; |  |  |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (v) 20,000 women provided with information on climate risk sharing instruments. |  |  |  |  | Project Recoding |  |  |  | Woman | No BL | 20000 | [11 empty] | 0 |  | 0% |  | 0 |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[29 empty] | #DIV/0! |  |  |  | #DIV/0!
[11 empty] | CS# |  | Units
[11 empty] | CS 1 |  | Person
[11 empty] | CS 2 |  | Km
[11 empty] | CS 3 |  | Ha
[11 empty] | CS 4 |  | %
[11 empty] | CS 5 |  | Pond
[11 empty] | MAFF |  | System
[11 empty] | MOWRAM |  | Kg
[11 empty] | MRD |  | Tone
[11 empty] | MEF |  | Tone/Ha
[11 empty] | Other |  | Woman
Household
AC
Sample
USD
Biodigesters
Compost hut
Variety
Irrigation System
FWUC
PADC
Workshop
Policy
Standard
No.
Assessment
Staff
Household
ICT Platform
Schemes
Document
Report
Recommendation
Session
Activity
Channel
Riel
Euro
Time
Piece
Set
LS
Book
Unit
Table
Laptop
Piece
Other
Note on D7: User: Several individual meetings with Mr. Vanarath - Head of DoP office/MAFF, and Mr. Mak Many - Head of DoP/MAFF, there is neither indicators codes related, nor database system.
Note on E10: XMG: PAM, p. 52, 53.
Note on E60: User: Just requested by Agro-Industry Dept., MAFF in 2021.
Note on E80: XMG: PAM, p. 47-50 Gender activities/actions, 1.1.1 Involve women and Women Farmers Network (WFN) representatives actively and meaningfully in each individual event for all consultations and planning activities related to improvement and climate resiliency of critical infrastructure supported by the project. - This would mean paying attention to the following aspects: convenient time, adequate venue, information sharing with visual aids/illustrations, having female facilitators, child supervision arrangements, etc.
Note on E88: XMG: Gender activities/actions, 1.2.1 Ensure women benefit from jobs created by the project related to infrastructure construction/rehabilitation as well as operation and maintenance. - This would mean that information about such employment opportunities will be communicated through adequate channels to reach out women in the communities. - Core labor standards will be complied with (equal pay for work of equal value, no child labor) for all civil works related to the project. - Other measures that are needed will be taken (e.g. child supervision arrangements even if informal) so that interested women can grasp such opportunities.
Note on E92: XMG: Gender activities/actions, 1.2.2 Provide skills enhancement for women in infrastructure related construction/rehabilitation (e.g. masonry skills for bio-digesters construction), and operation and maintenance (e.g. small-scale irrigation schemes).
Note on E94: XMG: Gender activities/actions, 1.3.1 As part of the promotion campaigns about biodigesters and other renewable energy solutions, raise awareness among women and men in the communities about the benefits for value chain improvement/climate change but also for greater gender equality (time saving, drudgery reduction, improved health).
Note on E98: XMG: Gender activities/actions, 1.3.2 Involve women as active agents in the promotion campaigns on the use of renewable energy solutions.
Note on E103: XMG: Gender Activities/Action, 2.1.1 Involve women farmers (and the WFN) actively in the selection and multiplication of climate resilient crops varieties and build on their local knowledge in this area.
Note on E106: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (1) agricultural extension and technical capacity-building activities including those related to climate change adaptation and mitigation;
Note on E113: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (2) trainings on how to operate and maintain a range of agricultural machinery; (3), management (including leadership, negotiation) and business skills trainings. - This would mean paying special attention to the following aspects: adequate venue, timing, duration, way that invitation is being done (not to head of household as is currently being done), use of visual aids and other illustrated materials, use of female facilitators/demonstrators and extension agents, child care arrangements even if informal, etc.
Note on E117: XMG: Gender Activities/Actions, 2.1.3 Strengthen linkages between women-led and/or owned farms/enterprises* and agribusiness industry For support provided to cooperatives: preferential support will be given to agricultural cooperatives with a majority of female members. .1.4 Work with the WFN to identify context-appropriate ways to address burden of household and care work for women farmers, especially female headed households, which prevents them to increasingly participate and move up along the value chains.
Note on E126: XMG: Gender Activities/Actions, 3.1.1 At project inception, refine the gender analysis for each of the 4 targeted value chains and develop a set of clear policy and program recommendations to strengthen women farmers’ involvement along the different value chains. Ensure that capacity is built within MAFF/ Gender & Children Project Support Unit (GCPSU) for gender responsive value chain analysis and develop methodology/guidelines that can be used in future analysis.
Note on E127: XMG: Gender Activities/Actions, 3.1.2 Integrate key recommendations from the above- mentioned gender analysis of value chains and key features of the MAFF Gender Policy into the Agribusiness policy and other related documents prepared under the project. - This would also mean that gender stakeholders (MAFF GCPSU representatives, gender focal points, and WFN) participate in policy committees and meetings.
Note on E128: XMG: Gender Activities/Actions, 3.1.3 Integrate a session on gender equality in climate- friendly agribusiness value chains (based on gender analysis report mentioned above) into the training and awareness raising activities for relevant project stakeholders (i.e. relevant departments in MAFF, agricultural extension agents, local leaders and government officials, GCPSU and Gender Focal Points, and WFN).
Note on E131: XMG: Gender Activities/Actions, 3.1.4 Actively involve the MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), and the WFN and the Agricultural Cooperatives as key partners in project implementation and monitoring, especially for the GAP activities. - This also entails partnering with the WFN as facilitators/resource persons for agricultural extension and technical capacity-building, awareness-raising and information sharing targeted at farmers including provision of market information. - WFN social media pages should be used as one of the ways to disseminate information to women farmers.
Note on E133: XMG: Gender Activities/Actions, 3.2.1 Raise awareness among women farmers/ cooperative members, women-led and/or owned enterprises, and female staff in financial institutions using adequate channels about existing credit facilities, green financing including crop insurance and required formalities to access these
Note on T23: User: Take 1 out is Ko Eurt Irrigation system in Batheay district, KPC, with reason due to PDoWRAM is repairing under the MoWRAM budget.
Note on AA8: User: Linked from DMF sheet of Physical Progress.
Note on AD8: User: Linked from DMF sheet of Physical Progress.
Note on AH8: User: Linked from DMF sheet of Physical Progress.
in JV with SBK Research and Development
Implemented by

## 1. MEF Progress Interpretation (hidden)
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS
MEF FORMAT
Status : January though Deember 2021
|  | . |  | Overall Accumulated Physical Progress as of Project Implementation To-date
ACTIVITY/Implementing Agency |  | Assigned Weight | Progress 31/12/20 | 15/01/21 |  |  | 15/02/21 |  |  | 15/03/21 |  |  | 15/04/21 |  |  | 15/05/21 |  |  | 15/06/21 |  |  | 15/07/21 |  |  | 15/08/21 |  |  | 15/09/21 |  |  | 15/10/21 |  |  | 15/11/21 |  |  | 15/12/21 |  |  | % Cumulative Progress to date (2020, 2021)
|  |  |  | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period | Solely progress in this month | Physical progress vs AWPB 2021 | Accumulative as of reporting period
1 | Establish project PMU & PRC | 0.5% | 0.5 | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 0.5 | 0 |  | 0.5 | [12 empty] | 7
2 | Recruitment of Consultants | 0.5% | 0.43 | 0.43 |  | 0.43 |  |  | 0.45 |  |  | 0.45 |  |  | 0.45 |  |  | 0.45 |  |  | 0.45 |  |  | 0.45 | 0 |  | 0.45 | [12 empty] | 4.44
3 | PMU Operation | 4% | 1 | 1.12 |  | 1.12 |  |  | 1.12 |  |  | 1.3 |  |  | 1.33 |  |  | 1.36 |  |  | 1.36 |  |  | 1.36 | 0 |  | 1.36 | [12 empty] | 12.43
4 | Social Safeguards and Resettlement | 2% | 0.03 | 0.04 |  | 0.04 |  |  | 0.04 |  |  | 0.05 |  |  | 0.06 |  |  | 0.07 |  |  | 0.03 |  |  | 0.03 | 0 |  | 0.03 | [12 empty] | 0.42
5 | Environmental Management | 2% | 0.02 | 0.03 |  | 0.03 |  |  | 0.03 |  |  | 0.04 |  |  | 0.04 |  |  | 0.04 |  |  | 0.03 |  |  | 0.03 | 0 |  | 0.03 | [12 empty] | 0.32
6 | Gender | 1% | 0.03 | 0.03 |  | 0.03 |  |  | 0.03 |  |  | 0.04 |  |  | 0.04 |  |  | 0.04 |  |  | 0.02 |  |  | 0.02 | 0.01 |  | 0.03 | [12 empty] | 0.32
7 | Implementation of Output 1 - MAFF | 27% | 1.4295 | 0.46979 |  | 1.8993 | 0.20301 |  | 2.1023 | 0.72998 |  | 2.8323 | 1.1933 |  | 4.0256 | 1.991 |  | 6.0165 | 2.194 |  | 8.2105 | 0.00219 |  | 8.2127 | 0.04941 |  | 8.2621 | [12 empty] | 143%
8 | Implementation of Output 1 - MOWRAM | 13.5% | 0.01509 | 2.2945 |  | 2.3096 | 0.23428 |  | 2.5439 | 1.0884 |  | 3.6323 | 0 |  | 3.6323 | 0 |  | 3.6323 | 1.6762 |  | 5.3084 | 0 |  | 5.3084 | 0 |  | 5.3084 | [12 empty] | 1.509%
9 | Implementation of Output 1 - MRD | 13.5% | 2.1075 | 0.32289 |  | 2.4304 | 0.14781 |  | 2.5782 | 0.52675 |  | 3.105 | 1.4015 |  | 4.5065 | 0.5262 |  | 5.0327 | 0.56233 |  | 5.595 | 0.54416 |  | 6.1392 | 1.068 |  | 7.2072 | [12 empty] | 210.8%
10 | Implementation of Output - Unassigned | 4.5% | 0.2065 | 0.018229 |  | 0.22473 | 0 |  | 0.22473 | 0.019792 |  | 0.24452 | 0 |  | 0.24452 | 0 |  | 0.24452 | 0 |  | 0.24452 | 0 |  | 0.24452 | 0 |  | 0.24452 | [12 empty] | 2.1611
11 | Implementation of Output 2 - MAFF | 12.6% | 2.2935 | 0.24118 |  | 2.5347 | 0.14755 |  | 2.6822 | 0.42273 |  | 3.105 | 1.9334 |  | 5.0384 | 0.543 |  | 5.5814 | 0.22899 |  | 5.8104 | 0.0090112 |  | 5.8194 | 0.10143 |  | 5.9208 | [12 empty] | 229.3%
12 | Implementation of Output 2 - MOWRAM | 5.4% | 0.663 | 0.584 |  | 1.247 | 0.40156 |  | 1.6486 | 1.2961 |  | 2.9446 | 0.069722 |  | 3.0143 | 0.016111 |  | 3.0304 | 0.23861 |  | 3.2691 | 0.00055556 |  | 3.2696 | 0.0081111 |  | 3.2777 | [12 empty] | 66.3%
13 | Implementation of Output 3 - MAFF | 13.5% | 1.395 | 0 |  | 1.395 | 0 |  | 1.395 | 0.1465 |  | 1.5415 | 0.37 |  | 1.9115 | 0.2 |  | 2.1115 | 1.255 |  | 3.3665 | 0.013 |  | 3.3795 | 0.336 |  | 3.7155 | [12 empty] | 139.5%
| TOTAL | 100% | 0.1012 | 14.0895 | 14.0895 | 14.1907 | 1.1542 | 15.2437 | 15.3449 | 4.4402 | 19.6839 | 19.7851 | 5.008 | 24.6919 | 24.7931 | 3.3163 | 28.0082 | 28.1094 | 6.0851 | 34.0932 | 34.1944 | 0.56891 | 34.6621 | 34.7633 | 1.5729 | 36.2351 | 36.3363 | [12 empty] | 10.12%
in JV with SBK Research and Development
Implemented by

## 1. MEF Progress
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS
MEF FORMAT
Status : January though Deember 2021
|  | . | [31 empty] | 2020 | 2021
ACTIVITY/Implementing Agency |  | Assigned Weight | Overall MEF Accumulated Physical Progress as of Project Implementation to-date | [13 empty] | As of June 2021 |  | As of July 2021 |  | As of August 2021 |  | As of Sept 2021 |  | As of Oct. 2021 |  | As of Nov. 2021 |  | As of Dec. 2021 |  |  | MEF | Assigned Weighted | Jan. - Dec. | Jan. - Jun | Jan. - July | Activity | IPIU | Assigned Weighted | Actual | Weighted Progress
|  |  | Progress 31/12/20 |  | As of 15/01/21 | As of 15/02/21 | As of 15/03/2021 | As of 15/04/2021 | As of 15/05/2021 | As of 15/06/2021 | As of 15/07/2021 | As of 15/08/2021 | As of 15/09/2021 | As of 15/10/2021 | As of 15/11/2021 | As of 15/12/2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | % Cumulative Progress to date (2020, 2021) | Physical progress vs AWPB 2021 | No. | Activity |  | Weighted Progress (%) | Weighted Progress (%) | Weighted Progress (%) |  |  |  | Progress
1 | Establish project PMU & PRC | 0.5% | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 |  | 0.5 | 3.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 |  |  |  |  | 1 | Establish project PMU & PRC | 0.5% | 0.5 | 0.5 | 0.5 | PMU | MAFF | 5% | 4620 | 2.31
2 | Recruitment of Consultants | 0.5% | 0.43 |  | 0.43 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 |  |  | 0.45 |  | 0.45 | 3.13 | 0.45 | 0.02 | 0.45 | 0.02 | 0.45 | 0.02 |  |  |  |  | 2 | Recruitment of Consultants | 0.5% | 0.43 | 0.45 | 0.45 | Safeguards and Gender | All | 5% | 160 | 0.08
3 | PMU Operation | 4% | 1 |  | 1.12 | 1.12 | 1.3 | 1.33 | 1.36 | 1.36 | 1.36 | 1.36 | 1.36 | 1.36 |  |  | 1.36 |  | 1.36 | 8.95 | 1.36 | 0.36 | 1.36 | 0.36 | 1.36 | 0.36 |  |  |  |  | 3 | PMU Operation | 4% | 1 | 1.36 | 1.36 | Output 1 | MAFF | 27% | 3040.9234 | 8.2105
4 | Social Safeguards and Resettlement | 2% | 0.03 |  | 0.04 | 0.04 | 0.05 | 0.06 | 0.07 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  |  | 0.03 |  | 0.03 | 0.32 | 0.03 | 0 | 0.03 | 0 | 0.03 | 0 |  |  |  |  | 4 | Social Safeguards and Resettlement | 2% | 0.03 | 0.03 | 0.03 |  | MOWRAM | 13.5% | 3932.1799 | 5.3084
5 | Environmental Management | 2% | 0.02 |  | 0.03 | 0.03 | 0.04 | 0.04 | 0.04 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  |  | 0.03 |  | 0.03 | 0.24 | 0.03 | 0.01 | 0.03 | 0.01 | 0.03 | 0.01 |  |  |  |  | 5 | Environmental Management | 2% | 0.02 | 0.03 | 0.03 |  | MRD | 13.5% | 4144.4667 | 5.595
6 | Gender | 1% | 0.03 |  | 0.03 | 0.03 | 0.04 | 0.04 | 0.04 | 0.02 | 0.02 | 0.03 | 0.03 | 0.03 |  |  | 0.02 |  | 0.02 | 0.22 | 0.03 | 0 | 0.03 | 0 | 0.03 | 0 |  |  |  |  | 6 | Gender | 1% | 0.03 | 0.02 | 0.02 | Output 2 | MAFF | 12.6% | 4611.4134 | 5.8104
7 | Implementation of Output 1 - MAFF | 27% | 1.4295 |  | 1.8993 | 2.1023 | 2.8323 | 4.0256 | 6.0165 | 8.2105 | 8.2127 | 8.2621 | 8.6336 | 9.0237 |  |  | 8.2105 |  | 8.2127 | 6.7832 | 8.2621 | 6.8326 | 8.6336 | 7.2041 | 9.0237 | 7.5941 |  |  |  |  | 7 | Implementation of Output 1 - MAFF | 27% | 1.4295 | 8.2105 | 8.2127 |  | MOWRAM | 5.4% | 6053.8066 | 3.2691
8 | Implementation of Output 1 - MOWRAM | 13.5% | 0.01509 |  | 2.3096 | 2.5439 | 3.6323 | 3.6323 | 3.6323 | 5.3084 | 5.3084 | 5.3084 | 5.3362 | 5.3362 |  |  | 5.3084 |  | 5.3084 | 5.2934 | 5.3084 | 5.2934 | 5.3362 | 5.3211 | 5.3362 | 5.3211 |  |  |  |  | 8 | Implementation of Output 1 - MOWRAM | 13.5% | 0.01509 | 5.3084 | 5.3084 | Output 3 | MAFF | 13.5% | 2493.7037 | 3.3665
9 | Implementation of Output 1 - MRD | 13.5% | 2.1075 |  | 2.4304 | 2.5782 | 3.105 | 4.5065 | 5.0327 | 5.595 | 6.1392 | 7.2072 | 8.0592 | 9.4168 |  |  | 5.595 |  | 6.1392 | 4.0317 | 7.2072 | 5.0997 | 8.0592 | 5.9517 | 9.4168 | 7.3093 |  |  |  |  | 9 | Implementation of Output 1 - MRD | 13.5% | 2.1075 | 5.595 | 6.1392 |  | Un Assigned | 4.5% | 543.3796 | 0.24452
10 | Implementation of Output - Unassigned | 4.5% | 0.2065 |  | 0.22473 | 0.22473 | 0.24452 | 0.24452 | 0.24452 | 0.24452 | 0.24452 | 0.24452 | 0.24452 | 0.24452 |  |  | 0.24452 |  | 0.24452 | 0.038021 | 0.24452 | 0.038021 | 0.24452 | 0.038021 | 0.24452 | 0.038021 |  |  |  |  | 10 | Implementation of Output - Unassigned | 4.5% | 0.2065 | 0.24452 | 0.24452 | TOTAL |  | 100% | 29599.8733 | 0.34194
11 | Implementation of Output 2 - MAFF | 12.6% | 2.2935 |  | 2.5347 | 2.6822 | 3.105 | 5.0384 | 5.5814 | 5.8104 | 5.8194 | 5.9208 | 7.2018 | 8.5469 |  |  | 5.8104 |  | 5.8194 | 3.5259 | 5.9208 | 3.6273 | 7.2018 | 4.9083 | 8.5469 | 6.2534 |  |  |  |  | 11 | Implementation of Output 2 - MAFF | 12.6% | 2.2935 | 5.8104 | 5.8194
12 | Implementation of Output 2 - MOWRAM | 5.4% | 0.663 |  | 1.247 | 1.6486 | 2.9446 | 3.0143 | 3.0304 | 3.2691 | 3.2696 | 3.2777 | 3.484 | 3.7006 |  |  | 3.2691 |  | 3.2696 | 2.6066 | 3.2777 | 2.6147 | 3.484 | 2.821 | 3.7006 | 3.0376 |  |  |  |  | 12 | Implementation of Output 2 - MOWRAM | 5.4% | 0.663 | 3.2691 | 3.2696
13 | Implementation of Output 3 - MAFF | 13.5% | 1.395 |  | 1.395 | 1.395 | 1.5415 | 1.9115 | 2.1115 | 3.3665 | 3.3795 | 3.7155 | 4.779 | 5.8957 |  |  | 3.3665 |  | 3.3795 | 1.9845 | 3.7155 | 2.3205 | 4.779 | 3.384 | 5.8957 | 4.5007 |  |  |  |  | 13 | Implementation of Output 3 - MAFF | 13.5% | 1.395 | 3.3665 | 3.3795
| TOTAL (%) | 100% | 10.1201 |  | 14.1907 | 15.3449 | 19.7851 | 24.7931 | 28.1094 | 34.1944 | 34.7633 | 36.3363 | 40.1384 | 44.5645 |  |  | 34.1944 | 24.0743 | 34.7633 | 24.6432 | 36.3363 | 26.2162 | 40.1384 | 30.0183 | 44.5645 | 34.4444 | [5 empty] | TOTAL (%) | 100% | 0.1012 | 0.34194 | 0.34763
|  |  | 8.955 |  | 11.3931 | 12.5093 | 16.7218 | 21.6901 | 24.9668 | 30.9168 | 31.4857 | 33.2531 | 37.0275
3.2777
| Original as of July 2021 (Dead formulation) | 100% | 13.38 |  | 16.17 | 17.57 | 21.45 | 25.42 | 27.28 | 30.92 | 31.31 | [20 empty] | IAs | Assigned Weighted | 2020 | 2021
| Deviation | 0 | 3.2599 | 0% | 1.9793 | 2.2251 | 1.6649 | 0.62692 | -0.82937 | -3.2744 | -3.4533 | [20 empty] | Activity |  | Jan. - Dec. | Jan. - Jun | Jan. - July
[34 empty] | Weighted Progress (%) | Weighted Progress (%) | Weighted Progress (%)
| Original as of aUG 2021 (Dead formulation) |  | 8.955 |  | 11.3931 | 12.5093 | 16.7218 | 21.6901 | 24.9668 | 30.9168 | 31.4857 | 33.291 | 37.0654 | [18 empty] | MAFF | 59 | 5.2768 | 18.2997 | 18.3241
| Deviation |  | -1.1651 |  | -2.7976 | -2.8357 | -3.0634 | -3.103 | -3.1426 | -3.2777 | -3.2777 | -3.0452 | -3.073 | [18 empty] | MOWRAM | 21 | 0.67809 | 8.5775 | 8.5781
[32 empty] | MRD | 15 | 2.1075 | 5.595 | 6.1392
[32 empty] | Undecided | 5 | 0.2065 | 0.24452 | 0.24452
[32 empty] | Total | 100 | 0.082689 | 0.32717 | 0.33286
[19 empty] | 31.31% | 17.93% | 31.31% | 17.93% | [9 empty] | DMF | Assigned Weighted | 2020 | 2021
[19 empty] | 3445% | 2446% | 3602% | 2604% | 4014% | 3002% | 4456% | 3444% | 0% | 0% | 0% | 0% |  | Activity |  | Jan. - Dec. | Jan. - Jun | Jan. - July
[34 empty] | Weighted Progress (%) | Weighted Progress (%) | Weighted Progress (%)
[32 empty] | Output 1 | 65 | 7.4776 | 16.5232 | 17.0698
[32 empty] | Output 2 | 20 | 2.9565 | 6.9481 | 6.9577
[32 empty] | Output 3 | 15 | 1.395 | 1.9715 | 1.9845
[32 empty] | Total | 100 | 0.11829 | 0.25443 | 0.26012
Note on D7: User: It is the cummulative Activity.
Note on D13: User: It is the cummulative Activity.
Note on D14: User: It is the cummulative Activity.
Note on D15: User: It is the cummulative Activity.
Note on D16: User: It is the cummulative Activity.
Note on D17: User: It is the cummulative Activity.
Note on D18: User: It is the cummulative Activity.
Note on D19: User: It is the cummulative Activity.
in JV with SBK Research and Development
Implemented by

## 2. IAs Progress
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS
Per IMPLENTING AGENCY
Status : January though Deember 2021
MAFF |  | Target Weight | 2020 |  |  | 2021-01-01 |  |  | 2021-02-01 |  |  | 2021-03-01 |  |  | 2021-04-01 |  |  | 2021-05-01 |  |  | 2021-06-01 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01
Output 1 – Critical Agribusiness Value Chain Infrastructure Improved and made Climate-Resilient |  |  | Actual | Weighted |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated
1.d | 80 Agricultural cooperatives have integrated adaptation measures in postharvest infrastructural investments | 15 | 0.1556 | 0.02334 |  | 0.45937 | 0.48272 |  | 0.54141 | 0.56475 |  | 0.57281 | 1.1376 |  | 0.65625 | 1.7938 |  | 1.5 | 3.2938 |  | 2.25 | 5.5438 |  | 0 | 5.5438 |  | 0 | 5.5438 |  | 0.060937 | 5.6047 |  | 0.063984 | 5.6687 |  | 0 | 5.6687 |  | 0 | 5.6687
1.e | Crop product quality and safety testing infrastructure in National Agriculture Laboratory upgraded | 5 | 16 | 0.8 |  | 0 | 0.8 |  | 0 | 0.8 |  | 0 | 0.8 |  | 0.5 | 1.3 |  | 0.52 | 1.82 |  | 0.15 | 1.97 |  | 0 | 1.97 |  | 0 | 1.97 |  | 0.20778 | 2.1778 |  | 0.21817 | 2.3959 |  | 0 | 2.3959 |  | 0 | 2.3959
1.f1 | 12,000 Bio-digesters made operational benefitting 40,000 persons (50% are women) | 4 | 9.525 | 0.381 |  | 0.00019361 | 0.38119 |  | 0.067931 | 0.44893 |  | 0.077931 | 0.52686 |  | 0 | 0.52686 |  | 0.0002 | 0.52706 |  | 0.00066667 | 0.52773 |  | 0.00016667 | 0.5279 |  | 0.0018333 | 0.52973 |  | 0.0053333 | 0.53506 |  | 0.0056 | 0.54066 |  | 0 | 0.54066 |  | 0 | 0.54066
1.f2 | 6,000 Compost-huts made operational benefiting 40,000 persons (50% are women) | 4 | 9.25 | 0.37 |  | 0 | 0.37 |  | 0.095335 | 0.46534 |  | 0.097924 | 0.56326 |  | 0 | 0.56326 |  | 0 | 0.56326 |  | 0.00066667 | 0.56393 |  | 0.00026667 | 0.56419 |  | 0.0026667 | 0.56686 |  | 0.008 | 0.57486 |  | 0.0084 | 0.58326 |  | 0 | 0.58326 |  | 0 | 0.58326
1.f.3 | 40,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed | 2 | 0.7 | 0.014 |  | 0.062422 | 0.076422 |  | 0.042884 | 0.056884 |  | 0.062422 | 0.11931 |  | 0.1696 | 0.28891 |  | 0.192 | 0.48091 |  | 0.0364 | 0.51731 |  | 0.002 | 0.51931 |  | 0.0504 | 0.56971 |  | 0.13072 | 0.70043 |  | 0.13726 | 0.83768 |  | 0 | 0.83768 |  | 0 | 0.83768
| sub-total Output 1 | 30 |  | 1.5883 |  |  | 2.1103 |  |  | 2.3359 |  | 0.81109 | 3.147 |  | 1.3258 | 4.4728 |  | 2.2122 | 6.685 |  | 2.4377 | 9.1228 |  | 0.0024333 | 9.1252 |  | 0.0549 | 9.1801 |  | 0.41277 | 9.5929 |  | 0.43341 | 10.0263 |  | 0 | 10.0263 |  | 0 | 10.0263
Output 2 – Climate-smart Agriculture and Agribusiness Promoted
2.a | 3 Additional climate-resilient varieties of rice and maize released | 5 | 6.25 | 0.3125 |  | 0.071875 | 0.38438 |  | 0.078125 | 0.39062 |  | 0.090625 | 0.48125 |  | 0.091438 | 0.57269 |  | 0.0305 | 0.60319 |  | 0.15438 | 0.75756 |  | 0 | 0.75756 |  | 0.0275 | 0.78506 |  | 0.052347 | 0.83741 |  | 0.054965 | 0.89237 |  | 0 | 0.89237 |  | 0 | 0.89237
2.b | 40,000 Farmers trained in Climate-smart Agriculture and agribusiness development skills | 5 | 16.98 | 0.849 |  | 0.04275 | 0.89175 |  | 0.0855 | 0.9345 |  | 0.08975 | 1.0243 |  | 0.3 | 1.3242 |  | 0.3125 | 1.6367 |  | 0.074618 | 1.7114 |  | 0.0090112 | 1.7204 |  | 0.073928 | 1.7943 |  | 0.9195 | 2.7138 |  | 0.96547 | 3.6793 |  | 0 | 3.6793 |  | 0 | 3.6793
2.d.1 | 4 Agricultural development centers made fully operational to provide agribusiness services | 2 | 26.3 | 0.526 |  | 0.0724 | 0.5984 |  | 0.12305 | 0.64905 |  | 0.13905 | 0.7881 |  | 0.792 | 1.5801 |  | 0 | 1.5801 |  | 0 | 1.5801 |  | 0 | 1.5801 |  | 0 | 1.5801 |  | 0.11733 | 1.6974 |  | 0.1232 | 1.8206 |  | 0 | 1.8206 |  | 0 | 1.8206
2.d.2 | 4 Engineering workshops made fully operational to provide agribusiness services | 2 | 30.3 | 0.606 |  | 0.05415 | 0.66015 |  | 0.10205 | 0.70805 |  | 0.1033 | 0.81135 |  | 0.75 | 1.5614 |  | 0.2 | 1.7613 |  | 0 | 1.7613 |  | 0 | 1.7613 |  | 0 | 1.7613 |  | 0.19183 | 1.9532 |  | 0.20142 | 2.1546 |  | 0 | 2.1546 |  | 0 | 2.1546
| sub-total Output 2 | 14 |  | 2.2935 |  |  | 2.5347 |  |  | 2.6822 |  | 0.42273 | 3.105 |  | 1.9334 | 5.0384 |  | 0.543 | 5.5814 |  | 0.22899 | 5.8104 |  | 0.0090112 | 5.8194 |  | 0.10143 | 5.9208 |  | 1.281 | 7.2018 |  | 1.3451 | 8.5469 |  | 0 | 8.5469 |  | 0 | 8.5469
Output 3 – Enabling Environment for Climate-Friendly Agribusiness Enhanced
3.a | Policy on Climate Smart and Gender Responsive Agribusiness and PPP framework formulated | 2 | 19 | 0.38 |  | 0 | 0.38 |  | 0 | 0.38 |  | 0.1465 | 0.5265 |  | 0.25 | 0.7765 |  | 0.2 | 0.9765 |  | 0.15 | 1.1265 |  | 0.005 | 1.1315 |  | 0.14 | 1.2715 |  | 0.27 | 1.5415 |  | 0.2835 | 1.825 |  | 0 | 1.825 |  | 0 | 1.825
3.b | Good Agriculture Practice for tropical fruit endorsed | 2 | 14.5 | 0.29 |  | 0 | 0.29 |  | 0 | 0.29 |  | 0 | 0.29 |  | 0.12 | 0.41 |  | 0 | 0.41 |  | 0.07 | 0.48 |  | 0 | 0.48 |  | 0.046 | 0.526 |  | 0.097 | 0.623 |  | 0.10185 | 0.72485 |  | 0 | 0.72485 |  | 0 | 0.72485
3.c | Good Agriculture Practice for organic fertilizer endorsed | 2 | 11.5 | 0.23 |  | 0 | 0.23 |  | 0 | 0.23 |  | 0 | 0.23 |  | 0 | 0.23 |  | 0 | 0.23 |  | 0.6 | 0.83 |  | 0.008 | 0.838 |  | 0.064 | 0.902 |  | 0.172 | 1.074 |  | 0.1806 | 1.2546 |  | 0 | 1.2546 |  | 0 | 1.2546
3.d | 50 Staff from financial institutions trained in CSA and green finance | 2 | 5.4 | 0.108 |  | 0 | 0.108 |  | 0 | 0.108 |  | 0 | 0.108 |  | 0 | 0.108 |  | 0 | 0.108 |  | 0.072 | 0.18 |  | 0 | 0.18 |  | 0.05 | 0.23 |  | 0.134 | 0.364 |  | 0.1407 | 0.5047 |  | 0 | 0.5047 |  | 0 | 0.5047
3.e | 30 agribusinesses trained in green finance and CSA | 2 | 4.5 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0.018 | 0.108 |  | 0 | 0.108 |  | 0.036 | 0.144 |  | 0.176 | 0.32 |  | 0.1848 | 0.5048 |  | 0 | 0.5048 |  | 0 | 0.5048
3.f | 20,000 Households provided with information on climate risk-sharing instruments | 2 | 4.5 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0 | 0.09 |  | 0.015 | 0.105 |  | 0 | 0.105 |  | 0 | 0.105 |  | 0 | 0.105 |  | 0 | 0.105 |  | 0 | 0.105 |  | 0 | 0.105
3.g | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | 3 | 6.9 | 0.207 |  | 0 | 0.207 |  | 0 | 0.207 |  | 0 | 0.207 |  | 0 | 0.207 |  | 0 | 0.207 |  | 0.33 | 0.537 |  | 0 | 0.537 |  | 0 | 0.537 |  | 0.2145 | 0.7515 |  | 0.22523 | 0.97672 |  | 0 | 0.97672 |  | 0 | 0.97672
| sub-total Output 3 | 15 |  | 1.395 |  |  | 1.395 |  |  | 1.395 |  | 0.1465 | 1.5415 |  | 0.37 | 1.9115 |  | 0.2 | 2.1115 |  | 1.255 | 3.3665 |  | 0.013 | 3.3795 |  | 0.336 | 3.7155 |  | 1.0635 | 4.779 |  | 1.1167 | 5.8957 |  | 0 | 5.8957 |  | 0 | 5.8957
OUTPUT | Output 1 | 30 |  | 1.5883 |  |  | 2.1103 |  |  | 2.3359 |  | 0.81109 | 3.147 |  | 1.3258 | 4.4728 |  | 2.2122 | 6.685 |  | 2.4377 | 9.1228 |  | 0.0024333 | 9.1252 |  | 0.0549 | 9.1801 |  | 0.41277 | 9.5929 |  | 0.43341 | 10.0263 |  | 0 | 10.0263 |  | 0 | 10.0263
| Output 2 | 14 |  | 2.2935 |  |  | 2.5347 |  |  | 2.6822 |  | 0.42273 | 3.105 |  | 1.9334 | 5.0384 |  | 0.543 | 5.5814 |  | 0.22899 | 5.8104 |  | 0.0090112 | 5.8194 |  | 0.10143 | 5.9208 |  | 1.281 | 7.2018 |  | 1.3451 | 8.5469 |  | 0 | 8.5469 |  | 0 | 8.5469
| Output 3 | 15 |  | 1.395 |  |  | 1.395 |  |  | 1.395 |  | 0.1465 | 1.5415 |  | 0.37 | 1.9115 |  | 0.2 | 2.1115 |  | 1.255 | 3.3665 |  | 0.013 | 3.3795 |  | 0.336 | 3.7155 |  | 1.0635 | 4.779 |  | 1.1167 | 5.8957 |  | 0 | 5.8957 |  | 0 | 5.8957
TOTAL MAFF |  | 59 |  | 5.2768 |  |  | 6.04 |  |  | 6.4131 |  | 1.3803 | 7.7934 |  | 3.6293 | 11.4227 |  | 2.9552 | 14.3779 |  | 3.9217 | 18.2997 |  | 0.024445 | 18.3241 |  | 0.49233 | 18.8164 |  | 2.7573 | 21.5737 |  | 2.8951 | 24.4689 |  | 0 | 24.4689 |  | 0 | 24.4689
MOWRAM |  |  | 2020 |  |  | 2021-01-01 |  |  | 2021-02-01 |  |  | 2021-03-01 |  |  | 2021-04-01 |  |  | 2021-05-01 |  |  | 2021-06-01 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01
Output 1 – Critical Agribusiness Value Chain Infrastructure Improved and made Climate-Resilient |  |  | Actual | Weighted |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated
1.a | 27 Irrigation and water management systems rehabilitated and made climate-friendly | 15 | 10.06 | 1.509 |  | 0.80063 | 2.3096 |  | 1.0349 | 2.5439 |  | 1.0884 | 3.6323 |  | 0 | 3.6323 |  | 0 | 3.6323 |  | 1.6762 | 5.3084 |  | 0 | 5.3084 |  | 0 | 5.3084 |  | 0.027778 | 5.3362 |  | 0 | 5.3362 |  | 0 | 5.3362 |  | 0 | 5.3362
| sub-total Output 1 | 15 |  | 0.01509 |  |  | 2.3096 |  |  | 2.5439 |  | 1.0884 | 3.6323 |  | 0 | 3.6323 |  | 0 | 3.6323 |  | 1.6762 | 5.3084 |  | 0 | 5.3084 |  | 0 | 5.3084 |  | 0.027778 | 5.3362 |  | 0 | 5.3362 |  | 0 | 5.3362 |  | 0 | 5.3362
Output 2 – Climate-smart Agriculture and Agribusiness Promoted
2.c.1 | 27 FWUCS of FWUGS made full operational | 3 | 12.1 | 0.363 |  | 0.194 | 0.557 |  | 0.59556 | 0.95856 |  | 0.90606 | 1.8646 |  | 0.069722 | 1.9343 |  | 0.016111 | 1.9504 |  | 0.13361 | 2.0841 |  | 0.00055556 | 2.0846 |  | 0.0081111 | 2.0927 |  | 0.16431 | 2.257 |  | 0.17252 | 2.4295 |  | 0 | 2.4295 |  | 0 | 2.4295
2.c.2 | 500 FWUCS of FWUGS developed capacity to operate and maintain their irrigation schemes | 3 | 10 | 0.3 |  | 0.39 | 0.69 |  | 0.39 | 0.69 |  | 0.39 | 1.08 |  | 0 | 1.08 |  | 0 | 1.08 |  | 0.105 | 1.185 |  | 0 | 1.185 |  | 0 | 1.185 |  | 0.042 | 1.227 |  | 0.0441 | 1.2711 |  | 0 | 1.2711 |  | 0 | 1.2711
| sub-total Output 2 | 6 |  | 0.663 |  |  | 1.247 |  |  | 1.6486 |  | 1.2961 | 2.9446 |  | 0.069722 | 3.0143 |  | 0.016111 | 3.0304 |  | 0.23861 | 3.2691 |  | 0.00055556 | 3.2696 |  | 0.0081111 | 3.2777 |  | 0.20631 | 3.484 |  | 0.21662 | 3.7006 |  | 0 | 3.7006 |  | 0 | 3.7006
TOTAL MOWRAM |  | 21 |  | 0.67809 |  |  | 3.5566 |  |  | 4.1925 |  | 2.3844 | 6.5769 |  | 0.069722 | 6.6466 |  | 0.016111 | 6.6627 |  | 1.9148 | 8.5775 |  | 0.00055556 | 8.5781 |  | 0.0081111 | 8.5862 |  | 0.23408 | 8.8202 |  | 0.21662 | 9.0369 |  | 0 | 9.0369 |  | 0 | 9.0369
MRD |  |  | 2020 |  |  | 2021-01-01 |  |  | 2021-02-01 |  |  | 2021-03-01 |  |  | 2021-04-01 |  |  | 2021-05-01 |  |  | 2021-06-01 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01
Output 1 – Critical Agribusiness Value Chain Infrastructure Improved and made Climate-Resilient |  |  | Actual | Weighted |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated
1.c | At least 250 Km Farm roads upgraded to climate resilient standards to improve Connectivity to Cooperatives and Markets | 15 | 14.05 | 2.1075 |  | 0.32289 | 2.4304 |  | 0.47071 | 2.5782 |  | 0.52675 | 3.105 |  | 1.4015 | 4.5065 |  | 0.5262 | 5.0327 |  | 0.56233 | 5.595 |  | 0.54416 | 6.1392 |  | 1.068 | 7.2072 |  | 0.852 | 8.0592 |  | 1.3577 | 9.4168 |  | 0 | 9.4168 |  | 0 | 9.4168
TOTAL MRD |  | 15 |  | 2.1075 |  |  | 2.4304 |  |  | 2.5782 |  | 0.52675 | 3.105 |  | 1.4015 | 4.5065 |  | 0.5262 | 5.0327 |  | 0.56233 | 5.595 |  | 0.54416 | 6.1392 |  | 1.068 | 7.2072 |  | 0.852 | 8.0592 |  | 1.3577 | 9.4168 |  | 0 | 9.4168 |  | 0 | 9.4168
UNDECIDED |  |  | 2020 |  |  | 2021-01-01 |  |  | 121/2021 |  |  | 2021-03-01 |  |  | 2021-04-01 |  |  | 2021-05-01 |  |  | 2021-06-01 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01
Output 1 – Critical Agribusiness Value Chain Infrastructure Improved and made Climate-Resilient |  |  | Actual | Weighted |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated
1.b | 800 On-farm rainwater harvesting ponds commissioned (incl. 15 drip irrigation) | 5 | 4.13 | 0.2065 |  | 0.018229 | 0.22473 |  | 0.018229 | 0.22473 |  | 0.019792 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452
TOTAL Output (Undecided) |  | 5 |  | 0.2065 |  |  | 0.22473 |  |  | 0.22473 |  | 0.019792 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452
OVERALL |  |  | 2020 |  |  | 2021-01-01 |  |  | 2021-02-01 |  |  | 2021-03-01 |  |  | 2021-04-01 |  |  | 2021-05-01 |  |  | 2021-06-01 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01
|  |  | Actual | Weighted |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated |  | Weighted | Accumulated
EI | MAFF | 59 |  | 5.2768 |  |  | 6.04 |  |  | 6.4131 |  | 1.3803 | 7.7934 |  | 3.6293 | 11.4227 |  | 2.9552 | 14.3779 |  | 3.9217 | 18.2997 |  | 0.024445 | 18.3241 |  | 0.49233 | 18.8164 |  | 2.7573 | 21.5737 |  | 2.8951 | 24.4689 |  | 0 | 24.4689 |  | 0 | 24.4689
| MOWRAM | 21 |  | 0.67809 |  |  | 3.5566 |  |  | 4.1925 |  | 2.3844 | 6.5769 |  | 0.069722 | 6.6466 |  | 0.016111 | 6.6627 |  | 1.9148 | 8.5775 |  | 0.00055556 | 8.5781 |  | 0.0081111 | 8.5862 |  | 0.23408 | 8.8202 |  | 0.21662 | 9.0369 |  | 0 | 9.0369 |  | 0 | 9.0369
| MRD | 15 |  | 2.1075 |  |  | 2.4304 |  |  | 2.5782 |  | 0.52675 | 3.105 |  | 1.4015 | 4.5065 |  | 0.5262 | 5.0327 |  | 0.56233 | 5.595 |  | 0.54416 | 6.1392 |  | 1.068 | 7.2072 |  | 0.852 | 8.0592 |  | 1.3577 | 9.4168 |  | 0 | 9.4168 |  | 0 | 9.4168
| Undecided | 5 |  | 0.2065 |  |  | 0.22473 |  |  | 0.22473 |  | 0.019792 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452 |  | 0 | 0.24452
Overall TOTAL for all |  | 100 |  | 8.2689 |  |  | 12.2518 |  |  | 13.4085 |  | 4.3113 | 17.7198 |  | 5.1005 | 22.8204 |  | 3.4975 | 26.3179 |  | 6.3988 | 32.7167 |  | 0.56916 | 33.2859 |  | 1.5684 | 34.8543 |  | 3.8434 | 38.6977 |  | 4.4694 | 43.1671 |  | 0 | 43.1671 |  | 0 | 43.1671
[19 empty] | 25.5364 |  | 6.3988 | 31.9352 |  | 0.56916 | 32.5044 |  | 1.5684 | 34.0728 |  | 3.8156 | 37.8884 |  | 0 | 37.8884 |  | 0 | 37.8884 |  | 0 | 37.8884
| Original as of July 2021 (Dead formulation) | 100 |  | 12.0735 |  |  | 14.4613 |  |  | 15.7665 |  | 4.2849 | 20.0514 |  | 4.0619 | 24.1133 |  | 1.8884 | 26.0017 |  | 3.665 | 29.6668 |  | 2.5551 | 32.2218 |  | 0 | 32.2218 |  | 0 | 32.2218 |  | 0 | 32.2218 |  | 0 | 32.2218 |  | 0 | 32.2218
| Deviation | 0 |  | -3.8046 | 0 | 0 | -2.2096 | 0 | 0 | -2.358 | 0 | 0.026427 | -2.3316 | 0 | 1.0386 | -1.2929 | 0 | 1.6091 | 0.31616 | 0 | 2.7338 | 3.0499 | 0 | -1.9859 | 1.064 | 0 | 1.5684 | 2.6325 | 0 | 3.8434 | 6.4758 | 0 | 4.4694 | 10.9452 | 0 | 0 | 10.9452 | 0 | 0 | 10.9452
| Original beforemodic=fication | 100 |  | 12.0735 |  |  | 257.5135 |  |  | 371.8012 |  | 427.8361 | 799.6372 |  | 510.055 | 1309.6922 |  | 349.7511 | 1659.4433 |  | 318.2474 | 1977.6907 |  | 72.7991 | 2050.4899 |  | 0 | 2050.4899 |  | 0 | 2050.4899 |  | 0 | 2050.4899 |  | 0 | 2050.4899 |  | 0 | 2050.4899
|  |  |  | -3.8046 |  |  | -245.2617 |  |  | -358.3926 |  | -423.5248 | -781.9174 |  | -504.9544 | -1286.8718 |  | -346.2536 | -1633.1254 |  | -311.8486 | -1944.974 |  | -72.23 | -2017.204 |  | 1.5684 | -2015.6356 |  | 3.8434 | -2011.7922 |  | 4.4694 | -2007.3228 |  | 0 | -2007.3228 |  | 0 | -2007.3228
|  |  |  | 9.0193 |  |  | 11.5083 |  |  | 12.665 |  | 4.3113 | 16.9383 |  | 5.1005 | 22.0389 |  | 3.4975 | 25.5364 |  | 6.3988 | 31.9352 |  | 0.56916 | 32.5044 |  | 1.5684 | 34.0728 |  | 0.038156 | 34.111 |  | 0 | 34.111 |  | 0 | 34.111 |  | 0 | 34.111
in JV with SBK Research and Development
Implemented by

## 3. DMF Progress
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS
DMF PROGRESS
Status : January though Deember 2021
Output and Activities |  | Assigned weight | Progress 2020 |  |  | Actual Monthly Weighted Progress Against AWP 2021 (%) | [19 empty] | Overall DMF's Cumulative Weighted Progress (%) | [19 empty] | % Cumulative Weight Progress to date (2020, 2021)
|  |  | Actual | Weighted |  | Jan | Feb | March | Q1 | April | May | Jun | Q2 | S1 | Jul | Aug | Sept | Q3 | 9 Ms | Oct | Nov | Dec | Q4 | S2 | Annual | Jan | Feb | March | Q1 | April | May | Jun | Q2 | S1 | Jul | Aug | Sept | Q3 | 9 Ms | Oct | Nov | Dec | Q4 | S2 | Annual
Output 1 – Critical Agribusiness Value Chain Infrastructure Improved and made Climate-Resilient
1.a | 27 Irrigation and water management systems rehabilitated and made climate-friendly | 15 | 10.06 | 1.509 |  | 5.3375 | 6.8994 | 7.2559 | 19.4928 | 0 | 0 | 11.1744 | 11.1744 | 30.6671 | 0 | 0 | 0.18519 | 0.18519 | 30.8523 | 0 | 0 | 0 | 0 | 0.18519 | 30.8523 | 0.80063 | 1.0349 | 1.0884 | 2.9239 | 0 | 0 | 1.6762 | 1.6762 | 4.6001 | 0 | 0 | 0.027778 | 0.027778 | 4.6278 | 0 | 0 | 0 | 0 | 0.027778 | 4.6278 | 4.6001
1.b | 800 On-farm rainwater harvesting ponds commissioned (incl. 15 drip irrigation) | 5 | 4.13 | 0.2065 |  | 0.36458 | 0.36458 | 0.39583 | 1.125 | 0 | 0 | 0 | 0 | 1.125 | 0 | 0 | 0 | 0 | 1.125 | 0 | 0 | 0 | 0 | 0 | 1.125 | 0.018229 | 0.018229 | 0.019792 | 0.05625 | 0 | 0 | 0 | 0 | 0.05625 | 0 | 0 | 0 | 0 | 0.05625 | 0 | 0 | 0 | 0 | 0 | 0.05625 | 0.05625
1.c | At least 250 Km Farm roads upgraded to climate resilient standards to improve Connectivity to Cooperatives and Markets | 15 | 14.05 | 2.1075 |  | 2.1526 | 3.138 | 3.5117 | 8.8023 | 9.3436 | 3.508 | 3.7489 | 16.6005 | 25.4028 | 3.6277 | 7.12 | 5.68 | 16.4277 | 41.8305 | 9.0511 | 0 | 0 | 9.0511 | 25.4788 | 50.8816 | 0.32289 | 0.47071 | 0.52675 | 1.3203 | 1.4015 | 0.5262 | 0.56233 | 2.4901 | 3.8104 | 0.54416 | 1.068 | 0.852 | 2.4642 | 6.2746 | 1.3577 | 0 | 0 | 1.3577 | 3.8218 | 7.6322 | 4.3546
1.d | 80 Agricultural cooperatives have integrated adaptation measures in postharvest infrastructural investments | 15 | 15.06 | 2.259 |  | 3.0625 | 3.6094 | 3.8188 | 10.4906 | 4.375 | 10 | 15 | 29.375 | 39.8656 | 0 | 0 | 0.40625 | 0.40625 | 40.2719 | 0.42656 | 0 | 0 | 0.42656 | 0.83281 | 40.6984 | 0.45937 | 0.54141 | 0.57281 | 1.5736 | 0.65625 | 1.5 | 2.25 | 4.4062 | 5.9798 | 0 | 0 | 0.060937 | 0.060937 | 6.0408 | 0.063984 | 0 | 0 | 0.063984 | 0.12492 | 6.1048 | 5.9798
1.e | Crop product quality and safety testing infrastructure in National Agriculture Laboratory upgraded | 5 | 16 | 0.8 |  | 0 | 0 | 0 | 0 | 10 | 10.4 | 3 | 23.4 | 23.4 | 0 | 0 | 4.1556 | 4.1556 | 27.5556 | 4.3633 | 0 | 0 | 4.3633 | 8.5189 | 31.9189 | 0 | 0 | 0 | 0 | 0.5 | 0.52 | 0.15 | 1.17 | 1.17 | 0 | 0 | 0.20778 | 0.20778 | 1.3778 | 0.21817 | 0 | 0 | 0.21817 | 0.42594 | 1.5959 | 1.17
1.f1 | 12,000 Bio-digesters made operational benefitting 40,000 persons (50% are women) | 4 | 7.07 | 0.2828 |  | 0.0048402 | 1.6983 | 1.9483 | 3.6514 | 0 | 0.005 | 0.016667 | 0.021667 | 3.6731 | 0.0041667 | 0.045833 | 0.13333 | 0.18333 | 3.8564 | 0.14 | 0 | 0 | 0.14 | 0.32333 | 3.9964 | 0.00019361 | 0.067931 | 0.077931 | 0.14606 | 0 | 0.0002 | 0.00066667 | 0.00086667 | 0.14692 | 0.00016667 | 0.0018333 | 0.0053333 | 0.0073333 | 0.15426 | 0.0056 | 0 | 0 | 0.0056 | 0.012933 | 0.15986 | 0.14709
1.f2 | 6,000 Compost-huts made operational benefiting 40,000 persons (50% are women) | 4 | 7.47 | 0.2988 |  | 0 | 2.3834 | 2.4481 | 4.8315 | 0 | 0 | 0.016667 | 0.016667 | 4.8482 | 0.0066667 | 0.066667 | 0.2 | 0.27333 | 5.1215 | 0.21 | 0 | 0 | 0.21 | 0.48333 | 5.3315 | 0 | 0.095335 | 0.097924 | 0.19326 | 0 | 0 | 0.00066667 | 0.00066667 | 0.19393 | 0.00026667 | 0.0026667 | 0.008 | 0.010933 | 0.20486 | 0.0084 | 0 | 0 | 0.0084 | 0.019333 | 0.21326 | 0.19419
1.f.3 | 20,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed | 2 | 0.7 | 0.014 |  | 3.1211 | 2.1442 | 3.1211 | 8.3864 | 8.48 | 9.6 | 1.82 | 19.9 | 28.2864 | 0.1 | 2.52 | 6.536 | 9.156 | 37.4424 | 6.8628 | 0 | 0 | 6.8628 | 16.0188 | 44.3052 | 0.062422 | 0.042884 | 0.062422 | 0.16773 | 0.1696 | 0.192 | 0.0364 | 0.398 | 0.56573 | 0.002 | 0.0504 | 0.13072 | 0.18312 | 0.74885 | 0.13726 | 0 | 0 | 0.13726 | 0.32038 | 0.8861 | 0.56773
| sub-total Output 1 | 65 |  | 7.4776 |  | 14.0432 | 20.2373 | 22.4996 | 56.7801 | 32.1986 | 33.513 | 34.7766 | 100.4882 | 157.2682 | 3.7386 | 9.7525 | 17.2963 | 30.7874 | 188.0556 | 21.0538 | 0 | 0 | 21.0538 | 51.8411 | 209.1094 | 1.6637 | 2.2714 | 2.446 | 6.3812 | 2.7274 | 2.7384 | 4.6762 | 10.142 | 16.5232 | 0.54659 | 1.1229 | 1.2925 | 2.962 | 19.4852 | 1.7911 | 0 | 0 | 1.7911 | 4.7531 | 21.2763 | 17.0698
Output 2 – Climate-smart Agriculture and Agribusiness Promoted
2.a | 3 Additional climate-resilient varieties of rice and maize released | 5 | 6.25 | 0.3125 |  | 1.4375 | 1.5625 | 1.8125 | 1.6042 | 1.8288 | 0.61 | 3.0875 | 5.5263 | 7.1304 | 0 | 0.55 | 1.047 | 1.6042 | 8.7274 | 1.0993 | 0 | 0 | 1.0993 | 2.6962 | 9.8267 | 0.071875 | 0.078125 | 0.090625 | 0.24063 | 0.091438 | 0.0305 | 0.15438 | 0.27631 | 0.51694 | 0 | 0.0275 | 0.052347 | 0.079848 | 0.59679 | 0.054965 | 0 | 0 | 0.054965 | 0.13481 | 0.65175 | 0.51694
2.b | 40,000 Farmers trained in Climate-smart Agriculture and agribusiness development skills | 5 | 16.98 | 0.849 |  | 0.855 | 1.71 | 1.795 | 1.4533 | 6 | 6.25 | 1.4924 | 13.7424 | 15.1957 | 0.18022 | 1.4786 | 18.39 | 1.4533 | 35.2445 | 19.3095 | 0 | 0 | 19.3095 | 39.3583 | 54.554 | 0.04275 | 0.0855 | 0.08975 | 0.218 | 0.3 | 0.3125 | 0.074618 | 0.68712 | 0.90512 | 0.0090112 | 0.073928 | 0.9195 | 1.0024 | 1.9076 | 0.96547 | 0 | 0 | 0.96547 | 1.9679 | 2.873 | 0.91413
2.c.1 | 27 FWUCS of FWUGS made full operational | 3 | 12.1 | 0.363 |  | 6.4667 | 19.8519 | 30.2019 | 18.8401 | 2.3241 | 0.53704 | 4.4537 | 7.3148 | 26.1549 | 0.018519 | 0.27037 | 5.4769 | 18.8401 | 31.9207 | 5.7507 | 0 | 0 | 5.7507 | 11.5164 | 37.6714 | 0.194 | 0.59556 | 0.90606 | 1.6956 | 0.069722 | 0.016111 | 0.13361 | 0.21944 | 1.9151 | 0.00055556 | 0.0081111 | 0.16431 | 0.17297 | 2.088 | 0.17252 | 0 | 0 | 0.17252 | 0.34549 | 2.2605 | 1.9156
2.c.2 | 500 FWUCS of FWUGS developed capacity to operate and maintain their irrigation schemes | 3 | 10 | 0.3 |  | 13 | 13 | 13 | 13 | 0 | 0 | 3.5 | 3.5 | 16.5 | 0 | 0 | 1.4 | 13 | 17.9 | 1.47 | 0 | 0 | 1.47 | 2.87 | 19.37 | 0.39 | 0.39 | 0.39 | 1.17 | 0 | 0 | 0.105 | 0.105 | 1.275 | 0 | 0 | 0.042 | 0.042 | 1.317 | 0.0441 | 0 | 0 | 0.0441 | 0.0861 | 1.3611 | 1.275
2.d.1 | 4 Agricultural development centers made fully operational to provide agribusiness services | 2 | 26.3 | 0.526 |  | 3.62 | 6.1525 | 6.9525 | 5.575 | 39.6 | 0 | 0 | 39.6 | 45.175 | 0 | 0 | 5.8667 | 5.575 | 51.0417 | 6.16 | 0 | 0 | 6.16 | 12.0267 | 57.2017 | 0.0724 | 0.12305 | 0.13905 | 0.3345 | 0.792 | 0 | 0 | 0.792 | 1.1265 | 0 | 0 | 0.11733 | 0.11733 | 1.2438 | 0.1232 | 0 | 0 | 0.1232 | 0.24053 | 1.367 | 1.1265
2.d.2 | 4 Engineering workshops made fully operational to provide agribusiness services | 2 | 30.3 | 0.606 |  | 2.7075 | 5.1025 | 5.165 | 4.325 | 37.5 | 10 | 0 | 47.5 | 51.825 | 0 | 0 | 9.5917 | 4.325 | 61.4167 | 10.0712 | 0 | 0 | 10.0712 | 19.6629 | 71.4879 | 0.05415 | 0.10205 | 0.1033 | 0.2595 | 0.75 | 0.2 | 0 | 0.95 | 1.2095 | 0 | 0 | 0.19183 | 0.19183 | 1.4013 | 0.20142 | 0 | 0 | 0.20142 | 0.39326 | 1.6028 | 1.2095
| sub-total Output 2 | 20 |  | 2.9565 |  | 28.0867 | 47.3794 | 58.9269 | 44.7976 | 87.2528 | 17.397 | 12.5336 | 117.1834 | 161.9811 | 0.19874 | 2.2989 | 41.7721 | 44.7976 | 206.2509 | 43.8607 | 0 | 0 | 43.8607 | 88.1305 | 250.1116 | 0.82517 | 1.3743 | 1.7188 | 3.9182 | 2.0032 | 0.55911 | 0.4676 | 3.0299 | 6.9481 | 0.0095667 | 0.10954 | 1.4873 | 1.6064 | 8.5545 | 1.5617 | 0 | 0 | 1.5617 | 3.1681 | 10.1162 | 6.9577
Output 3 – Enabling Environment for Climate-Friendly Agribusiness Enhanced
3.a | Policy on Climate Smart and Gender Responsive Agribusiness and PPP framework formulated | 2 | 19 | 0.38 |  | 0 | 0 | 7.325 | 7.325 | 12.5 | 10 | 7.5 | 30 | 37.325 | 0.25 | 7 | 13.5 | 20.75 | 58.075 | 14.175 | 0 | 0 | 14.175 | 34.925 | 72.25 | 0 | 0 | 0.1465 | 0.1465 | 0.25 | 0.2 | 0.15 | 0.6 | 0.7465 | 0.005 | 0.14 | 0.27 | 0.415 | 1.1615 | 0.2835 | 0 | 0 | 0.2835 | 0.6985 | 1.445 | 0.7515
3.b | Good Agriculture Practice for tropical fruit endorsed | 2 | 14.5 | 0.29 |  | 0 | 0 | 0 | 0 | 6 | 0 | 3.5 | 9.5 | 9.5 | 0 | 2.3 | 4.85 | 7.15 | 16.65 | 5.0925 | 0 | 0 | 5.0925 | 0 | 21.7425 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0.07 | 0.19 | 0.19 | 0 | 0.046 | 0.097 | 0.143 | 0.333 | 0.10185 | 0 | 0 | 0.10185 | 0.24485 | 0.43485 | 0.19
3.c | Good Agriculture Practice for organic fertilizer endorsed | 2 | 11.5 | 0.23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 0.4 | 3.2 | 8.6 | 12.2 | 42.2 | 9.03 | 0 | 0 | 9.03 | 0 | 51.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.008 | 0.064 | 0.172 | 0.244 | 0.844 | 0.1806 | 0 | 0 | 0.1806 | 0.4246 | 1.0246 | 0.608
3.d | 50 Staff from financial institutions trained in CSA and green finance | 2 | 5.4 | 0.108 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 3.6 | 3.6 | 0 | 2.5 | 6.7 | 9.2 | 12.8 | 7.035 | 0 | 0 | 7.035 | 0 | 19.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072 | 0.072 | 0.072 | 0 | 0.05 | 0.134 | 0.184 | 0.256 | 0.1407 | 0 | 0 | 0.1407 | 0.3247 | 0.3967 | 0.072
3.e | 30 agribusinesses trained in green finance and CSA | 2 | 4.5 | 0.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0 | 1.8 | 8.8 | 10.6 | 11.5 | 9.24 | 0 | 0 | 9.24 | 0 | 20.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0.018 | 0.018 | 0.018 | 0 | 0.036 | 0.176 | 0.212 | 0.23 | 0.1848 | 0 | 0 | 0.1848 | 0.3968 | 0.4148 | 0.018
3.f | 20,000 Households provided with information on climate risk-sharing instruments | 2 | 4.5 | 0.09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015 | 0.015 | 0.015 | 0 | 0 | 0 | 0 | 0.015 | 0 | 0 | 0 | 0 | 0 | 0.015 | 0.015
3.g | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | 3 | 6.9 | 0.207 |  | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11 | 0 | 0 | 7.15 | 7.15 | 18.15 | 7.5075 | 0 | 0 | 7.5075 | 0 | 25.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0.33 | 0.33 | 0 | 0 | 0.2145 | 0.2145 | 0.5445 | 0.22523 | 0 | 0 | 0.22523 | 0.43972 | 0.76972 | 0.33
| sub-total Output 3 | 15 |  | 1.395 |  | 0 | 0 | 7.325 | 7.325 | 18.5 | 10 | 57.25 | 85.75 | 93.075 | 0.65 | 16.8 | 49.6 | 67.05 | 160.125 | 52.08 | 0 | 0 | 52.08 | 34.925 | 212.205 | 0 | 0 | 0.1465 | 0.1465 | 0.37 | 0.2 | 1.255 | 1.825 | 1.9715 | 0.013 | 0.336 | 1.0635 | 1.4125 | 3.384 | 1.1167 | 0 | 0 | 1.1167 | 2.5292 | 4.5007 | 1.9845
OUTPUT | Output 1 | 65 |  | 7.4776 |  | 14.0432 | 20.2373 | 22.4996 | 56.7801 | 32.1986 | 33.513 | 34.7766 | 100.4882 | 157.2682 | 3.7386 | 9.7525 | 17.2963 | 30.7874 | 188.0556 | 21.0538 | 0 | 0 | 21.0538 | 51.8411 | 209.1094 | 1.6637 | 2.2714 | 2.446 | 6.3812 | 2.7274 | 2.7384 | 4.6762 | 10.142 | 16.5232 | 0.54659 | 1.1229 | 1.2925 | 2.962 | 19.4852 | 1.7911 | 0 | 0 | 1.7911 | 4.7531 | 21.2763 | 17.0698
| Output 2 | 20 |  | 2.9565 |  | 28.0867 | 47.3794 | 58.9269 | 44.7976 | 87.2528 | 17.397 | 12.5336 | 117.1834 | 161.9811 | 0.19874 | 2.2989 | 41.7721 | 44.7976 | 206.2509 | 43.8607 | 0 | 0 | 43.8607 | 88.1305 | 250.1116 | 0.82517 | 1.3743 | 1.7188 | 3.9182 | 2.0032 | 0.55911 | 0.4676 | 3.0299 | 6.9481 | 0.0095667 | 0.10954 | 1.4873 | 1.6064 | 8.5545 | 1.5617 | 0 | 0 | 1.5617 | 3.1681 | 10.1162 | 6.9577
| Output 3 | 15 |  | 1.395 |  | 0 | 0 | 7.325 | 7.325 | 18.5 | 10 | 57.25 | 85.75 | 93.075 | 0.65 | 16.8 | 49.6 | 67.05 | 160.125 | 52.08 | 0 | 0 | 52.08 | 34.925 | 212.205 | 0 | 0 | 0.1465 | 0.1465 | 0.37 | 0.2 | 1.255 | 1.825 | 1.9715 | 0.013 | 0.336 | 1.0635 | 1.4125 | 3.384 | 1.1167 | 0 | 0 | 1.1167 | 2.5292 | 4.5007 | 1.9845
TOTAL Output (1 + 2 + 3) |  | 100 |  | 11.8291 |  | 0.4213 | 0.67617 | 0.88751 | 1.089 | 1.3795 | 0.6091 | 1.0456 | 3.0342 | 4.1232 | 0.045873 | 0.28851 | 1.0867 | 1.4264 | 5.5443 | 1.1699 | 0 | 0 | 1.1699 | 1.749 | 6.7143 | 2.4889 | 3.6457 | 4.3113 | 10.4459 | 5.1005 | 3.4975 | 6.3988 | 14.9969 | 25.4428 | 0.56916 | 1.5684 | 3.8434 | 5.981 | 31.4237 | 0.044694 | 0 | 0 | 0.044694 | 6.0257 | 31.4684 | 26.0119
| Verified figures on the changing before deviding by 100 |  |  | 11.8291 |  | 0.4213 | 0.67617 | 0.88751 | 1.089 | 1.3795 | 0.6091 | 1.0456 | 3.0342 | 4.1232 | 0.045873 | 0.28851 | 1.0848 | 1.4245 | 5.5425 | 0 | 0 | 0 | 0 | 0.95622 | 5.5425 | 2.4889 | 3.6457 | 4.3113 | 10.4459 | 5.1005 | 3.4975 | 6.3988 | 14.9969 | 25.4428 | 0.56916 | 1.5684 | 3.8156 | 5.9532 | 31.396
| Original as of July 2021 (Dead formulation) | 100 |  | 11.8291 |  | 0.2979 | 0.46455 | 0.62964 | 0.46143 | 0.54669 | 0.19295 | 0.41436 | 1.154 | 1.6154 | 0.070523 | 0 | 0 | 0.4858 | 1.686 | 0 | 0 | 0 | 0 | 0.026023 | 1.686 | 2.3878 | 3.693 | 4.2849 | 10.3657 | 4.0619 | 1.8884 | 3.665 | 9.6154 | 19.9811 | 2.5551 | 0 | 0 | 2.5551 | 22.5362 | 0 | 0 | 0 | 0 | 2.5551 | 22.5362
| Deviation | 0 |  | 0 | 0 | 0.12339 | 0.21162 | 0.25788 | 0.62759 | 0.83282 | 0.41615 | 0.63125 | 1.8802 | 2.5078 | -0.02465 | 0.28851 | 1.0867 | 0.94055 | 3.8584 | 1.1699 | 0 | 0 | 1.1699 | 1.7229 | 5.0283 | 0.10109 | -0.047324 | 0.026427 | 0.080194 | 1.0386 | 1.6091 | 2.7338 | 5.3815 | 5.4617 | -1.9859 | 1.5684 | 3.8434 | 3.4259 | 8.8876 | 0.044694 | 0 | 0 | 0.044694 | 3.4706 | 8.9323
| Inetrim Accumulative Progresses |  |  | 11.8291 | [24 empty] | 22.275 |  |  |  | 37.2719 | 37.2719 |  |  |  | 43.2528 | 43.2528 |  |  |  | 43.2975 | 43.2975
| Original beforemodic=fication |  |  | 11.8291 |  | 0.42271 | 0.66108 | 0.87105 | 1.041 | 1.3795 | 0.6091 | 0.44094 | 2.4296 | 3.4706 | 0.11486 | 0 | 0 | 0.56284 | 3.5854 | 0 | 0 | 0 | 0 | 0.070361 | 3.5854 | 2.4544 | 3.6155 | 4.2784 | 10.3483 | 5.1005 | 3.4975 | 3.1825 | 11.7805 | 22.1288 | 0.72799 | 0 | 0 | 0.72799 | 22.8568 | 0 | 0 | 0 | 0 | 0.72799 | 22.8568
|  |  |  | 0 |  | -0.0014148 | 0.015088 | 0.016466 | 0.048019 | 0 | 0 | 0.60466 | 0.60466 | 0.65268 | -0.068988 | 0.28851 | 1.0867 | 0.86351 | 1.9589 | 1.1699 | 0 | 0 | 1.1699 | 1.6786 | 3.1288 | 0.034517 | 0.030176 | 0.032931 | 0.097625 | 0 | 0 | 3.2164 | 3.2164 | 3.314 | -0.15883 | 1.5684 | 3.8434 | 5.253 | 8.5669 | 0.044694 | 0 | 0 | 0.044694 | 5.2977 | 8.6116
Overall Progress, by Quarters
|  |  |  | 2020 |  | 2021
[6 empty] | Q1 | Q2 | Q3 | Q4 | Total |  | S1 | S2 | 9Ms
| Output 1 |  |  | 7.4776 |  | 6.3812 | 10.142 | 2.962 | 1.7911 | 28.7539 |  | 16.5232 | 4.7531 | 19.4852
| Output 2 |  |  | 2.9565 |  | 3.9182 | 3.0299 | 1.6064 | 1.5617 | 13.0727 |  | 6.9481 | 3.1681 | 8.5545
| Output 3 |  |  | 1.395 |  | 0.1465 | 1.825 | 1.4125 | 1.1167 | 5.8957 |  | 1.9715 | 2.5292 | 3.384
| Total |  |  | 11.8291 |  | 10.4459 | 14.9969 | 5.981 | 0.044694 | 43.2975 |  | 25.4428 | 6.0257 | 31.4237
| Accumulative |  |  | 11.8291 |  | 22.275 | 37.2719 | 43.2528 | 43.2975 | 43.2975 |  | 37.2719 | 43.2975 | 43.2528
in JV with SBK Research and Development
Implemented by

## Output 1
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS | [114 empty] | 10
OUTPUT 1
Status : January though Deember 2021
| ACTIVITY |  | SUBACTIVITY | UNIT | OVERALL TARGET | Sub- Weight (%) | AWP 2020 |  |  | 2021 |  | Progress Jan 2021 |  |  | Progress Feb 2021 |  |  | Progress Mar 2021 |  |  | Progress Q1 2021 |  |  | Progress in Apr. 2021 | [6 empty] | Progress in May 2021 | [6 empty] | Progress in Jun. 2021 | [6 empty] | Progress in Q2 2021 | [6 empty] | Progress in First Six-months 2021 | [6 empty] | Progress in Jul 2021 | [6 empty] | Progress in Aug. 2021 | [6 empty] | Progress in Sept. 2021 | [6 empty] | Progress in Q3 2021 | [6 empty] | Progress in First Nine-months 2021 | [6 empty] | Progress in Oct. 2021 | [6 empty] | Progress in Nov. 2021 | [6 empty] | Progress in Dec. 2021 | [6 empty] | Progress in Q4 2021 | [6 empty] | Progress in Second Six-months 2021 | [6 empty] | Progress in Annually 2021
[7 empty] | Plan | Realisation |  | AWP | AWP & Carry Over from 2020 | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff
[8 empty] | Nr | Physical %
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 12 | 13 | 14 | 12 | 13 | 14 | 12 | 13 | 14 | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14
| 1.a | 27 Irrigation and water management systems rehabilitated and made climate-friendly | Step 1A Identification of ISs | Schemes | 27 | 5 | 10 | 17.1936 | 3.184 | 9 | 1.8064 | 100 | 1.8064 | 0.33452 | 100 | 1.8064 | 0.33452 | 100 | 1.8064 | 0.33452 | 100 | 1.8064 | 0.33452 | 0 | 1 |  | 0 | 1.8064 | 0.33452 | CS1/MoWRAM | 0 | 1 |  | 0 | 1.8064 | 0.33452 | CS1/MoWRAM | 100 | 26.1936 | 26.1936 | 4.8507 | 28 | 5.1852 | CS1/MoWRAM | 92.9062 | 28.1936 | 26.1936 | 4.8507 | 28 | 5.1852 | CS1/MoWRAM | 0 |  | 28 | 5.1852 | 28 | 5.1852 | CS1/MoWRAM | 0 |  |  | 0 | 28 | 5.1852 | CS1/MoWRAM | 0 |  |  | 0 | 28 | 5.1852 | CS1/MoWRAM | 100 | 1 | 1 | 0.18519 | 29 | 5.3704 | CS1/MoWRAM | 100 | 1 | 1 | 0.18519 | 29 | 5.3704 | CS1/MoWRAM | 2900 | 1 | 29 | 5.3704 | 29 | 5.3704 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 29 | 5.3704 | CS1/MoWRAM | 0 |  |  | 0 | 29 | 5.3704 | CS1/MoWRAM | 0 |  |  | 0 | 29 | 5.3704 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 29 | 5.3704 | CS1/MoWRAM | 100 | 1 | 1 | 0.18519 | 29 | 5.3704 | CS1/MoWRAM | 2900 | 1 | 29 | 5.3704 | 29 | 5.3704 | CS1/MoWRAM
|  |  | Step 1B Feasibility Study | Schemes | 27 | 10 | 10 | 6.3045 | 2.335 | 9 | 12.6955 | 20 | 2.5391 | 0.94041 | 25 | 3.1739 | 1.1755 | 30 | 3.8087 | 1.4106 | 25 | 3.1739 | 1.1755 | 0 | 1 |  | 0 | 3.1739 | 1.1755 | CS1/MoWRAM | 0 | 1 |  | 0 | 3.1739 | 1.1755 | CS1/MoWRAM | 100 | 4.8261 | 4.8261 | 1.7875 | 8 | 2.963 | CS1/MoWRAM | 70.7008 | 6.8261 | 4.8261 | 1.7875 | 8 | 2.963 | CS1/MoWRAM | 0 |  | 8 | 2.963 | 8 | 2.963 | CS1/MoWRAM | 0 |  |  | 0 | 8 | 2.963 | CS1/MoWRAM | 0 |  |  | 0 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 8 | 2.963 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 8 | 2.963 | CS1/MoWRAM | 0 |  |  | 0 | 8 | 2.963 | CS1/MoWRAM | 0 |  |  | 0 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 8 | 2.963 | CS1/MoWRAM | 0 | 0 | 8 | 2.963 | 8 | 2.963 | CS1/MoWRAM
|  |  | Step 2 Topographic Survey | Ha | 15000 | 10 | 4050 | 3754.5 | 2.503 | 5333 | 5628.5 | 5 | 281.425 | 0.18762 | 10 | 562.85 | 0.37523 | 10 | 562.85 | 0.37523 | 8.3333 | 469.0417 | 0.31269 | 0 | 1 |  | 0 | 469.0417 | 0.31269 | CS1/MoWRAM | 0 | 1 |  | 0 | 469.0417 | 0.31269 | CS1/MoWRAM | 100 | 5245.244 | 5245.244 | 3.4968 | 5714.2857 | 3.8095 | CS1/MoWRAM | 99.9619 | 5247.244 | 5245.244 | 3.4968 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 |  | 5714.2857 | 3.8095 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 5714.2857 | 3.8095 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 5714.2857 | 3.8095 | CS1/MoWRAM | 0 | 0 | 5714.2857 | 3.8095 | 5714.2857 | 3.8095 | CS1/MoWRAM
|  |  | Step 3 + 4DED & Tender file | Ha | 15000 | 20 | 4050 | 1399.5 | 1.866 | 5333 | 7983.5 | 25 | 1995.875 | 2.6612 | 30 | 2395.05 | 3.1934 | 30 | 2395.05 | 3.1934 | 28.3333 | 2261.9917 | 3.016 | 0 | 1 |  | 0 | 2261.9917 | 3.016 | CS1/MoWRAM | 0 | 1 |  | 0 | 2261.9917 | 3.016 | CS1/MoWRAM | 100 | 595.1512 | 595.1512 | 0.79353 | 2857.1429 | 3.8095 | CS1/MoWRAM | 99.6651 | 597.1512 | 595.1512 | 0.79353 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 |  | 2857.1429 | 3.8095 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 2857.1429 | 3.8095 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 |  |  | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 2857.1429 | 3.8095 | CS1/MoWRAM | 0 | 0 | 2857.1429 | 3.8095 | 2857.1429 | 3.8095 | CS1/MoWRAM
|  |  | Procurement & Implementation | Ha | 15000 | 50 | 2000 | 50.1 | 0.167 | 5333 | 7282.9 | 5 | 364.145 | 1.2138 | 7.5 | 546.2175 | 1.8207 | 8 | 582.632 | 1.9421 | 6.8333 | 497.6648 | 1.6589 | 0 | 1 |  | 0 | 497.6648 | 1.6589 | CS1/MoWRAM | 0 | 1 |  | 0 | 497.6648 | 1.6589 | CS1/MoWRAM | 100 | 73.7637 | 73.7637 | 0.24588 | 571.4286 | 1.9048 | CS1/MoWRAM | 97.3602 | 75.7637 | 73.7637 | 0.24588 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 |  | 571.4286 | 1.9048 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 |  |  | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 |  |  | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 571.4286 | 1.9048 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 |  |  | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 |  |  | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 571.4286 | 1.9048 | CS1/MoWRAM | 0 | 0 | 571.4286 | 1.9048 | 571.4286 | 1.9048 | CS1/MoWRAM
|  |  | O&M | Schemes | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | CS1/MoWRAM | 0 | 1 |  | 0 | 0 | 0 | CS1/MoWRAM | 0 |  | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 | 2 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 |  | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 |  |  | 0 | 0 | 0 | CS1/MoWRAM | 0 |  |  | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 |  |  | 0 | 0 | 0 | CS1/MoWRAM | 0 |  |  | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MoWRAM
|  |  | Subtotal |  |  | 100 |  |  | 10.055 |  |  |  |  | 5.3375 |  |  | 6.8994 |  |  | 7.2559 |  |  | 19.4928 |  |  |  | 0 |  | 6.4976 |  |  |  |  | 0 |  | 6.4976 |  |  |  |  | 11.1744 |  | 17.672 |  |  |  |  | 11.1744 |  | 17.672 |  |  |  |  | 30.6671 |  | 17.672 |  |  |  |  | 0 |  | 17.672 |  |  |  |  | 0 |  | 17.672 |  |  |  |  | 0.18519 |  | 17.8571 |  |  |  |  | 0.18519 |  | 17.8571 |  |  |  |  | 30.8523 |  | 17.8571 |  |  |  |  | 0 |  | 17.8571 |  |  |  |  | 0 |  | 17.8571 |  |  |  |  | 0 |  | 17.8571 |  |  |  |  | 0 |  | 17.8571 |  |  |  |  | 0.18519 |  | 17.8571 |  |  |  |  | 30.8523 |  | 17.8571
| 1.b | 800 On-farm rainwater harvesting ponds commissioned (incl. 15 drip irrigation) | Identification of ponds | no | 800 | 5 | 80 | 160 | 1 | 80 | 0 | 0.00625 | 5 | 0.03125 | 0.00625 | 5 | 0.03125 | 0.00625 | 10 | 0.0625 | #DIV/0! | 20 | 0.125 | 0 | 20 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 20 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 20 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 60 | 0 | 0 | 20 | 0.125 | CS2 | 25 | 80 | 20 | 0.125 | 20 | 0.125 | CS2 | 0 | 0 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 0 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 0 |  | 0 | 20 | 0.125 | CS2 | 0 | 0 | 0 | 0 | 20 | 0.125 | CS2 | 25 | 80 | 20 | 0.125 | 20 | 0.125 | CS2 | 0 | 0 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 0 |  | 0 | 20 | 0.125 | CS2 | 0 | 0 |  | 0 | 20 | 0.125 | CS2 | 0 | 0 | 0 | 0 | 20 | 0.125 | CS2 | 0 | 0 | 0 | 0 | 20 | 0.125 | CS2 | 25 | 80 | 20 | 0.125 | 20 | 0.125 | CS2
|  |  | Farm identification for drip system | no | 15 | 5 | 2 | 3.999 | 1.333 | 8 | 6.001 | 16.6639 | 1 | 0.33333 | 16.6639 | 1 | 0.33333 | 16.6639 | 1 | 0.33333 | 49.9917 | 3 | 1 | 0 | 2 | 0 | 0 | 3 | 1 | CS2 | 0 | 2 | 0 | 0 | 3 | 1 | CS2 | 0 | 1 | 0 | 0 | 3 | 1 | CS2 | 0 | 5 | 0 | 0 | 3 | 1 | CS2 | 37.5 | 8 | 3 | 1 | 3 | 1 | CS2 | 0 | 0 | 0 | 0 | 3 | 1 | CS2 | 0 | 0 | 0 | 0 | 3 | 1 | CS2 | 0 | 0.66678 |  | 0 | 3 | 1 | CS2 | 0 | 0.66678 | 0 | 0 | 3 | 1 | CS2 | 34.6149 | 8.6668 | 3 | 1 | 3 | 1 | CS2 | 0 | 0.66678 | 0 | 0 | 3 | 1 | CS2 | 0 | 0.66678 |  | 0 | 3 | 1 | CS2 | 0 | 0.66678 |  | 0 | 3 | 1 | CS2 | 0 | 2.0003 | 0 | 0 | 3 | 1 | CS2 | 0 | 2.6671 | 0 | 0 | 3 | 1 | CS2 | 28.1238 | 10.6671 | 3 | 1 | 3 | 1 | CS2
|  |  | DED Ponds | no | 800 | 15 | 80 | 60 | 1.125 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.66 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.3333 |  | 0 | 0 | 0 | CS2 | 0 | 2.9933 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.9933 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.3333 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.3333 |  | 0 | 0 | 0 | CS2 | 0 | 2.3333 |  | 0 | 0 | 0 | CS2 | 0 | 7 | 0 | 0 | 0 | 0 | CS2 | 0 | 9.9933 | 0 | 0 | 0 | 0 | CS2 | 0 | 9.9933 | 0 | 0 | 0 | 0 | CS2
|  |  | DED Drip system | no | 15 | 15 | 2 | 0.67 | 0.67 | 2 | 3.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.37 |  | 0 | 0 | 0 | CS2 | 0 | 1.37 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.37 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.37 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.37 |  | 0 | 0 | 0 | CS2 | 0 | 0.37 |  | 0 | 0 | 0 | CS2 | 0 | 1.11 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.48 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.48 | 0 | 0 | 0 | 0 | CS2
|  |  | Procurement & Implementation ponds | no | 800 | 35 | 80 | 0 | 0 | 1 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 |  | 0 | 0 | 0 | CS2 | 0 | 10 | 0 | 0 | 0 | 0 | CS2 | 0 | 10 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 |  | 0 | 0 | 0 | CS2 | 0 | 9 |  | 0 | 0 | 0 | CS2 | 0 | 27 | 0 | 0 | 0 | 0 | CS2 | 0 | 37 | 0 | 0 | 0 | 0 | CS2 | 0 | 37 | 0 | 0 | 0 | 0 | CS2
|  |  | Drip systems installation | no | 15 | 25 | 80 | 0 | 0 | 1 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 |  | 0 | 0 | 0 | CS2 | 0 | 10 | 0 | 0 | 0 | 0 | CS2 | 0 | 10 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 |  | 0 | 0 | 0 | CS2 | 0 | 9 |  | 0 | 0 | 0 | CS2 | 0 | 27 | 0 | 0 | 0 | 0 | CS2 | 0 | 37 | 0 | 0 | 0 | 0 | CS2 | 0 | 37 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 4.128 |  | 192.331 |  |  | 0.36458 |  |  | 0.36458 |  |  | 0.39583 |  |  | 1.125 |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 1.125 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 1.125 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 0 |  | 1.125 |  |  |  |  | 1.125 |  | 1.125
| 1.c | At least 250 Km Farm roads upgraded to climate resilient standards to improve Connectivity to Cooperatives and Markets | Step 1A: Identification | km | 250 | 5 | 67.95 | 68 | 1.36 | 100.1 | 100.05 | 10 | 10.005 | 0.2001 | 15 | 15.0075 | 0.30015 | 15 | 15.0075 | 0.30015 | 13.3333 | 13.34 | 0.2668 | 100 | 234.98 | 234.98 | 4.6996 | 248.32 | 4.9664 | CS1/MRD | 0 | 0 | 0 | 0 | 248.32 | 4.9664 | CS1/MRD | 100 | 25.07 | 25.07 | 0.5014 | 273.39 | 5.4678 | CS1/MRD | 100 | 260.05 | 260.05 | 5.201 | 273.39 | 5.4678 | CS1/MRD | 0 |  | 273.39 | 5.4678 | 273.39 | 5.4678 | CS1/MRD | 0 | 0 | 0 | 0 | 273.39 | 5.4678 | CS1/MRD | 100 | 100 | 100 | 2 | 373.39 | 7.4678 | CS1/MRD | 100 | 100 | 100 | 2 | 473.39 | 9.4678 | CS1/MRD | 100 | 200 | 200 | 4 | 473.39 | 9.4678 | CS1/MRD | 236.695 | 200 | 473.39 | 9.4678 | 473.39 | 9.4678 | CS1/MRD | 100 | 102.5 | 102.5 | 2.05 | 575.89 | 11.5178 | CS1/MRD | 0 |  |  | 0 | 575.89 | 11.5178 | CS1/MRD | 0 |  |  | 0 | 575.89 | 11.5178 | CS1/MRD | 100 | 102.5 | 102.5 | 2.05 | 575.89 | 11.5178 | CS1/MRD | 100 | 302.5 | 302.5 | 6.05 | 575.89 | 11.5178 | CS1/MRD | 190.3769 | 302.5 | 575.89 | 11.5178 | 575.89 | 11.5178 | CS1/MRD
|  |  | Step 1B Feasibility Study | km | 250 | 10 | 67.95 | 37.5 | 1.5 | 100.1 | 130.55 | 25 | 32.6375 | 1.3055 | 30 | 39.165 | 1.5666 | 35 | 45.6925 | 1.8277 | 30 | 39.165 | 1.5666 | 0 | 0 | 0 | 0 | 39.165 | 1.5666 | CS1/MRD | 0 | 0 | 0 | 0 | 39.165 | 1.5666 | CS1/MRD | 100 | 30.955 | 30.955 | 1.2382 | 70.12 | 2.8048 | CS1/MRD | 100 | 30.955 | 30.955 | 1.2382 | 70.12 | 2.8048 | CS1/MRD | 0 |  | 70.12 | 2.8048 | 70.12 | 2.8048 | CS1/MRD | 100 | 60.462 | 60.462 | 2.4185 | 130.582 | 5.2233 | CS1/MRD | 100 | 60 | 60 | 2.4 | 190.582 | 7.6233 | CS1/MRD | 100 | 10 | 10 | 0.4 | 200.582 | 8.0233 | CS1/MRD | 100 | 130.462 | 130.462 | 5.2185 | 200.582 | 8.0233 | CS1/MRD | 153.7475 | 130.462 | 200.582 | 8.0233 | 200.582 | 8.0233 | CS1/MRD | 100.0113 | 75 | 75.0085 | 3.0003 | 275.5905 | 11.0236 | CS1/MRD | 0 |  |  | 0 | 275.5905 | 11.0236 | CS1/MRD | 0 |  |  | 0 | 275.5905 | 11.0236 | CS1/MRD | 100.0113 | 75 | 75.0085 | 3.0003 | 275.5905 | 11.0236 | CS1/MRD | 100.0041 | 205.462 | 205.4705 | 8.2188 | 275.5905 | 11.0236 | CS1/MRD | 134.1321 | 205.462 | 275.5905 | 11.0236 | 275.5905 | 11.0236 | CS1/MRD
|  |  | Step 2:Topographic Survey | km | 250 | 10 | 67.95 | 71 | 2.84 | 100.1 | 97.05 | 1 | 0.9705 | 0.03882 | 7.5 | 7.2787 | 0.29115 | 9 | 8.7345 | 0.34938 | 5.8333 | 5.6612 | 0.22645 | 100 | 30 | 30 | 1.2 | 35.6613 | 1.4264 | CS1/MRD | 100 | 24.02 | 24.02 | 0.9608 | 59.6812 | 2.3872 | CS1/MRD | 100 | 10.4388 | 10.4388 | 0.41755 | 70.12 | 2.8048 | CS1/MRD | 100 | 64.4587 | 64.4587 | 2.5783 | 70.12 | 2.8048 | CS1/MRD | 0 |  | 70.12 | 2.8048 | 70.12 | 2.8048 | CS1/MRD | 100 | 30.231 | 30.231 | 1.2092 | 100.351 | 4.014 | CS1/MRD | 100 | 60 | 60 | 2.4 | 160.351 | 6.414 | CS1/MRD | 100 | 20 | 20 | 0.8 | 180.351 | 7.214 | CS1/MRD | 100 | 110.231 | 110.231 | 4.4092 | 180.351 | 7.214 | CS1/MRD | 163.6119 | 110.231 | 180.351 | 7.214 | 180.351 | 7.214 | CS1/MRD | 100.0129 | 70 | 70.009 | 2.8004 | 250.36 | 10.0144 | CS1/MRD | 0 |  |  | 0 | 250.36 | 10.0144 | CS1/MRD | 0 |  |  | 0 | 250.36 | 10.0144 | CS1/MRD | 100.0129 | 70 | 70.009 | 2.8004 | 250.36 | 10.0144 | CS1/MRD | 100.005 | 180.231 | 180.24 | 7.2096 | 250.36 | 10.0144 | CS1/MRD | 138.9106 | 180.231 | 250.36 | 10.0144 | 250.36 | 10.0144 | CS1/MRD
|  |  | Step 3+4 DED & Tender file | km | 250 | 20 | 36.5 | 68.75 | 5.5 | 100.1 | 67.85 | 2.5 | 1.6963 | 0.1357 | 5 | 3.3925 | 0.2714 | 6 | 4.071 | 0.32568 | 4.5 | 3.0532 | 0.24426 | 100 | 30 | 30 | 2.4 | 33.0532 | 2.6443 | CS1/MRD | 100 | 31.84 | 31.84 | 2.5472 | 64.8932 | 5.1915 | CS1/MRD | 100 | 5.2268 | 5.2268 | 0.41814 | 70.12 | 5.6096 | CS1/MRD | 100 | 67.0667 | 67.0667 | 5.3653 | 70.12 | 5.6096 | CS1/MRD | 0 |  | 70.12 | 5.6096 | 70.12 | 5.6096 | CS1/MRD | 0 | 0 | 0 | 0 | 70.12 | 5.6096 | CS1/MRD | 100 | 4 | 4 | 0.32 | 74.12 | 5.9296 | CS1/MRD | 103.3333 | 30 | 31 | 2.48 | 105.12 | 8.4096 | CS1/MRD | 102.9412 | 34 | 35 | 2.8 | 105.12 | 8.4096 | CS1/MRD | 309.1765 | 34 | 105.12 | 8.4096 | 105.12 | 8.4096 | CS1/MRD | 100.0307 | 15 | 15.0046 | 1.2004 | 120.1246 | 9.61 | CS1/MRD | 0 |  |  | 0 | 120.1246 | 9.61 | CS1/MRD | 0 |  |  | 0 | 120.1246 | 9.61 | CS1/MRD | 100.0307 | 15 | 15.0046 | 1.2004 | 120.1246 | 9.61 | CS1/MRD | 102.0502 | 49 | 50.0046 | 4.0004 | 120.1246 | 9.61 | CS1/MRD | 245.1522 | 49 | 120.1246 | 9.61 | 120.1246 | 9.61 | CS1/MRD
|  |  | Procurement & Implementation | km | 250 | 50 | 36.5 | 14.25 | 2.85 | 25 | 47.25 | 5 | 2.3625 | 0.4725 | 7.5 | 3.5438 | 0.70875 | 7.5 | 3.5438 | 0.70875 | 6.6667 | 3.15 | 0.63 | 100 | 5.22 | 5.22 | 1.044 | 8.37 | 1.674 | CS1/MRD | 0 | 0 | 0 | 0 | 8.37 | 1.674 | CS1/MRD | 100 | 5.868 | 5.868 | 1.1736 | 14.238 | 2.8476 | CS1/MRD | 100 | 11.088 | 11.088 | 2.2176 | 14.238 | 2.8476 | CS1/MRD | 0 |  | 14.238 | 2.8476 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 14.238 | 2.8476 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 |  |  | 0 | 14.238 | 2.8476 | CS1/MRD | 0 |  |  | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 0 | 0 | 14.238 | 2.8476 | CS1/MRD | 0 | 0 | 14.238 | 2.8476 | 14.238 | 2.8476 | CS1/MRD
|  |  | O&M | km | 250 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 |  | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 |  |  | 0 | 0 | 0 | CS1/MRD | 0 |  |  | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD | 0 | 0 | 0 | 0 | 0 | 0 | CS1/MRD
|  |  | Subtotal |  |  | 100 |  |  | 14.05 |  |  |  |  | 2.1526 |  |  | 3.138 |  |  | 3.5117 |  |  | 8.8023 |  |  |  | 9.3436 |  | 12.2777 |  |  |  |  | 3.508 |  | 15.7857 |  |  |  |  | 3.7489 |  | 19.5346 |  |  |  |  | 16.6005 |  | 19.5346 |  |  |  |  | 25.4028 |  | 19.5346 |  |  |  |  | 3.6277 |  | 23.1623 |  |  |  |  | 7.12 |  | 30.2823 |  |  |  |  | 5.68 |  | 35.9623 |  |  |  |  | 16.4277 |  | 35.9623 |  |  |  |  | 41.8305 |  | 35.9623 |  |  |  |  | 9.0511 |  | 45.0134 |  |  |  |  | 0 |  | 45.0134 |  |  |  |  | 0 |  | 45.0134 |  |  |  |  | 9.0511 |  | 45.0134 |  |  |  |  | 25.4788 |  | 45.0134 |  |  |  |  | 50.8816 |  | 45.0134
| 1.d | 80 Agricultural cooperatives have integrated adaptation measures in postharvest infrastructural investments | Identification | No | 80 | 5 | 20 | 20 | 1.25 | 35 | 35 | 70 | 24.5 | 1.5312 | 100 | 35 | 2.1875 | 100 | 35 | 2.1875 | 90 | 31.5 | 1.9688 | 100 | 35 | 35 | 2.1875 | 66.5 | 4.1562 | CS2 | 0 | 35 | 0 | 0 | 66.5 | 4.1562 | CS2 | 0 | 35 | 0 | 0 | 66.5 | 4.1562 | CS2 | 33.3333 | 105 | 35 | 2.1875 | 66.5 | 4.1562 | CS2 | 0 |  | 66.5 | 4.1562 | 66.5 | 4.1562 | CS2 | 0 | 0 | 0 | 0 | 66.5 | 4.1562 | CS2 | 0 | 0 | 0 | 0 | 66.5 | 4.1562 | CS2 | 0 | 3.8889 | 0 | 0 | 66.5 | 4.1562 | CS2 | 0 | 3.8889 | 0 | 0 | 66.5 | 4.1562 | CS2 | 1710 | 3.8889 | 66.5 | 4.1562 | 66.5 | 4.1562 | CS2 | 0 | 3.8889 | 0 | 0 | 66.5 | 4.1562 | CS2 | 0 | 3.8889 |  | 0 | 66.5 | 4.1562 | CS2 | 0 | 3.8889 |  | 0 | 66.5 | 4.1562 | CS2 | 0 | 11.6667 | 0 | 0 | 66.5 | 4.1562 | CS2 | 0 | 15.5556 | 0 | 0 | 66.5 | 4.1562 | CS2 | 427.5 | 15.5556 | 66.5 | 4.1562 | 66.5 | 4.1562 | CS2
|  |  | Site location Survey | no | 80 | 5 | 20 | 20 | 1.25 | 35 | 35 | 70 | 24.5 | 1.5312 | 25 | 8.75 | 0.54688 | 30 | 10.5 | 0.65625 | 41.6667 | 14.5833 | 0.91146 | 100 | 35 | 35 | 2.1875 | 49.5833 | 3.099 | CS2 | 0 | 35 | 0 | 0 | 49.5833 | 3.099 | CS2 | 0 | 35 | 0 | 0 | 49.5833 | 3.099 | CS2 | 33.3333 | 105 | 35 | 2.1875 | 49.5833 | 3.099 | CS2 | 0 |  | 49.5833 | 3.099 | 49.5833 | 3.099 | CS2 | 0 | 0 | 0 | 0 | 49.5833 | 3.099 | CS2 | 0 | 0 | 0 | 0 | 49.5833 | 3.099 | CS2 | 0 | 3.8889 | 0 | 0 | 49.5833 | 3.099 | CS2 | 0 | 3.8889 | 0 | 0 | 49.5833 | 3.099 | CS2 | 1275 | 3.8889 | 49.5833 | 3.099 | 49.5833 | 3.099 | CS2 | 0 | 3.8889 | 0 | 0 | 49.5833 | 3.099 | CS2 | 0 | 3.8889 |  | 0 | 49.5833 | 3.099 | CS2 | 0 | 3.8889 |  | 0 | 49.5833 | 3.099 | CS2 | 0 | 11.6667 | 0 | 0 | 49.5833 | 3.099 | CS2 | 0 | 15.5556 | 0 | 0 | 49.5833 | 3.099 | CS2 | 318.75 | 15.5556 | 49.5833 | 3.099 | 49.5833 | 3.099 | CS2
|  |  | DED & Tender file | no | 4 | 20 | 1 | 1 | 5 | 1 | 1 | 0 | 0 | 0 | 7.5 | 0.075 | 0.375 | 7.5 | 0.075 | 0.375 | 5 | 0.05 | 0.25 | 0 | 2 | 0 | 0 | 0.05 | 0.25 | CS2 | 100 | 2 | 2 | 10 | 2.05 | 10.25 | CS2 | 50 | 2 | 1 | 5 | 3.05 | 15.25 | CS2 | 50 | 6 | 3 | 15 | 3.05 | 15.25 | CS2 | 0 |  | 3.05 | 15.25 | 3.05 | 15.25 | CS2 | 0 | 0 | 0 | 0 | 3.05 | 15.25 | CS2 | 0 | 0.11111 | 0 | 0 | 3.05 | 15.25 | CS2 | 45 | 0.11111 | 0.05 | 0.25 | 3.1 | 15.5 | CS2 | 22.5 | 0.22222 | 0.05 | 0.25 | 3.1 | 15.5 | CS2 | 1395 | 0.22222 | 3.1 | 15.5 | 3.1 | 15.5 | CS2 | 47.25 | 0.11111 | 0.0525 | 0.2625 | 3.1525 | 15.7625 | CS2 | 0 | 0.11111 |  | 0 | 3.1525 | 15.7625 | CS2 | 0 | 0.11111 |  | 0 | 3.1525 | 15.7625 | CS2 | 15.75 | 0.33333 | 0.0525 | 0.2625 | 3.1525 | 15.7625 | CS2 | 18.45 | 0.55556 | 0.1025 | 0.5125 | 3.1525 | 15.7625 | CS2 | 567.45 | 0.55556 | 3.1525 | 15.7625 | 3.1525 | 15.7625 | CS2
|  |  | Procurement | no | 4 | 40 | 1 | 0.8 | 8 | 1 | 1 | 0 | 0 | 0 | 5 | 0.05 | 0.5 | 6 | 0.06 | 0.6 | 3.6667 | 0.036667 | 0.36667 | 0 | 1 | 0 | 0 | 0.036667 | 0.36667 | CS2 | 0 | 1 | 0 | 0 | 0.036667 | 0.36667 | CS2 | 100 | 1 | 1 | 10 | 1.0367 | 10.3667 | CS2 | 33.3333 | 3 | 1 | 10 | 1.0367 | 10.3667 | CS2 | 0 |  | 1.0367 | 10.3667 | 1.0367 | 10.3667 | CS2 | 0 | 0 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.11111 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.11111 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.22222 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 466.5 | 0.22222 | 1.0367 | 10.3667 | 1.0367 | 10.3667 | CS2 | 0 | 0.11111 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.11111 |  | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.11111 |  | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.33333 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 0 | 0.55556 | 0 | 0 | 1.0367 | 10.3667 | CS2 | 186.6 | 0.55556 | 1.0367 | 10.3667 | 1.0367 | 10.3667 | CS2
|  |  | Construction | No | 80 | 25 | 20 | 0.2016 | 0.063 | 35 | 54.7984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | CS2 | 0 | 54.8 | 0 | 0 | 0 | 0 | CS2 | 0 | 54 | 0 | 0 | 0 | 0 | CS2 | 0 | 163.8 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.0887 | 0 | 0 | 0 | 0 | CS2 | 8.2119 | 6.0887 | 0.5 | 0.15625 | 0.5 | 0.15625 | CS2 | 4.106 | 12.1774 | 0.5 | 0.15625 | 0.5 | 0.15625 | CS2 | 4.106 | 12.1774 | 0.5 | 0.15625 | 0.5 | 0.15625 | CS2 | 8.6225 | 6.0887 | 0.525 | 0.16406 | 1.025 | 0.32031 | CS2 | 0 | 6.0887 |  | 0 | 1.025 | 0.32031 | CS2 | 0 | 6.0887 |  | 0 | 1.025 | 0.32031 | CS2 | 2.8742 | 18.2661 | 0.525 | 0.16406 | 1.025 | 0.32031 | CS2 | 3.3669 | 30.4436 | 1.025 | 0.32031 | 1.025 | 0.32031 | CS2 | 3.3669 | 30.4436 | 1.025 | 0.32031 | 1.025 | 0.32031 | CS2
|  |  | O&M | no | 80 | 5 | 20 | 0 | 0 | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | CS2 | 0 | 20 | 0 | 0 | 0 | 0 | CS2 | 0 | 20 | 0 | 0 | 0 | 0 | CS2 | 0 | 60 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 12.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 12.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.1111 |  | 0 | 0 | 0 | CS2 | 0 | 6.1111 |  | 0 | 0 | 0 | CS2 | 0 | 18.3333 | 0 | 0 | 0 | 0 | CS2 | 0 | 30.5556 | 0 | 0 | 0 | 0 | CS2 | 0 | 30.5556 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 15.563 |  |  |  |  | 3.0625 |  |  | 3.6094 |  |  | 3.8188 |  |  | 10.4906 |  |  |  | 4.375 |  | 7.8719 |  |  |  |  | 10 |  | 17.8719 |  |  |  |  | 15 |  | 32.8719 |  |  |  |  | 29.375 |  | 32.8719 |  |  |  |  | 39.8656 |  | 32.8719 |  |  |  |  | 0 |  | 32.8719 |  |  |  |  | 0 |  | 32.8719 |  |  |  |  | 0.40625 |  | 33.2781 |  |  |  |  | 0.40625 |  | 33.2781 |  |  |  |  | 40.2719 |  | 33.2781 |  |  |  |  | 0.42656 |  | 33.7047 |  |  |  |  | 0 |  | 33.7047 |  |  |  |  | 0 |  | 33.7047 |  |  |  |  | 0.42656 |  | 33.7047 |  |  |  |  | 0.83281 |  | 33.7047 |  |  |  |  | 40.6984 |  | 33.7047
| 1.e | Crop product quality and safety testing infrastructure in National Agriculture Laboratory upgraded | TNA for LAB staff | No | 1 | 10 | 1 | 1 | 10 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 1 | 10 | 1 | 10 | CS2 | 100 | 1 | 1 | 10 | 2 | 20 | CS2 | 100 | 0.3 | 0.3 | 3 | 2.3 | 23 | CS2 | 100 | 2.3 | 2.3 | 23 | 2.3 | 23 | CS2 | 0 |  | 2.3 | 23 | 2.3 | 23 | CS2 | 0 | 0 | 0 | 0 | 2.3 | 23 | CS2 | 0 | 0 | 0 | 0 | 2.3 | 23 | CS2 | 0 | 0.11111 | 0 | 0 | 2.3 | 23 | CS2 | 0 | 0.11111 | 0 | 0 | 2.3 | 23 | CS2 | 2070 | 0.11111 | 2.3 | 23 | 2.3 | 23 | CS2 | 0 | 0.11111 | 0 | 0 | 2.3 | 23 | CS2 | 0 | 0.11111 |  | 0 | 2.3 | 23 | CS2 | 0 | 0.11111 |  | 0 | 2.3 | 23 | CS2 | 0 | 0.33333 | 0 | 0 | 2.3 | 23 | CS2 | 0 | 0.44444 | 0 | 0 | 2.3 | 23 | CS2 | 517.5 | 0.44444 | 2.3 | 23 | 2.3 | 23 | CS2
|  |  | DED & Tender file | No | 1 | 20 | 1 | 0.25 | 5 | 1 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.75 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.75 | 0 | 0 | 0 | 0 | CS2 | 0 | 5.25 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.19444 | 0 | 0 | 0 | 0 | CS2 | 15.4286 | 0.19444 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 7.7143 | 0.38889 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 7.7143 | 0.38889 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 16.2 | 0.19444 | 0.0315 | 0.63 | 0.0615 | 1.23 | CS2 | 0 | 0.19444 |  | 0 | 0.0615 | 1.23 | CS2 | 0 | 0.19444 |  | 0 | 0.0615 | 1.23 | CS2 | 5.4 | 0.58333 | 0.0315 | 0.63 | 0.0615 | 1.23 | CS2 | 6.3257 | 0.97222 | 0.0615 | 1.23 | 0.0615 | 1.23 | CS2 | 6.3257 | 0.97222 | 0.0615 | 1.23 | 0.0615 | 1.23 | CS2
|  |  | Procurement | No | 1 | 60 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | CS2 | 0 | 2 | 0 | 0 | 0 | 0 | CS2 | 0 | 2 | 0 | 0 | 0 | 0 | CS2 | 0 | 6 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.44444 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.44444 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.66667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1111 | 0 | 0 | 0 | 0 | CS2
|  |  | Training of staff | Person | 9 | 10 |  |  | 0 | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 | 0 | 0 | 0 | 0 | CS2 | 0 | 9 | 0 | 0 | 0 | 0 | CS2 | 0 | 27 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 9 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0.5 | 0.55556 | 0.5 | 0.55556 | CS2 | 5.5556 | 9 | 0.5 | 0.55556 | 0.5 | 0.55556 | CS2 | 5.5556 | 9 | 0.5 | 0.55556 | 0.5 | 0.55556 | CS2 | 0 | 0 | 0.525 | 0.58333 | 1.025 | 1.1389 | CS2 | 0 | 0 |  | 0 | 1.025 | 1.1389 | CS2 | 0 | 0 |  | 0 | 1.025 | 1.1389 | CS2 | 0 | 0 | 0.525 | 0.58333 | 1.025 | 1.1389 | CS2 | 11.3889 | 9 | 1.025 | 1.1389 | 1.025 | 1.1389 | CS2 | 11.3889 | 9 | 1.025 | 1.1389 | 1.025 | 1.1389 | CS2
|  |  | On-the job training | Person | 50 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | CS2 | 20 | 10 | 2 | 0.4 | 2 | 0.4 | CS2 | 0 | 10 | 0 | 0 | 2 | 0.4 | CS2 | 6.6667 | 30 | 2 | 0.4 | 2 | 0.4 | CS2 | 0 |  | 2 | 0.4 | 2 | 0.4 | CS2 | 0 | 0 | 0 | 0 | 2 | 0.4 | CS2 | 0 | 0 | 0 | 0 | 2 | 0.4 | CS2 | 1350 | 1.1111 | 15 | 3 | 17 | 3.4 | CS2 | 1350 | 1.1111 | 15 | 3 | 17 | 3.4 | CS2 | 1530 | 1.1111 | 17 | 3.4 | 17 | 3.4 | CS2 | 1417.5 | 1.1111 | 15.75 | 3.15 | 32.75 | 6.55 | CS2 | 0 | 1.1111 |  | 0 | 32.75 | 6.55 | CS2 | 0 | 1.1111 |  | 0 | 32.75 | 6.55 | CS2 | 472.5 | 3.3333 | 15.75 | 3.15 | 32.75 | 6.55 | CS2 | 691.875 | 4.4444 | 30.75 | 6.15 | 32.75 | 6.55 | CS2 | 736.875 | 4.4444 | 32.75 | 6.55 | 32.75 | 6.55 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 15 |  |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 10 |  | 10 |  |  |  |  | 10.4 |  | 20.4 |  |  |  |  | 3 |  | 23.4 |  |  |  |  | 23.4 |  | 23.4 |  |  |  |  | 23.4 |  | 23.4 |  |  |  |  | 0 |  | 23.4 |  |  |  |  | 0 |  | 23.4 |  |  |  |  | 4.1556 |  | 27.5556 |  |  |  |  | 4.1556 |  | 27.5556 |  |  |  |  | 27.5556 |  | 27.5556 |  |  |  |  | 4.3633 |  | 31.9189 |  |  |  |  | 0 |  | 31.9189 |  |  |  |  | 0 |  | 31.9189 |  |  |  |  | 4.3633 |  | 31.9189 |  |  |  |  | 8.5189 |  | 31.9189 |  |  |  |  | 31.9189 |  | 31.9189
| 1.f.1 | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) | Identification of Bio-digesters | Biodigester | 12000 | 10 | 500 | 50.04 | 0.417 | 750 | 1199.96 | 0 | 0 | 0 | 1.5 | 17.9994 | 0.015 | 1.5 | 17.9994 | 0.015 | 1 | 11.9996 | 0.0099997 | 0 | 750 | 0 | 0 | 11.9996 | 0.0099997 | CS2 | 0 | 750 | 0 | 0 | 11.9996 | 0.0099997 | CS2 | 2.6667 | 750 | 20 | 0.016667 | 31.9996 | 0.026666 | CS2 | 0.88889 | 2250 | 20 | 0.016667 | 31.9996 | 0.026666 | CS2 | 0 |  | 31.9996 | 0.026666 | 31.9996 | 0.026666 | CS2 | 0.66667 | 750 | 5 | 0.0041667 | 36.9996 | 0.030833 | CS2 | 41.2514 | 133.3289 | 55 | 0.045833 | 91.9996 | 0.076666 | CS2 | 120.004 | 133.3289 | 160 | 0.13333 | 251.9996 | 0.21 | CS2 | 21.6395 | 1016.6578 | 220 | 0.18333 | 251.9996 | 0.21 | CS2 | 24.7871 | 1016.6578 | 251.9996 | 0.21 | 251.9996 | 0.21 | CS2 | 126.0042 | 133.3289 | 168 | 0.14 | 419.9996 | 0.35 | CS2 | 0 | 133.3289 |  | 0 | 419.9996 | 0.35 | CS2 | 0 | 133.3289 |  | 0 | 419.9996 | 0.35 | CS2 | 42.0014 | 399.9867 | 168 | 0.14 | 419.9996 | 0.35 | CS2 | 27.3887 | 1416.6444 | 388 | 0.32333 | 419.9996 | 0.35 | CS2 | 29.6475 | 1416.6444 | 419.9996 | 0.35 | 419.9996 | 0.35 | CS2
|  |  | DED & Tender file | document | 4 | 20 | 1 | 0.26668 | 6.667 | 1 | 1.7333 | 0 | 0 | 0 | 5 | 0.086666 | 0.43333 | 5 | 0.086666 | 0.43333 | 3.3333 | 0.057777 | 0.28889 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 5.4 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 |  | 0.057777 | 0.28889 | 0.057777 | 0.28889 | CS2 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 2.1852 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 2.6441 | 2.1852 | 0.057777 | 0.28889 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 |  | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 |  | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.57777 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 2.763 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 2.0911 | 2.763 | 0.057777 | 0.28889 | 0.057777 | 0.28889 | CS2
|  |  | Procurement | document | 4 | 50 | 1 | 8e-05 | 0.002 | 1 | 1.9999 | 0 | 0 | 0 | 5 | 0.099996 | 1.2499 | 6 | 0.12 | 1.4999 | 3.6667 | 0.07333 | 0.91663 | 0 | 2 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 2 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 2 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 6 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 |  | 0.07333 | 0.91663 | 0.07333 | 0.91663 | CS2 | 0 | 2 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 0.22221 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 0.22221 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 2.4444 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 2.9999 | 2.4444 | 0.07333 | 0.91663 | 0.07333 | 0.91663 | CS2 | 0 | 0.22221 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 0.22221 |  | 0 | 0.07333 | 0.91663 | CS2 | 0 | 0.22221 |  | 0 | 0.07333 | 0.91663 | CS2 | 0 | 0.66664 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 0 | 3.1111 | 0 | 0 | 0.07333 | 0.91663 | CS2 | 2.3571 | 3.1111 | 0.07333 | 0.91663 | 0.07333 | 0.91663 | CS2
|  |  | Construction of biodigesters | Biodigester | 12000 | 20 | 500 | 39.96 | 0.333 | 750 | 1210.04 | 0.24 | 2.9041 | 0.0048402 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.96803 | 0.0016134 | 0 | 1210 | 0 | 0 | 0.96803 | 0.0016134 | CS2 | 0.24793 | 1210 | 3 | 0.005 | 3.968 | 0.0066134 | CS2 | 0 | 1210 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0.082645 | 3630 | 3 | 0.005 | 3.968 | 0.0066134 | CS2 | 0 |  | 3.968 | 0.0066134 | 3.968 | 0.0066134 | CS2 | 0 | 1210 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0 | 134.4489 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0 | 134.4489 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0 | 1478.8978 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0.26831 | 1478.8978 | 3.968 | 0.0066134 | 3.968 | 0.0066134 | CS2 | 0 | 134.4489 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0 | 134.4489 |  | 0 | 3.968 | 0.0066134 | CS2 | 0 | 134.4489 |  | 0 | 3.968 | 0.0066134 | CS2 | 0 | 403.3467 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0 | 1882.2444 | 0 | 0 | 3.968 | 0.0066134 | CS2 | 0.21081 | 1882.2444 | 3.968 | 0.0066134 | 3.968 | 0.0066134 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 7.419 |  | 0 |  |  | 0.0048402 |  |  | 1.6983 |  |  | 1.9483 |  |  | 3.6514 |  |  |  | 0 |  | 1.2171 |  |  |  |  | 0.005 |  | 1.2221 |  |  |  |  | 0.016667 |  | 1.2388 |  |  |  |  | 0.021667 |  | 1.2388 |  |  |  |  | 3.6731 |  | 1.2388 |  |  |  |  | 0.0041667 |  | 1.243 |  |  |  |  | 0.045833 |  | 1.2888 |  |  |  |  | 0.13333 |  | 1.4221 |  |  |  |  | 0.18333 |  | 1.4221 |  |  |  |  | 3.8564 |  | 1.4221 |  |  |  |  | 0.14 |  | 1.5621 |  |  |  |  | 0 |  | 1.5621 |  |  |  |  | 0 |  | 1.5621 |  |  |  |  | 0.14 |  | 1.5621 |  |  |  |  | 0.32333 |  | 1.5621 |  |  |  |  | 3.9964 |  | 1.5621
| 1.f.2 | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) | Identification of compost-huts | Compost hut | 6000 | 10 | 250 | 22.5 | 0.375 | 375 | 602.5 | 0 | 0 | 0 | 7.5 | 45.1875 | 0.075313 | 1.5 | 9.0375 | 0.015062 | 3 | 18.075 | 0.030125 | 0 | 375 | 0 | 0 | 18.075 | 0.030125 | CS2 | 0 | 375 | 0 | 0 | 18.075 | 0.030125 | CS2 | 2.6667 | 375 | 10 | 0.016667 | 28.075 | 0.046792 | CS2 | 0.88889 | 1125 | 10 | 0.016667 | 28.075 | 0.046792 | CS2 | 0 |  | 28.075 | 0.046792 | 28.075 | 0.046792 | CS2 | 1.0667 | 375 | 4 | 0.0066667 | 32.075 | 0.053458 | CS2 | 59.751 | 66.9444 | 40 | 0.066667 | 72.075 | 0.12012 | CS2 | 179.2531 | 66.9444 | 120 | 0.2 | 192.075 | 0.32012 | CS2 | 32.2271 | 508.8889 | 164 | 0.27333 | 192.075 | 0.32012 | CS2 | 37.744 | 508.8889 | 192.075 | 0.32012 | 192.075 | 0.32012 | CS2 | 188.2158 | 66.9444 | 126 | 0.21 | 318.075 | 0.53012 | CS2 | 0 | 66.9444 |  | 0 | 318.075 | 0.53012 | CS2 | 0 | 66.9444 |  | 0 | 318.075 | 0.53012 | CS2 | 62.7386 | 200.8333 | 126 | 0.21 | 318.075 | 0.53012 | CS2 | 40.8611 | 709.7222 | 290 | 0.48333 | 318.075 | 0.53012 | CS2 | 44.8168 | 709.7222 | 318.075 | 0.53012 | 318.075 | 0.53012 | CS2
|  |  | DED & Tender file | document | 4 | 20 | 1 | 0.26668 | 6.667 | 1 | 1.7333 | 0 | 0 | 0 | 5 | 0.086666 | 0.43333 | 5 | 0.086666 | 0.43333 | 3.3333 | 0.057777 | 0.28889 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 5.4 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 |  | 0.057777 | 0.28889 | 0.057777 | 0.28889 | CS2 | 0 | 1.8 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 2.1852 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 2.6441 | 2.1852 | 0.057777 | 0.28889 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 |  | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.19259 |  | 0 | 0.057777 | 0.28889 | CS2 | 0 | 0.57777 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 0 | 2.763 | 0 | 0 | 0.057777 | 0.28889 | CS2 | 2.0911 | 2.763 | 0.057777 | 0.28889 | 0.057777 | 0.28889 | CS2
|  |  | Procurement | document | 4 | 50 | 1 | 0.00028 | 0.007 | 1 | 1.9997 | 0 | 0 | 0 | 7.5 | 0.14998 | 1.8747 | 8 | 0.15998 | 1.9997 | 5.1667 | 0.10332 | 1.2915 | 0 | 2 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 2 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 2 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 6 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 |  | 0.10332 | 1.2915 | 0.10332 | 1.2915 | CS2 | 0 | 2 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 0.22219 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 0.22219 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 2.4444 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 4.2268 | 2.4444 | 0.10332 | 1.2915 | 0.10332 | 1.2915 | CS2 | 0 | 0.22219 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 0.22219 |  | 0 | 0.10332 | 1.2915 | CS2 | 0 | 0.22219 |  | 0 | 0.10332 | 1.2915 | CS2 | 0 | 0.66657 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 0 | 3.111 | 0 | 0 | 0.10332 | 1.2915 | CS2 | 3.3211 | 3.111 | 0.10332 | 1.2915 | 0.10332 | 1.2915 | CS2
|  |  | Construction of compost huts | Compost hut | 6000 | 20 | 250 | 0 | 0 | 625 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | CS2 | 0 | 625 | 0 | 0 | 0 | 0 | CS2 | 0 | 625 | 0 | 0 | 0 | 0 | CS2 | 0 | 1875 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 625 | 0 | 0 | 0 | 0 | CS2 | 0 | 97.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 97.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 819.4444 | 0 | 0 | 0 | 0 | CS2 | 0 | 819.4444 | 0 | 0 | 0 | 0 | CS2 | 0 | 97.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 97.2222 |  | 0 | 0 | 0 | CS2 | 0 | 97.2222 |  | 0 | 0 | 0 | CS2 | 0 | 291.6667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1111.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 1111.1111 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 7.049 |  |  |  |  | 0 |  |  | 2.3834 |  |  | 2.4481 |  |  | 4.8315 |  |  |  | 0 |  | 1.6105 |  |  |  |  | 0 |  | 1.6105 |  |  |  |  | 0.016667 |  | 1.6272 |  |  |  |  | 0.016667 |  | 1.6272 |  |  |  |  | 4.8482 |  | 1.6272 |  |  |  |  | 0.0066667 |  | 1.6338 |  |  |  |  | 0.066667 |  | 1.7005 |  |  |  |  | 0.2 |  | 1.9005 |  |  |  |  | 0.27333 |  | 1.9005 |  |  |  |  | 5.1215 |  | 1.9005 |  |  |  |  | 0.21 |  | 2.1105 |  |  |  |  | 0 |  | 2.1105 |  |  |  |  | 0 |  | 2.1105 |  |  |  |  | 0.21 |  | 2.1105 |  |  |  |  | 0.48333 |  | 2.1105 |  |  |  |  | 5.3315 |  | 2.1105
| 1.f.3 | 20,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed | Training and Capacity Building | Person | 5000 | 20 | 1000 | 441 | 44.1 | 1000 | 1559 | 16 | 249.44 | 0.99776 | 15 | 233.85 | 0.9354 | 16 | 249.44 | 0.99776 | 15.6667 | 244.2433 | 0.97697 | 11.3173 | 2209 | 250 | 1 | 494.2433 | 1.977 | CS2 | 15.8443 | 2209 | 350 | 1.4 | 844.2433 | 3.377 | CS2 | 69.2752 | 173.2222 | 120 | 0.48 | 964.2433 | 3.857 | CS2 | 15.6821 | 4591.2222 | 720 | 2.88 | 964.2433 | 3.857 | CS2 | 0 |  | 964.2433 | 3.857 | 964.2433 | 3.857 | CS2 | 4.6183 | 173.2222 | 8 | 0.032 | 972.2433 | 3.889 | CS2 | 98.1398 | 173.2222 | 170 | 0.68 | 1142.2433 | 4.569 | CS2 | 87.7486 | 173.2222 | 152 | 0.608 | 1294.2433 | 5.177 | CS2 | 63.5022 | 519.6667 | 330 | 1.32 | 1294.2433 | 5.177 | CS2 | 249.0526 | 519.6667 | 1294.2433 | 5.177 | 1294.2433 | 5.177 | CS2 | 92.136 | 173.2222 | 159.6 | 0.6384 | 1453.8433 | 5.8154 | CS2 | 0 | 173.2222 |  | 0 | 1453.8433 | 5.8154 | CS2 | 0 | 173.2222 |  | 0 | 1453.8433 | 5.8154 | CS2 | 30.712 | 519.6667 | 159.6 | 0.6384 | 1453.8433 | 5.8154 | CS2 | 47.1071 | 1039.3333 | 489.6 | 1.9584 | 1453.8433 | 5.8154 | CS2 | 139.8823 | 1039.3333 | 1453.8433 | 5.8154 | 1453.8433 | 5.8154 | CS2
|  |  | Promotion and Marketing | Person | 5000 | 20 | 1000 | 450 | 45 | 1000 | 1550 | 12 | 186 | 0.744 | 10 | 155 | 0.62 | 12 | 186 | 0.744 | 11.3333 | 175.6667 | 0.70267 | 2.4378 | 6153 | 150 | 0.6 | 325.6667 | 1.3027 | CS2 | 4.0631 | 6153 | 250 | 1 | 575.6667 | 2.3027 | CS2 | 63.5022 | 173.2222 | 110 | 0.44 | 685.6667 | 2.7427 | CS2 | 4.0868 | 12479.2222 | 510 | 2.04 | 685.6667 | 2.7427 | CS2 | 0 |  | 685.6667 | 2.7427 | 685.6667 | 2.7427 | CS2 | 3.2743 | 152.7037 | 5 | 0.02 | 690.6667 | 2.7627 | CS2 | 92.9032 | 172.2222 | 160 | 0.64 | 850.6667 | 3.4027 | CS2 | 523.7419 | 172.2222 | 902 | 3.608 | 1752.6667 | 7.0107 | CS2 | 214.6242 | 497.1481 | 1067 | 4.268 | 1752.6667 | 7.0107 | CS2 | 352.5441 | 497.1481 | 1752.6667 | 7.0107 | 1752.6667 | 7.0107 | CS2 | 549.929 | 172.2222 | 947.1 | 3.7884 | 2699.7667 | 10.7991 | CS2 | 0 | 172.2222 |  | 0 | 2699.7667 | 10.7991 | CS2 | 0 | 172.2222 |  | 0 | 2699.7667 | 10.7991 | CS2 | 183.3097 | 516.6667 | 947.1 | 3.7884 | 2699.7667 | 10.7991 | CS2 | 198.6655 | 1013.8148 | 2014.1 | 8.0564 | 2699.7667 | 10.7991 | CS2 | 266.2978 | 1013.8148 | 2699.7667 | 10.7991 | 2699.7667 | 10.7991 | CS2
|  |  | Monitoring and Evaluation | Person | 5000 | 20 | 1000 | 318 | 31.8 | 1000 | 1682 | 10 | 168.2 | 0.6728 | 10 | 168.2 | 0 | 10 | 168.2 | 0.6728 | 10 | 168.2 | 0.6728 | 4.583 | 2182 | 100 | 0.4 | 268.2 | 1.0728 | CS2 | 6.8744 | 2182 | 150 | 0.6 | 418.2 | 1.6728 | CS2 | 75.0481 | 173.2222 | 130 | 0.52 | 548.2 | 2.1928 | CS2 | 8.3752 | 4537.2222 | 380 | 1.52 | 548.2 | 2.1928 | CS2 | 0 |  | 548.2 | 2.1928 | 548.2 | 2.1928 | CS2 | 4.1617 | 168.2 | 7 | 0.028 | 555.2 | 2.2208 | CS2 | 80.2616 | 186.8889 | 150 | 0.6 | 705.2 | 2.8208 | CS2 | 176.5755 | 186.8889 | 330 | 1.32 | 1035.2 | 4.1408 | CS2 | 89.8561 | 541.9778 | 487 | 1.948 | 1035.2 | 4.1408 | CS2 | 191.0041 | 541.9778 | 1035.2 | 4.1408 | 1035.2 | 4.1408 | CS2 | 185.4043 | 186.8889 | 346.5 | 1.386 | 1381.7 | 5.5268 | CS2 | 0 | 186.8889 |  | 0 | 1381.7 | 5.5268 | CS2 | 0 | 186.8889 |  | 0 | 1381.7 | 5.5268 | CS2 | 61.8014 | 560.6667 | 346.5 | 1.386 | 1381.7 | 5.5268 | CS2 | 75.591 | 1102.6444 | 833.5 | 3.334 | 1381.7 | 5.5268 | CS2 | 125.3078 | 1102.6444 | 1381.7 | 5.5268 | 1381.7 | 5.5268 | CS2
|  |  | Innovation & VC improvement | Person | 5000 | 20 | 1000 | 528 | 52.8 | 1000 | 1472 | 12 | 176.64 | 0.70656 | 10 | 147.2 | 0.5888 | 12 | 176.64 | 0.70656 | 11.3333 | 166.8267 | 0.66731 | 6.0852 | 1972 | 120 | 0.48 | 286.8267 | 1.1473 | CS2 | 7.6065 | 1972 | 150 | 0.6 | 436.8267 | 1.7473 | CS2 | 54.8428 | 173.2222 | 95 | 0.38 | 531.8267 | 2.1273 | CS2 | 8.8652 | 4117.2222 | 365 | 1.46 | 531.8267 | 2.1273 | CS2 | 0 |  | 531.8267 | 2.1273 | 531.8267 | 2.1273 | CS2 | 3.4478 | 145.0193 | 5 | 0.02 | 536.8267 | 2.1473 | CS2 | 91.712 | 163.5556 | 150 | 0.6 | 686.8267 | 2.7473 | CS2 | 91.712 | 163.5556 | 150 | 0.6 | 836.8267 | 3.3473 | CS2 | 64.6008 | 472.1304 | 305 | 1.22 | 836.8267 | 3.3473 | CS2 | 177.2448 | 472.1304 | 836.8267 | 3.3473 | 836.8267 | 3.3473 | CS2 | 96.2976 | 163.5556 | 157.5 | 0.63 | 994.3267 | 3.9773 | CS2 | 0 | 163.5556 |  | 0 | 994.3267 | 3.9773 | CS2 | 0 | 163.5556 |  | 0 | 994.3267 | 3.9773 | CS2 | 32.0992 | 490.6667 | 157.5 | 0.63 | 994.3267 | 3.9773 | CS2 | 48.0371 | 962.797 | 462.5 | 1.85 | 994.3267 | 3.9773 | CS2 | 103.2748 | 962.797 | 994.3267 | 3.9773 | 994.3267 | 3.9773 | CS2
|  |  | National Policy and Standards of Biodigester and bioslurry | Polcy | 1 | 20 | 0.2 | 0 | 0 | 0.2 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 0.3 | 6 | 0.3 | 6 | CS2 | 30 | 1 | 0.3 | 6 | 0.6 | 12 | CS2 | 0 | 0.5 | 0 | 0 | 0.6 | 12 | CS2 | 24 | 2.5 | 0.6 | 12 | 0.6 | 12 | CS2 | 0 |  | 0.6 | 12 | 0.6 | 12 | CS2 | 0 | 0.06 | 0 | 0 | 0.6 | 12 | CS2 | 0 | 0.044444 | 0 | 0 | 0.6 | 12 | CS2 | 45 | 0.044444 | 0.02 | 0.4 | 0.62 | 12.4 | CS2 | 13.4328 | 0.14889 | 0.02 | 0.4 | 0.62 | 12.4 | CS2 | 416.4179 | 0.14889 | 0.62 | 12.4 | 0.62 | 12.4 | CS2 | 47.25 | 0.044444 | 0.021 | 0.42 | 0.641 | 12.82 | CS2 | 0 | 0.044444 |  | 0 | 0.641 | 12.82 | CS2 | 0 | 0.044444 |  | 0 | 0.641 | 12.82 | CS2 | 15.75 | 0.13333 | 0.021 | 0.42 | 0.641 | 12.82 | CS2 | 14.5276 | 0.28222 | 0.041 | 0.82 | 0.641 | 12.82 | CS2 | 227.126 | 0.28222 | 0.641 | 12.82 | 0.641 | 12.82 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 173.7 |  |  |  |  | 3.1211 |  |  | 2.1442 |  |  | 3.1211 |  |  | 8.3864 |  |  |  | 8.48 |  | 11.4997 |  |  |  |  | 9.6 |  | 21.0997 |  |  |  |  | 1.82 |  | 22.9197 |  |  |  |  | 19.9 |  | 22.9197 |  |  |  |  | 28.2864 |  | 22.9197 |  |  |  |  | 0.1 |  | 23.0197 |  |  |  |  | 2.52 |  | 25.5397 |  |  |  |  | 6.536 |  | 32.0757 |  |  |  |  | 9.156 |  | 32.0757 |  |  |  |  | 37.4424 |  | 32.0757 |  |  |  |  | 6.8628 |  | 38.9385 |  |  |  |  | 0 |  | 38.9385 |  |  |  |  | 0 |  | 38.9385 |  |  |  |  | 6.8628 |  | 38.9385 |  |  |  |  | 16.0188 |  | 38.9385 |  |  |  |  | 44.3052 |  | 38.9385
|  |  | Total for all Outputs | [5 empty] | 246.964 |  |  |  |  | 14.0432 |  |  | 20.2373 |  |  | 22.4996 | [6 empty] | 32.1986 |  | 52.0996 |  |  |  |  | 33.513 |  | 85.6126 |  |  |  |  | 34.7766 |  | 120.3891 |  |  |  |  | 100.4882 |  | 120.3891 |  |  |  |  | 157.2682 |  | 120.3891 |  |  |  |  | 3.7386 |  | 124.1277 |  |  |  |  | 9.7525 |  | 133.8802 |  |  |  |  | 17.2963 |  | 151.1765 |  |  |  |  | 30.7874 |  | 151.1765 |  |  |  |  | 188.0556 |  | 151.1765 |  |  |  |  | 21.0538 |  | 172.2303 |  |  |  |  | 0 |  | 172.2303 |  |  |  |  | 0 |  | 172.2303 |  |  |  |  | 21.0538 |  | 172.2303 |  |  |  |  | 51.8411 |  | 172.2303 |  |  |  |  | 209.1094 |  | 172.2303
|  |  | Original as of July 2021 (Dead formulation) | [5 empty] | 271.677 |  |  |  |  | 14.3259 |  |  | 22.4116 |  |  | 25.1023 | [6 empty] | 31.667 |  | 52.5712 |  |  |  |  | 23.1421 |  | 75.7133 |  |  |  |  | 19.8617 |  | 95.575 |  |  |  |  | 74.6708 |  | 95.575 |  |  |  |  | 136.5106 |  | 95.575 |  |  |  |  | 18.5617 |  | 114.1367 |  |  |  |  | 0 |  | 114.1367 |  |  |  |  | 0 |  | 114.1367 |  |  |  |  | 18.5617 |  | 114.1367 |  |  |  |  | 155.0724 |  | 114.1367 |  |  |  |  | 0 |  | 114.1367 |  |  |  |  | 0 |  | 114.1367 |  |  |  |  | 0
|  |  | Deviation | [5 empty] | -24.713 |  |  |  |  | -0.28269 |  |  | -2.1744 |  |  | -2.6027 | [6 empty] | 0.5316 | [6 empty] | 10.3709 | [6 empty] | 14.9149 | [20 empty] | -14.8232 | [6 empty] | 9.7525 | [6 empty] | 17.2963 | [20 empty] | 21.0538 | [6 empty] | 0 | [6 empty] | 0
Note on F32: User: Previous 80
Note on F33: User: Previous 80
Note on F44: User: Previous 3
Note on F45: User: Previous 3
Note on F49: User: Previous 3
Note on F50: User: Previous 3
Note on F53: User: Previous 5,300
Note on F54: User: Previous 24,000
Note on I32: User: Previous 20
Note on I33: User: Previous 20
Note on I53: User: Previous 1,325
Note on I54: User: Previous 6,000
Note on J54: User: Previous 5,847
Note on M32: User: Previous 35
Note on M33: User: Previous 35
Note on M35: User: Previous 0
Note on M53: User: Previous 1,325
Note on M54: User: Previous 6,000
Note on N6: User: Light Yellow fill color are edited during the meeting with PMU (Mr. Heng Bunny), CS2/DTL, CS1/DTL (PSH), and N&I M&E, on 10 August 2021, @PMU. Office.
Note on N32: User: Previous 20
Note on N33: User: Previous 20.2
Note on X13: user: To be filled by CS1
Note on X14: user: To be filled by CS1
Note on X27: user: To be filled by CS1
Note on X28: user: To be filled by CS1
Note on CL9: User: During this period, there is no CS5 member is mobilized into MOWRAM
in JV with SBK Research and Development
Implemented by

## Output 2
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS
OUTPUT 2
Status : January though Deember 2021
ACTIVITY |  | SUBACTIVITY | UNIT | OVERALL TARGET | Sub- Weight (%) |  | AWP 2020 |  |  | 2021 |  | Progress Jan 2021 |  |  | Progress Feb 2021 |  |  | Progress Mar 2021 |  |  | Progress Q1 2021 |  |  | Progress Apr. 2021 | [6 empty] | Progress May 2021 | [6 empty] | Progress Jun. 2021 | [6 empty] | Progress Q2. 2021 | [6 empty] | Progress First Six-monthly 2021 | [6 empty] | Progress Jul. 2021 | [6 empty] | Progress Aug. 2021 | [6 empty] | Progress Sept. 2021 | [6 empty] | Progress Q3. 2021 | [6 empty] | Progress First Nine-monthly 2021 | [6 empty] | Progress Oct. 2021 | [6 empty] | Progress Nov. 2021 | [6 empty] | Progress Dec. 2021 | [6 empty] | Progress Q4. 2021 | [6 empty] | Progress Second Six-monthly 2021 | [6 empty] | Progress Annually 2021
[6 empty] | Progress 2020 | Plan | Realisation |  | AWP | AWPB & Carry Over from 2020 | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Target | Actual progress | Weighted Progress | Cumulative Actual Progress (%) | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Actual Progress | Cummulative Weighted Progress | Responsible staff
[8 empty] | Nr | Physical %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 12 | 13 | 14 | 12 | 13 | 14 | 12 | 13 | 14 | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 |  |  | 14 |  | 12 |  | 13 |  |  | 14 |  | 12 |  | 13 |  |  | 14
2.a | 3 Additional climate-resilient varieties of rice and maize released | Development of new rice varieties | Varieties | 2 | 30 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.16667 | 0 | 0 | 0 | 0 | CS2 | 0 | 2 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.3333 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.16667 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.38889 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.38889 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.66667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.0556 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.0556 | 0 | 0 | 0 | 0 | CS2
|  | Development of new maize varieties | Variety | 1 | 10 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.16667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.3333 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.16667 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.38889 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.38889 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.66667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.0556 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.0556 | 0 | 0 | 0 | 0 | CS2
|  | Multiplication of existed rice varieties production of FS rice for PRD, PMD and CAR 16 | Seeds | 2 | 10 | 5 | 1 | 1 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.33333 | 0 | 0 | 0 | 0 | CS2 | 60 | 0.33333 | 0.2 | 1 | 0.2 | 1 | CS2 | 20 | 1 | 0.2 | 1 | 0.2 | 1 | CS2 | 0 |  | 0.2 | 1 | 0.2 | 1 | CS2 | 0 | 0 | 0 | 0 | 0.2 | 1 | CS2 | 99 | 0.11111 | 0.11 | 0.55 | 0.31 | 1.55 | CS2 | 99 | 0.11111 | 0.11 | 0.55 | 0.42 | 2.1 | CS2 | 99 | 0.22222 | 0.22 | 1.1 | 0.42 | 2.1 | CS2 | 189 | 0.22222 | 0.42 | 2.1 | 0.42 | 2.1 | CS2 | 103.95 | 0.11111 | 0.1155 | 0.5775 | 0.5355 | 2.6775 | CS2 | 0 | 0.11111 |  | 0 | 0.5355 | 2.6775 | CS2 | 0 | 0.11111 |  | 0 | 0.5355 | 2.6775 | CS2 | 34.65 | 0.33333 | 0.1155 | 0.5775 | 0.5355 | 2.6775 | CS2 | 60.39 | 0.55556 | 0.3355 | 1.6775 | 0.5355 | 2.6775 | CS2 | 96.39 | 0.55556 | 0.5355 | 2.6775 | 0.5355 | 2.6775 | CS2
|  | Multiplication of maize seed (CM1) varieties | Seeds | 1 | 10 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.44444 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.44444 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.66667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1111 | 0 | 0 | 0 | 0 | CS2
|  | Distribution of rice seeds for demonstration seed production (PRD, PMD) for WS and CAR 16 for DS | Seeds | 160 | 10 | 1.25 | 40 | 38.4 | 2.4 | 40 | 41.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.5333 | 0 | 0 | 0 | 0 | CS2 | 1.6376 | 30.5333 | 0.5 | 0.03125 | 0.5 | 0.03125 | CS2 | 101.5284 | 30.5333 | 31 | 1.9375 | 31.5 | 1.9688 | CS2 | 34.3886 | 91.6 | 31.5 | 1.9688 | 31.5 | 1.9688 | CS2 | 0 |  | 31.5 | 1.9688 | 31.5 | 1.9688 | CS2 | 0 | 0 | 0 | 0 | 31.5 | 1.9688 | CS2 | 0 | 0 | 0 | 0 | 31.5 | 1.9688 | CS2 | 99.9519 | 4.6222 | 4.62 | 0.28875 | 36.12 | 2.2575 | CS2 | 99.9519 | 4.6222 | 4.62 | 0.28875 | 36.12 | 2.2575 | CS2 | 781.4423 | 4.6222 | 36.12 | 2.2575 | 36.12 | 2.2575 | CS2 | 104.9495 | 4.6222 | 4.851 | 0.30319 | 40.971 | 2.5607 | CS2 | 0 | 4.6222 |  | 0 | 40.971 | 2.5607 | CS2 | 0 | 4.6222 |  | 0 | 40.971 | 2.5607 | CS2 | 34.9832 | 13.8667 | 4.851 | 0.30319 | 40.971 | 2.5607 | CS2 | 51.2254 | 18.4889 | 9.471 | 0.59194 | 40.971 | 2.5607 | CS2 | 221.598 | 18.4889 | 40.971 | 2.5607 | 40.971 | 2.5607 | CS2
|  | Distribution of maize for seed production | Seeds | 3 | 10 | 1 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.22222 |  | 0 | 0 | 0 | CS2 | 0 | 0.66667 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.88889 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.88889 | 0 | 0 | 0 | 0 | CS2
|  | Training of farmer group on BMP (240 courses) | Persons | 10000 | 5 |  | 2500 | 0 | 0 | 2500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 500 | 0.25 | 3.3333 | 166.6667 | 0.083333 | 0 | 625 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 625 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 625 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 1875 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 |  | 166.6667 | 0.083333 | 166.6667 | 0.083333 | CS2 | 0 | 0 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 555.5556 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 555.5556 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 1111.1111 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 15 | 1111.1111 | 166.6667 | 0.083333 | 166.6667 | 0.083333 | CS2 | 0 | 555.5556 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 555.5556 |  | 0 | 166.6667 | 0.083333 | CS2 | 0 | 555.5556 |  | 0 | 166.6667 | 0.083333 | CS2 | 0 | 1666.6667 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 0 | 2777.7778 | 0 | 0 | 166.6667 | 0.083333 | CS2 | 6 | 2777.7778 | 166.6667 | 0.083333 | 166.6667 | 0.083333 | CS2
|  | Training of farmer group on rice seed produciton (120 courses) | Persons | 4000 | 5 |  | 1000 | 0 | 0 | 1000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 222.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 222.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 444.4444 | 0 | 0 | 0 | 0 | CS2 | 0 | 444.4444 | 0 | 0 | 0 | 0 | CS2 | 0 | 222.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 222.2222 |  | 0 | 0 | 0 | CS2 | 0 | 222.2222 |  | 0 | 0 | 0 | CS2 | 0 | 666.6667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1111.1111 | 0 | 0 | 0 | 0 | CS2 | 0 | 1111.1111 | 0 | 0 | 0 | 0 | CS2
|  | Field day (120 events) | People | 15000 | 10 |  | 1500 | 0 | 0 | 1500 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 3000 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 333.3333 | 0 | 0 | 0 | 0 | CS2 | 0 | 333.3333 | 0 | 0 | 0 | 0 | CS2 | 0 | 666.6667 | 0 | 0 | 0 | 0 | CS2 | 0 | 666.6667 | 0 | 0 | 0 | 0 | CS2 | 0 | 333.3333 | 0 | 0 | 0 | 0 | CS2 | 0 | 333.3333 |  | 0 | 0 | 0 | CS2 | 0 | 333.3333 |  | 0 | 0 | 0 | CS2 | 0 | 1000 | 0 | 0 | 0 | 0 | CS2 | 0 | 1666.6667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1666.6667 | 0 | 0 | 0 | 0 | CS2
|  | Site identification for Cassava seeds demonstration | Demo | 40 | 5 |  | 0 | 0 | 0 | 10 | 10 | 100 | 10 | 1.25 | 100 | 10 | 1.25 | 100 | 10 | 1.25 | 100 | 10 | 1.25 | 100 | 10 | 10 | 1.25 | 20 | 2.5 | CS2 | 0 | 0 | 0 | 0 | 20 | 2.5 | CS2 | 0 | 0 | 0 | 0 | 20 | 2.5 | CS2 | 100 | 10 | 10 | 1.25 | 20 | 2.5 | CS2 | 0 |  | 20 | 2.5 | 20 | 2.5 | CS2 | 0 | 0 | 0 | 0 | 20 | 2.5 | CS2 | 0 | 0 | 0 | 0 | 20 | 2.5 | CS2 | 99.9 | 1.1111 | 1.11 | 0.13875 | 21.11 | 2.6387 | CS2 | 99.9 | 1.1111 | 1.11 | 0.13875 | 21.11 | 2.6387 | CS2 | 1899.9 | 1.1111 | 21.11 | 2.6387 | 21.11 | 2.6387 | CS2 | 104.895 | 1.1111 | 1.1655 | 0.14569 | 22.2755 | 2.7844 | CS2 | 0 | 1.1111 |  | 0 | 22.2755 | 2.7844 | CS2 | 0 | 1.1111 |  | 0 | 22.2755 | 2.7844 | CS2 | 34.965 | 3.3333 | 1.1655 | 0.14569 | 22.2755 | 2.7844 | CS2 | 51.1987 | 4.4444 | 2.2755 | 0.28444 | 22.2755 | 2.7844 | CS2 | 501.1988 | 4.4444 | 22.2755 | 2.7844 | 22.2755 | 2.7844 | CS2
|  | Laser Land Leveling (LLL) | Demo/ha | 4000 | 5 |  | 0 | 0 | 0 | 500 | 500 | 30 | 150 | 0.1875 | 50 | 250 | 0.3125 | 50 | 250 | 0.3125 | 43.3333 | 216.6667 | 0.27083 | 487.3684 | 95 | 463 | 0.57875 | 679.6667 | 0.84958 | CS2 | 487.3684 | 95 | 463 | 0.57875 | 1142.6667 | 1.4283 | CS2 | 127.6596 | 94 | 120 | 0.15 | 1262.6667 | 1.5783 | CS2 | 368.3099 | 284 | 1046 | 1.3075 | 1262.6667 | 1.5783 | CS2 | 0 |  | 1262.6667 | 1.5783 | 1262.6667 | 1.5783 | CS2 | 0 | 0 | 0 | 0 | 1262.6667 | 1.5783 | CS2 | 0 | 0 | 0 | 0 | 1262.6667 | 1.5783 | CS2 | 100.008 | 55.5556 | 55.56 | 0.06945 | 1318.2267 | 1.6478 | CS2 | 100.008 | 55.5556 | 55.56 | 0.06945 | 1318.2267 | 1.6478 | CS2 | 2372.808 | 55.5556 | 1318.2267 | 1.6478 | 1318.2267 | 1.6478 | CS2 | 105.0084 | 55.5556 | 58.338 | 0.072923 | 1376.5647 | 1.7207 | CS2 | 0 | 55.5556 |  | 0 | 1376.5647 | 1.7207 | CS2 | 0 | 55.5556 |  | 0 | 1376.5647 | 1.7207 | CS2 | 35.0028 | 166.6667 | 58.338 | 0.072923 | 1376.5647 | 1.7207 | CS2 | 51.2541 | 222.2222 | 113.898 | 0.14237 | 1376.5647 | 1.7207 | CS2 | 619.4541 | 222.2222 | 1376.5647 | 1.7207 | 1376.5647 | 1.7207 | CS2
|  | sub total |  |  | 100 |  |  |  | 7.4 |  |  |  |  | 1.4375 |  |  | 1.5625 |  |  | 1.8125 |  |  | 1.6042 |  |  |  | 1.8288 |  | 3.4329 |  |  |  |  | 0.61 |  | 4.0429 |  |  |  |  | 3.0875 |  | 7.1304 |  |  |  |  | 5.5263 |  | 7.1304 |  |  |  |  | 7.1304 |  | 7.1304 |  |  |  |  | 0 |  | 7.1304 |  |  |  |  | 0.55 |  | 7.6804 |  |  |  |  | 1.047 |  | 8.7274 |  |  |  |  | 1.597 |  | 8.7274 |  |  |  |  | 8.7274 |  | 8.7274 |  |  |  |  | 1.0993 |  | 9.8267 |  |  |  |  | 0 |  | 9.8267 |  |  |  |  | 0 |  | 9.8267 |  |  |  |  | 1.0993 |  | 9.8267 |  |  |  |  | 2.6962 |  | 9.8267 |  |  |  |  | 9.8267 |  | 9.8267
2.b | 40,000 Farmers trained in Climate-smart Agriculture and agribusiness development skills | Training of TOT-Trainers | Persons | 80 | 3 | 1 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 40 | 0 | 0 | 0 | 0 | CS2 | 40 | 40 | 16 | 0.6 | 16 | 0.6 | CS2 | 20 | 80 | 16 | 0.6 | 16 | 0.6 | CS2 | 0 |  | 16 | 0.6 | 16 | 0.6 | CS2 | 0 | 40 | 0 | 0 | 16 | 0.6 | CS2 | 100 | 20 | 20 | 0.75 | 36 | 1.35 | CS2 | 1080 | 8.8889 | 96 | 3.6 | 132 | 4.95 | CS2 | 168.3871 | 68.8889 | 116 | 4.35 | 132 | 4.95 | CS2 | 191.6129 | 68.8889 | 132 | 4.95 | 132 | 4.95 | CS2 | 1134 | 8.8889 | 100.8 | 3.78 | 232.8 | 8.73 | CS2 | 0 | 8.8889 |  | 0 | 232.8 | 8.73 | CS2 | 0 | 8.8889 |  | 0 | 232.8 | 8.73 | CS2 | 378 | 26.6667 | 100.8 | 3.78 | 232.8 | 8.73 | CS2 | 226.8837 | 95.5556 | 216.8 | 8.13 | 232.8 | 8.73 | CS2 | 243.6279 | 95.5556 | 232.8 | 8.73 | 232.8 | 8.73 | CS2
|  | Drafting of training material for climate smart agriculture | set | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 5 | 0.05 | 0.1 | 10 | 0.1 | 0.2 | 10 | 0.1 | 0.2 | 8.3333 | 0.083333 | 0.16667 | 100 | 1 | 1 | 2 | 1.0833 | 2.1667 | CS2 | 0 | 0 | 1 | 2 | 2.0833 | 4.1667 | CS2 | 0 | 0 | 0 | 0 | 2.0833 | 4.1667 | CS2 | 200 | 1 | 2 | 4 | 2.0833 | 4.1667 | CS2 | 0 |  | 2.0833 | 4.1667 | 2.0833 | 4.1667 | CS2 | 0 | 0 | 0 | 0 | 2.0833 | 4.1667 | CS2 | 0 | 0 | 0 | 0 | 2.0833 | 4.1667 | CS2 | 99 | 0.11111 | 0.11 | 0.22 | 2.1933 | 4.3867 | CS2 | 99 | 0.11111 | 0.11 | 0.22 | 2.1933 | 4.3867 | CS2 | 1974 | 0.11111 | 2.1933 | 4.3867 | 2.1933 | 4.3867 | CS2 | 103.95 | 0.11111 | 0.1155 | 0.231 | 2.3088 | 4.6177 | CS2 | 0 | 0.11111 |  | 0 | 2.3088 | 4.6177 | CS2 | 0 | 0.11111 |  | 0 | 2.3088 | 4.6177 | CS2 | 34.65 | 0.33333 | 0.1155 | 0.231 | 2.3088 | 4.6177 | CS2 | 50.7375 | 0.44444 | 0.2255 | 0.451 | 2.3088 | 4.6177 | CS2 | 519.4875 | 0.44444 | 2.3088 | 4.6177 | 2.3088 | 4.6177 | CS2
|  | Implementation of comprehensive Needs assessment | set | 4 | 2 | 1 | 1 | 2.5 | 1.25 | 4 | 2.5 | 5 | 0.125 | 0.0625 | 10 | 0.25 | 0.125 | 12 | 0.3 | 0.15 | 9 | 0.225 | 0.1125 | 80 | 2.5 | 2 | 1 | 2.225 | 1.1125 | CS2 | 0 | 0 | 2.5 | 1.25 | 4.725 | 2.3625 | CS2 | 0 | 0 | 0 | 0 | 4.725 | 2.3625 | CS2 | 180 | 2.5 | 4.5 | 2.25 | 4.725 | 2.3625 | CS2 | 0 |  | 4.725 | 2.3625 | 4.725 | 2.3625 | CS2 | 0 | 0 | 0 | 0 | 4.725 | 2.3625 | CS2 | 0 | 0 | 0 | 0 | 4.725 | 2.3625 | CS2 | 10080 | 0.27778 | 28 | 14 | 32.725 | 16.3625 | CS2 | 10080 | 0.27778 | 28 | 14 | 32.725 | 16.3625 | CS2 | 11781 | 0.27778 | 32.725 | 16.3625 | 32.725 | 16.3625 | CS2 | 10584 | 0.27778 | 29.4 | 14.7 | 62.125 | 31.0625 | CS2 | 0 | 0.27778 |  | 0 | 62.125 | 31.0625 | CS2 | 0 | 0.27778 |  | 0 | 62.125 | 31.0625 | CS2 | 3528 | 0.83333 | 29.4 | 14.7 | 62.125 | 31.0625 | CS2 | 5166 | 1.1111 | 57.4 | 28.7 | 62.125 | 31.0625 | CS2 | 5591.25 | 1.1111 | 62.125 | 31.0625 | 62.125 | 31.0625 | CS2
|  | Drafting of training material for agribusiness development | set | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 5 | 0.05 | 0.15 | 10 | 0.1 | 0.3 | 12 | 0.12 | 0.36 | 9 | 0.09 | 0.27 | 100 | 1 | 1 | 3 | 1.09 | 3.27 | CS2 | 0 | 0 | 1 | 3 | 2.09 | 6.27 | CS2 | 0 | 0 | 0 | 0 | 2.09 | 6.27 | CS2 | 200 | 1 | 2 | 6 | 2.09 | 6.27 | CS2 | 0 |  | 2.09 | 6.27 | 2.09 | 6.27 | CS2 | 0 | 0 | 0 | 0 | 2.09 | 6.27 | CS2 | 0 | 0 | 0 | 0 | 2.09 | 6.27 | CS2 | 99 | 0.11111 | 0.11 | 0.33 | 2.2 | 6.6 | CS2 | 99 | 0.11111 | 0.11 | 0.33 | 2.2 | 6.6 | CS2 | 1980 | 0.11111 | 2.2 | 6.6 | 2.2 | 6.6 | CS2 | 103.95 | 0.11111 | 0.1155 | 0.3465 | 2.3155 | 6.9465 | CS2 | 0 | 0.11111 |  | 0 | 2.3155 | 6.9465 | CS2 | 0 | 0.11111 |  | 0 | 2.3155 | 6.9465 | CS2 | 34.65 | 0.33333 | 0.1155 | 0.3465 | 2.3155 | 6.9465 | CS2 | 50.7375 | 0.44444 | 0.2255 | 0.6765 | 2.3155 | 6.9465 | CS2 | 520.9875 | 0.44444 | 2.3155 | 6.9465 | 2.3155 | 6.9465 | CS2
|  | Farmers trained on CAMGAP standards | Persons | 500 | 15 | 250 | 100 | 80 | 2.4 | 100 | 120 | 5 | 6 | 0.18 | 10 | 12 | 0.36 | 10 | 12 | 0.36 | 8.3333 | 10 | 0.3 | 0 | 13.3333 | 0 | 0 | 10 | 0.3 | CS2 | 0 | 13.3333 | 0 | 0 | 10 | 0.3 | CS2 | 97.5 | 13.3333 | 13 | 0.39 | 23 | 0.69 | CS2 | 32.5 | 40 | 13 | 0.39 | 23 | 0.69 | CS2 | 0 |  | 23 | 0.69 | 23 | 0.69 | CS2 | 37.5 | 13.3333 | 5 | 0.15 | 28 | 0.84 | CS2 | 112.5 | 13.3333 | 15 | 0.45 | 43 | 1.29 | CS2 | 0 | 13.3333 | 0 | 0 | 43 | 1.29 | CS2 | 50 | 40 | 20 | 0.6 | 43 | 1.29 | CS2 | 107.5 | 40 | 43 | 1.29 | 43 | 1.29 | CS2 | 0 | 13.3333 | 0 | 0 | 43 | 1.29 | CS2 | 0 | 13.3333 |  | 0 | 43 | 1.29 | CS2 | 0 | 13.3333 |  | 0 | 43 | 1.29 | CS2 | 0 | 40 | 0 | 0 | 43 | 1.29 | CS2 | 25 | 80 | 20 | 0.6 | 43 | 1.29 | CS2 | 53.75 | 80 | 43 | 1.29 | 43 | 1.29 | CS2
|  | Farmers trained on CSA | Persons | 20000 | 25 | 2500 | 4000 | 2200 | 2.75 | 4000 | 5800 | 5 | 290 | 0.3625 | 10 | 580 | 0.725 | 10 | 580 | 0.725 | 8.3333 | 483.3333 | 0.60417 | 0 | 644.4444 | 0 | 0 | 483.3333 | 0.60417 | CS2 | 0 | 644.4444 | 0 | 0 | 483.3333 | 0.60417 | CS2 | 14.7414 | 644.4444 | 95 | 0.11875 | 578.3333 | 0.72292 | CS2 | 4.9138 | 1933.3333 | 95 | 0.11875 | 578.3333 | 0.72292 | CS2 | 0 |  | 578.3333 | 0.72292 | 578.3333 | 0.72292 | CS2 | 1.2414 | 644.4444 | 8 | 0.01 | 586.3333 | 0.73292 | CS2 | 12.4138 | 644.4444 | 80 | 0.1 | 666.3333 | 0.83292 | CS2 | 0 | 644.4444 | 0 | 0 | 666.3333 | 0.83292 | CS2 | 4.5517 | 1933.3333 | 88 | 0.11 | 666.3333 | 0.83292 | CS2 | 34.4655 | 1933.3333 | 666.3333 | 0.83292 | 666.3333 | 0.83292 | CS2 | 0 | 644.4444 | 0 | 0 | 666.3333 | 0.83292 | CS2 | 0 | 644.4444 |  | 0 | 666.3333 | 0.83292 | CS2 | 0 | 644.4444 |  | 0 | 666.3333 | 0.83292 | CS2 | 0 | 1933.3333 | 0 | 0 | 666.3333 | 0.83292 | CS2 | 2.2759 | 3866.6667 | 88 | 0.11 | 666.3333 | 0.83292 | CS2 | 17.2328 | 3866.6667 | 666.3333 | 0.83292 | 666.3333 | 0.83292 | CS2
|  | Farmers trained on SRP | Persons | 20000 | 20 | 2000 | 4000 | 2750 | 2.75 | 4000 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583.3333 | 0 | 0 | 0 | 0 | CS2 | 0 | 583.3333 | 0 | 0 | 0 | 0 | CS2 | 17.1429 | 583.3333 | 100 | 0.1 | 100 | 0.1 | CS2 | 5.7143 | 1750 | 100 | 0.1 | 100 | 0.1 | CS2 | 0 |  | 100 | 0.1 | 100 | 0.1 | CS2 | 1.2 | 583.3333 | 7 | 0.007 | 107 | 0.107 | CS2 | 9.4286 | 583.3333 | 55 | 0.055 | 162 | 0.162 | CS2 | 41.1429 | 583.3333 | 240 | 0.24 | 402 | 0.402 | CS2 | 17.2571 | 1750 | 302 | 0.302 | 402 | 0.402 | CS2 | 22.9714 | 1750 | 402 | 0.402 | 402 | 0.402 | CS2 | 43.2 | 583.3333 | 252 | 0.252 | 654 | 0.654 | CS2 | 0 | 583.3333 |  | 0 | 654 | 0.654 | CS2 | 0 | 583.3333 |  | 0 | 654 | 0.654 | CS2 | 14.4 | 1750 | 252 | 0.252 | 654 | 0.654 | CS2 | 15.8286 | 3500 | 554 | 0.554 | 654 | 0.654 | CS2 | 18.6857 | 3500 | 654 | 0.654 | 654 | 0.654 | CS2
|  | Farm mechanization and agriculture conservation | Persons | 9500 | 15 | 250 | 1900 | 1741.6667 | 2.75 | 1900 | 2058.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228.7037 | 0 | 0 | 0 | 0 | CS2 | 0 | 228.7037 | 0 | 0 | 0 | 0 | CS2 | 54.6559 | 228.7037 | 125 | 0.19737 | 125 | 0.19737 | CS2 | 18.2186 | 686.1111 | 125 | 0.19737 | 125 | 0.19737 | CS2 | 0 |  | 125 | 0.19737 | 125 | 0.19737 | CS2 | 2.6235 | 228.7037 | 6 | 0.0094737 | 131 | 0.20684 | CS2 | 19.6761 | 228.7037 | 45 | 0.071053 | 176 | 0.27789 | CS2 | 0 | 228.7037 | 0 | 0 | 176 | 0.27789 | CS2 | 7.4332 | 686.1111 | 51 | 0.080526 | 176 | 0.27789 | CS2 | 25.6518 | 686.1111 | 176 | 0.27789 | 176 | 0.27789 | CS2 | 0 | 228.7037 | 0 | 0 | 176 | 0.27789 | CS2 | 0 | 228.7037 |  | 0 | 176 | 0.27789 | CS2 | 0 | 228.7037 |  | 0 | 176 | 0.27789 | CS2 | 0 | 686.1111 | 0 | 0 | 176 | 0.27789 | CS2 | 3.7166 | 1372.2222 | 51 | 0.080526 | 176 | 0.27789 | CS2 | 12.8259 | 1372.2222 | 176 | 0.27789 | 176 | 0.27789 | CS2
|  | Agriculture Cooperative (board members) | Persons | 20000 | 15 | 250 | 4000 | 106.6667 | 0.08 | 4000 | 7893.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877.037 | 0 | 0 | 0 | 0 | CS2 | 0 | 877.037 | 0 | 0 | 0 | 0 | CS2 | 13.1123 | 877.037 | 115 | 0.08625 | 115 | 0.08625 | CS2 | 4.3708 | 2631.1111 | 115 | 0.08625 | 115 | 0.08625 | CS2 | 0 |  | 115 | 0.08625 | 115 | 0.08625 | CS2 | 0.5701 | 877.037 | 5 | 0.00375 | 120 | 0.09 | CS2 | 7.9814 | 877.037 | 70 | 0.0525 | 190 | 0.1425 | CS2 | 0 | 877.037 | 0 | 0 | 190 | 0.1425 | CS2 | 2.8505 | 2631.1111 | 75 | 0.05625 | 190 | 0.1425 | CS2 | 7.2213 | 2631.1111 | 190 | 0.1425 | 190 | 0.1425 | CS2 | 0 | 877.037 | 0 | 0 | 190 | 0.1425 | CS2 | 0 | 877.037 |  | 0 | 190 | 0.1425 | CS2 | 0 | 877.037 |  | 0 | 190 | 0.1425 | CS2 | 0 | 2631.1111 | 0 | 0 | 190 | 0.1425 | CS2 | 1.4253 | 5262.2222 | 75 | 0.05625 | 190 | 0.1425 | CS2 | 3.6106 | 5262.2222 | 190 | 0.1425 | 190 | 0.1425 | CS2
|  | subtotal |  |  | 100 |  |  |  | 16.98 |  |  |  |  | 0.855 |  |  | 1.71 |  |  | 1.795 |  |  | 1.4533 |  |  |  | 6 |  | 7.4533 |  |  |  |  | 6.25 |  | 13.7033 |  |  |  |  | 1.4924 |  | 15.1957 |  |  |  |  | 13.7424 |  | 15.1957 |  |  |  |  | 15.1957 |  | 15.1957 |  |  |  |  | 0.18022 |  | 15.3759 |  |  |  |  | 1.4786 |  | 16.8545 |  |  |  |  | 18.39 |  | 35.2445 |  |  |  |  | 20.0488 |  | 35.2445 |  |  |  |  | 35.2445 |  | 35.2445 |  |  |  |  | 19.3095 |  | 54.554 |  |  |  |  | 0 |  | 54.554 |  |  |  |  | 0 |  | 54.554 |  |  |  |  | 19.3095 |  | 54.554 |  |  |  |  | 39.3583 |  | 54.554 |  |  |  |  | 54.554 |  | 54.554
2.c.1 | 27 FWUCS of FWUGS made operational | Preparation of training materials | set | 1 | 2.5 | 5 | 1 | 0.2 | 0.5 | 0 | 0.8 | 0 | 0 | 0 | 5 | 0.04 | 0.1 | 5 | 0.04 | 0.1 | 3.3333 | 0.026667 | 0.066667 | 37.5 | 0.8 | 0.3 | 0.75 | 0.32667 | 0.81667 | CS2 | 25 | 0.8 | 0.2 | 0.5 | 0.52667 | 1.3167 | CS2 | 37.5 | 0.8 | 0.3 | 0.75 | 0.82667 | 2.0667 | CS2 | 33.3333 | 2.4 | 0.8 | 2 | 0.82667 | 2.0667 | CS2 | 0 |  | 0.82667 | 2.0667 | 0.82667 | 2.0667 | CS2 | 0 | 0 | 0 | 0 | 0.82667 | 2.0667 | CS2 | 0 | 0 | 0 | 0 | 0.82667 | 2.0667 | CS2 | 101.25 | 0.088889 | 0.09 | 0.225 | 0.91667 | 2.2917 | CS2 | 101.25 | 0.088889 | 0.09 | 0.225 | 0.91667 | 2.2917 | CS2 | 1031.25 | 0.088889 | 0.91667 | 2.2917 | 0.91667 | 2.2917 | CS2 | 106.3125 | 0.088889 | 0.0945 | 0.23625 | 1.0112 | 2.5279 | CS2 | 0 | 0.088889 |  | 0 | 1.0112 | 2.5279 | CS2 | 0 | 0.088889 |  | 0 | 1.0112 | 2.5279 | CS2 | 35.4375 | 0.26667 | 0.0945 | 0.23625 | 1.0112 | 2.5279 | CS2 | 51.8906 | 0.35556 | 0.1845 | 0.46125 | 1.0112 | 2.5279 | CS2 | 284.3906 | 0.35556 | 1.0112 | 2.5279 | 1.0112 | 2.5279 | CS2
|  | Initial meeting with local authorities | meeting | 27 | 5 | 1.19 | 10 | 14.04 | 2.6 | 9 | 4.96 | 100 | 4.96 | 0.91852 | 100 | 4.96 | 0.91852 | 100 | 4.96 | 0.91852 | 100 | 4.96 | 0.91852 | 10.0806 | 4.96 | 0.5 | 0.092593 | 5.46 | 1.0111 | CS2 | 4.0323 | 4.96 | 0.2 | 0.037037 | 5.66 | 1.0481 | CS2 | 50.4032 | 4.96 | 2.5 | 0.46296 | 8.16 | 1.5111 | CS2 | 21.5054 | 14.88 | 3.2 | 0.59259 | 8.16 | 1.5111 | CS2 | 0 |  | 8.16 | 1.5111 | 8.16 | 1.5111 | CS2 | 1.0081 | 4.96 | 0.05 | 0.0092593 | 8.21 | 1.5204 | CS2 | 99.7984 | 0.55111 | 0.55 | 0.10185 | 8.76 | 1.6222 | CS2 | 54.4355 | 0.55111 | 0.3 | 0.055556 | 9.06 | 1.6778 | CS2 | 14.846 | 6.0622 | 0.9 | 0.16667 | 9.06 | 1.6778 | CS2 | 149.4501 | 6.0622 | 9.06 | 1.6778 | 9.06 | 1.6778 | CS2 | 57.1573 | 0.55111 | 0.315 | 0.058333 | 9.375 | 1.7361 | CS2 | 0 | 0.55111 |  | 0 | 9.375 | 1.7361 | CS2 | 0 | 0.55111 |  | 0 | 9.375 | 1.7361 | CS2 | 19.0524 | 1.6533 | 0.315 | 0.058333 | 9.375 | 1.7361 | CS2 | 15.7474 | 7.7156 | 1.215 | 0.225 | 9.375 | 1.7361 | CS2 | 121.5078 | 7.7156 | 9.375 | 1.7361 | 9.375 | 1.7361 | CS2
|  | Village meeting | meeting | 54 | 10 | 1.19 | 10 | 10.8 | 2 | 9 | 8.2 | 100 | 8.2 | 1.5185 | 100 | 8.2 | 1.5185 | 100 | 8.2 | 1.5185 | 100 | 8.2 | 1.5185 | 24.3902 | 8.2 | 2 | 0.37037 | 10.2 | 1.8889 | CS2 | 0 | 8.2 | 0 | 0 | 10.2 | 1.8889 | CS2 | 42.6829 | 8.2 | 3.5 | 0.64815 | 13.7 | 2.537 | CS2 | 22.3577 | 24.6 | 5.5 | 1.0185 | 13.7 | 2.537 | CS2 | 0 |  | 13.7 | 2.537 | 13.7 | 2.537 | CS2 | 0.60976 | 8.2 | 0.05 | 0.0092593 | 13.75 | 2.5463 | CS2 | 99.878 | 0.91111 | 0.91 | 0.16852 | 14.66 | 2.7148 | CS2 | 54.878 | 0.91111 | 0.5 | 0.092593 | 15.16 | 2.8074 | CS2 | 14.5676 | 10.0222 | 1.46 | 0.27037 | 15.16 | 2.8074 | CS2 | 151.2639 | 10.0222 | 15.16 | 2.8074 | 15.16 | 2.8074 | CS2 | 57.622 | 0.91111 | 0.525 | 0.097222 | 15.685 | 2.9046 | CS2 | 0 | 0.91111 |  | 0 | 15.685 | 2.9046 | CS2 | 0 | 0.91111 |  | 0 | 15.685 | 2.9046 | CS2 | 19.2073 | 2.7333 | 0.525 | 0.097222 | 15.685 | 2.9046 | CS2 | 15.5618 | 12.7556 | 1.985 | 0.36759 | 15.685 | 2.9046 | CS2 | 122.966 | 12.7556 | 15.685 | 2.9046 | 15.685 | 2.9046 | CS2
|  | Screening potential candidates FWUC committee | FWUC | 27 | 10 | 1.19 | 10 | 5.4 | 2 | 9 | 13.6 | 40 | 5.44 | 2.0148 | 90 | 12.24 | 4.5333 | 92 | 12.512 | 4.6341 | 74 | 10.064 | 3.7274 | 7.3529 | 13.6 | 1 | 0.37037 | 11.064 | 4.0978 | CS2 | 0 | 13.6 | 0 | 0 | 11.064 | 4.0978 | CS2 | 0 | 13 | 0 | 0 | 11.064 | 4.0978 | CS2 | 2.4876 | 40.2 | 1 | 0.37037 | 11.064 | 4.0978 | CS2 | 0 |  | 11.064 | 4.0978 | 11.064 | 4.0978 | CS2 | 0 | 13 | 0 | 0 | 11.064 | 4.0978 | CS2 | 0 | 1.5111 | 0 | 0 | 11.064 | 4.0978 | CS2 | 1.9853 | 1.5111 | 0.03 | 0.011111 | 11.094 | 4.1089 | CS2 | 0.18724 | 16.0222 | 0.03 | 0.011111 | 11.094 | 4.1089 | CS2 | 69.2413 | 16.0222 | 11.094 | 4.1089 | 11.094 | 4.1089 | CS2 | 2.0846 | 1.5111 | 0.0315 | 0.011667 | 11.1255 | 4.1206 | CS2 | 0 | 1.5111 |  | 0 | 11.1255 | 4.1206 | CS2 | 0 | 1.5111 |  | 0 | 11.1255 | 4.1206 | CS2 | 0.69485 | 4.5333 | 0.0315 | 0.011667 | 11.1255 | 4.1206 | CS2 | 0.29919 | 20.5556 | 0.0615 | 0.022778 | 11.1255 | 4.1206 | CS2 | 54.1241 | 20.5556 | 11.1255 | 4.1206 | 11.1255 | 4.1206 | CS2
|  | Candidate selection | FWUC | 27 | 10 | 1.19 | 10 | 5.4 | 2 | 9 | 13.6 | 40 | 5.44 | 2.0148 | 90 | 12.24 | 4.5333 | 92 | 12.512 | 4.6341 | 74 | 10.064 | 3.7274 | 0 | 13.6 | 0 | 0 | 10.064 | 3.7274 | CS2 | 0 | 13.6 | 0 | 0 | 10.064 | 3.7274 | CS2 | 0 | 13 | 0 | 0 | 10.064 | 3.7274 | CS2 | 0 | 40.2 | 0 | 0 | 10.064 | 3.7274 | CS2 | 0 |  | 10.064 | 3.7274 | 10.064 | 3.7274 | CS2 | 0 | 13 | 0 | 0 | 10.064 | 3.7274 | CS2 | 0 | 1.5111 | 0 | 0 | 10.064 | 3.7274 | CS2 | 231.6176 | 1.5111 | 3.5 | 1.2963 | 13.564 | 5.0237 | CS2 | 21.8447 | 16.0222 | 3.5 | 1.2963 | 13.564 | 5.0237 | CS2 | 84.6574 | 16.0222 | 13.564 | 5.0237 | 13.564 | 5.0237 | CS2 | 243.1985 | 1.5111 | 3.675 | 1.3611 | 17.239 | 6.3848 | CS2 | 0 | 1.5111 |  | 0 | 17.239 | 6.3848 | CS2 | 0 | 1.5111 |  | 0 | 17.239 | 6.3848 | CS2 | 81.0662 | 4.5333 | 3.675 | 1.3611 | 17.239 | 6.3848 | CS2 | 34.9054 | 20.5556 | 7.175 | 2.6574 | 17.239 | 6.3848 | CS2 | 83.8654 | 20.5556 | 17.239 | 6.3848 | 17.239 | 6.3848 | CS2
|  | Village representation election | FWUC | 27 | 10 | 1.19 | 10 | 2.7 | 1 | 9 | 16.3 | 0 | 0 | 0 | 90 | 14.67 | 5.4333 | 92 | 14.996 | 5.5541 | 60.6667 | 9.8887 | 3.6625 | 12.2699 | 16.3 | 2 | 0.74074 | 11.8887 | 4.4032 | CS2 | 0 | 16.3 | 0 | 0 | 11.8887 | 4.4032 | CS2 | 43.75 | 16 | 7 | 2.5926 | 18.8887 | 6.9958 | CS2 | 18.5185 | 48.6 | 9 | 3.3333 | 18.8887 | 6.9958 | CS2 | 0 |  | 18.8887 | 6.9958 | 18.8887 | 6.9958 | CS2 | 0 | 16 | 0 | 0 | 18.8887 | 6.9958 | CS2 | 0 | 1.8111 | 0 | 0 | 18.8887 | 6.9958 | CS2 | 193.2515 | 1.8111 | 3.5 | 1.2963 | 22.3887 | 8.2921 | CS2 | 17.8369 | 19.6222 | 3.5 | 1.2963 | 22.3887 | 8.2921 | CS2 | 114.0985 | 19.6222 | 22.3887 | 8.2921 | 22.3887 | 8.2921 | CS2 | 202.9141 | 1.8111 | 3.675 | 1.3611 | 26.0637 | 9.6532 | CS2 | 0 | 1.8111 |  | 0 | 26.0637 | 9.6532 | CS2 | 0 | 1.8111 |  | 0 | 26.0637 | 9.6532 | CS2 | 67.638 | 5.4333 | 3.675 | 1.3611 | 26.0637 | 9.6532 | CS2 | 28.6364 | 25.0556 | 7.175 | 2.6574 | 26.0637 | 9.6532 | CS2 | 104.0235 | 25.0556 | 26.0637 | 9.6532 | 26.0637 | 9.6532 | CS2
|  | FWUC committee election | FWUC | 27 | 15 | 1.19 | 10 | 0 | 0 | 9 | 19 | 0 | 0 | 0 | 10 | 1.9 | 1.0556 | 95 | 18.05 | 10.0278 | 35 | 6.65 | 3.6944 | 0 | 19 | 0 | 0 | 6.65 | 3.6944 | CS2 | 0 | 19 | 0 | 0 | 6.65 | 3.6944 | CS2 | 0 | 19 | 0 | 0 | 6.65 | 3.6944 | CS2 | 0 | 57 | 0 | 0 | 6.65 | 3.6944 | CS2 | 0 |  | 6.65 | 3.6944 | 6.65 | 3.6944 | CS2 | 0 | 19 | 0 | 0 | 6.65 | 3.6944 | CS2 | 0 | 2.1111 | 0 | 0 | 6.65 | 3.6944 | CS2 | 23.6842 | 2.1111 | 0.5 | 0.27778 | 7.15 | 3.9722 | CS2 | 2.1531 | 23.2222 | 0.5 | 0.27778 | 7.15 | 3.9722 | CS2 | 30.7895 | 23.2222 | 7.15 | 3.9722 | 7.15 | 3.9722 | CS2 | 24.8684 | 2.1111 | 0.525 | 0.29167 | 7.675 | 4.2639 | CS2 | 0 | 2.1111 |  | 0 | 7.675 | 4.2639 | CS2 | 0 | 2.1111 |  | 0 | 7.675 | 4.2639 | CS2 | 8.2895 | 6.3333 | 0.525 | 0.29167 | 7.675 | 4.2639 | CS2 | 3.468 | 29.5556 | 1.025 | 0.56944 | 7.675 | 4.2639 | CS2 | 25.968 | 29.5556 | 7.675 | 4.2639 | 7.675 | 4.2639 | CS2
|  | FWUC formation | FWUC | 27 | 25 | 0 | 10 | 0 | 0 | 9 | 19 | 0 | 0 | 0 | 10 | 1.9 | 1.7593 | 10 | 1.9 | 1.7593 | 6.6667 | 1.2667 | 1.1728 | 0 | 19 | 0 | 0 | 1.2667 | 1.1728 | CS2 | 0 | 19 | 0 | 0 | 1.2667 | 1.1728 | CS2 | 0 | 19 | 0 | 0 | 1.2667 | 1.1728 | CS2 | 0 | 57 | 0 | 0 | 1.2667 | 1.1728 | CS2 | 0 |  | 1.2667 | 1.1728 | 1.2667 | 1.1728 | CS2 | 0 | 19 | 0 | 0 | 1.2667 | 1.1728 | CS2 | 0 | 2.1111 | 0 | 0 | 1.2667 | 1.1728 | CS2 | 42.6316 | 2.1111 | 0.9 | 0.83333 | 2.1667 | 2.0062 | CS2 | 3.8756 | 23.2222 | 0.9 | 0.83333 | 2.1667 | 2.0062 | CS2 | 9.3301 | 23.2222 | 2.1667 | 2.0062 | 2.1667 | 2.0062 | CS2 | 44.7632 | 2.1111 | 0.945 | 0.875 | 3.1117 | 2.8812 | CS2 | 0 | 2.1111 |  | 0 | 3.1117 | 2.8812 | CS2 | 0 | 2.1111 |  | 0 | 3.1117 | 2.8812 | CS2 | 14.9211 | 6.3333 | 0.945 | 0.875 | 3.1117 | 2.8812 | CS2 | 6.2425 | 29.5556 | 1.845 | 1.7083 | 3.1117 | 2.8812 | CS2 | 10.5282 | 29.5556 | 3.1117 | 2.8812 | 3.1117 | 2.8812 | CS2
|  | Registration | FWUC | 27 | 12.5 | 0 | 10 | 0 | 0 | 9 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2.28 | 1.0556 | 4 | 0.76 | 0.35185 | 0 | 19 | 0 | 0 | 0.76 | 0.35185 | CS2 | 0 | 19 | 0 | 0 | 0.76 | 0.35185 | CS2 | 0 | 19 | 0 | 0 | 0.76 | 0.35185 | CS2 | 0 | 57 | 0 | 0 | 0.76 | 0.35185 | CS2 | 0 |  | 0.76 | 0.35185 | 0.76 | 0.35185 | CS2 | 0 | 1.5833 | 0 | 0 | 0.76 | 0.35185 | CS2 | 0 | 2.1111 | 0 | 0 | 0.76 | 0.35185 | CS2 | 142.1053 | 2.1111 | 3 | 1.3889 | 3.76 | 1.7407 | CS2 | 51.6746 | 5.8056 | 3 | 1.3889 | 3.76 | 1.7407 | CS2 | 64.7656 | 5.8056 | 3.76 | 1.7407 | 3.76 | 1.7407 | CS2 | 149.2105 | 2.1111 | 3.15 | 1.4583 | 6.91 | 3.1991 | CS2 | 0 | 2.1111 |  | 0 | 6.91 | 3.1991 | CS2 | 0 | 2.1111 |  | 0 | 6.91 | 3.1991 | CS2 | 49.7368 | 6.3333 | 3.15 | 1.4583 | 6.91 | 3.1991 | CS2 | 50.6636 | 12.1389 | 6.15 | 2.8472 | 6.91 | 3.1991 | CS2 | 56.9245 | 12.1389 | 6.91 | 3.1991 | 6.91 | 3.1991 | CS2
|  | subtotal |  |  | 100 | 12.14 |  |  | 10.1 |  |  |  |  | 6.4667 |  |  | 19.8519 |  |  | 30.2019 |  |  | 18.8401 |  |  |  | 2.3241 |  | 21.1642 |  |  |  |  | 0.53704 |  | 21.7012 |  |  |  |  | 4.4537 |  | 26.1549 |  |  |  |  | 7.3148 |  | 26.1549 |  |  |  |  | 26.1549 |  | 26.1549 |  |  |  |  | 0.018519 |  | 26.1735 |  |  |  |  | 0.27037 |  | 26.4438 |  |  |  |  | 5.4769 |  | 31.9207 |  |  |  |  | 5.7657 |  | 31.9207 |  |  |  |  | 31.9207 |  | 31.9207 |  |  |  |  | 5.7507 |  | 37.6714 |  |  |  |  | 0 |  | 37.6714 |  |  |  |  | 0 |  | 37.6714 |  |  |  |  | 5.7507 |  | 37.6714 |  |  |  |  | 11.5164 |  | 37.6714 |  |  |  |  | 37.6714 |  | 37.6714
2.c.2 | 500 FWUCS of FWUGS, developed capacity to operate and maintain their irrigation schemes | Preparation of training material on operation | set | 1 | 10 | 5 | 1 | 0 | 0 | 0 | 1 | 100 | 1 | 10 | 100 | 1 | 10 | 100 | 1 | 10 | 100 | 1 | 10 | 0 | 1 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 18.75 | 0.8 | 0.15 | 1.5 | 1.15 | 11.5 | CS2 | 8.3333 | 1.8 | 0.15 | 1.5 | 1.15 | 11.5 | CS2 | 0 |  | 1.15 | 11.5 | 1.15 | 11.5 | CS2 | 0 | 0 | 0 | 0 | 1.15 | 11.5 | CS2 | 0 | 0 | 0 | 0 | 1.15 | 11.5 | CS2 | 99 | 0.11111 | 0.11 | 1.1 | 1.26 | 12.6 | CS2 | 99 | 0.11111 | 0.11 | 1.1 | 1.26 | 12.6 | CS2 | 1134 | 0.11111 | 1.26 | 12.6 | 1.26 | 12.6 | CS2 | 103.95 | 0.11111 | 0.1155 | 1.155 | 1.3755 | 13.755 | CS2 | 0 | 0.11111 |  | 0 | 1.3755 | 13.755 | CS2 | 0 | 0.11111 |  | 0 | 1.3755 | 13.755 | CS2 | 34.65 | 0.33333 | 0.1155 | 1.155 | 1.3755 | 13.755 | CS2 | 50.7375 | 0.44444 | 0.2255 | 2.255 | 1.3755 | 13.755 | CS2 | 309.4875 | 0.44444 | 1.3755 | 13.755 | 1.3755 | 13.755 | CS2
|  | Preparation of training material on maintenance | set | 1 | 10 | 5 | 1 | 0.7 | 7 | 0 | 0.3 | 100 | 0.3 | 3 | 100 | 0.3 | 3 | 100 | 0.3 | 3 | 100 | 0.3 | 3 | 0 | 0.3 | 0 | 0 | 0.3 | 3 | CS2 | 0 | 0 | 0 | 0 | 0.3 | 3 | CS2 | 25 | 0.8 | 0.2 | 2 | 0.5 | 5 | CS2 | 18.1818 | 1.1 | 0.2 | 2 | 0.5 | 5 | CS2 | 0 |  | 0.5 | 5 | 0.5 | 5 | CS2 | 0 | 0 | 0 | 0 | 0.5 | 5 | CS2 | 0 | 0 | 0 | 0 | 0.5 | 5 | CS2 | 90 | 0.033333 | 0.03 | 0.3 | 0.53 | 5.3 | CS2 | 90 | 0.033333 | 0.03 | 0.3 | 0.53 | 5.3 | CS2 | 1590 | 0.033333 | 0.53 | 5.3 | 0.53 | 5.3 | CS2 | 94.5 | 0.033333 | 0.0315 | 0.315 | 0.5615 | 5.615 | CS2 | 0 | 0.033333 |  | 0 | 0.5615 | 5.615 | CS2 | 0 | 0.033333 |  | 0 | 0.5615 | 5.615 | CS2 | 31.5 | 0.1 | 0.0315 | 0.315 | 0.5615 | 5.615 | CS2 | 46.125 | 0.13333 | 0.0615 | 0.615 | 0.5615 | 5.615 | CS2 | 421.125 | 0.13333 | 0.5615 | 5.615 | 0.5615 | 5.615 | CS2
|  | Trained FWUCs of FWUGs on schemes management | Persons | 500 | 70 | 0 | 0 | 0 | 0 | 130 | 108.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.575 | 0 | 0 | 0 | 0 | CS2 | 0 | 13.575 | 0 | 0 | 0 | 0 | CS2 | 0 | 13.575 | 0 | 0 | 0 | 0 | CS2 | 0 | 40.725 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 12.0667 | 0 | 0 | 0 | 0 | CS2 | 0 | 12.0667 | 0 | 0 | 0 | 0 | CS2 | 0 | 12.0667 | 0 | 0 | 0 | 0 | CS2 | 0 | 36.2 | 0 | 0 | 0 | 0 | CS2 | 0 | 36.2 | 0 | 0 | 0 | 0 | CS2 | 0 | 12.0667 | 0 | 0 | 0 | 0 | CS2 | 0 | 12.0667 |  | 0 | 0 | 0 | CS2 | 0 | 12.0667 |  | 0 | 0 | 0 | CS2 | 0 | 36.2 | 0 | 0 | 0 | 0 | CS2 | 0 | 72.4 | 0 | 0 | 0 | 0 | CS2 | 0 | 72.4 | 0 | 0 | 0 | 0 | CS2
|  | Application of MEF budget (FWUC) | FWUC | 27 | 10 | 0 | 0 | 4.05 | 1.5 | 19 | 14.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8687 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.8687 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.8687 | 0 | 0 | 0 | 0 | CS2 | 0 | 5.6063 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.6611 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.6611 | 0 | 0 | 0 | 0 | CS2 | 0 | 3.3222 | 0 | 0 | 0 | 0 | CS2 | 0 | 3.3222 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.6611 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.6611 |  | 0 | 0 | 0 | CS2 | 0 | 1.6611 |  | 0 | 0 | 0 | CS2 | 0 | 4.9833 | 0 | 0 | 0 | 0 | CS2 | 0 | 8.3056 | 0 | 0 | 0 | 0 | CS2 | 0 | 8.3056 | 0 | 0 | 0 | 0 | CS2
|  | subtotal |  |  | 100 | 10 |  |  | 8.5 |  |  |  |  | 13 |  |  | 13 |  |  | 13 |  |  | 13 |  |  |  | 0 |  | 13 |  |  |  |  | 0 |  | 13 |  |  |  |  | 3.5 |  | 16.5 |  |  |  |  | 3.5 |  | 16.5 |  |  |  |  | 16.5 |  | 16.5 |  |  |  |  | 0 |  | 16.5 |  |  |  |  | 0 |  | 16.5 |  |  |  |  | 1.4 |  | 17.9 |  |  |  |  | 1.4 |  | 17.9 |  |  |  |  | 17.9 |  | 17.9 |  |  |  |  | 1.47 |  | 19.37 |  |  |  |  | 0 |  | 19.37 |  |  |  |  | 0 |  | 19.37 |  |  |  |  | 1.47 |  | 19.37 |  |  |  |  | 2.87 |  | 19.37 |  |  |  |  | 19.37 |  | 19.37
2.d.1 | 4 Agricultural development centers made fully operational to provide agribusiness services | Identification and Initial Survey | No | 4 | 10 | 7.5 | 3 | 4 | 10 | 0 | 0 | 2.5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 4.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2
|  | DED & Tender file | No | 1 | 35 | 12.5 | 1 | 0.28571 | 10 | 0 | 0.71429 | 5 | 0.035714 | 1.25 | 7.5 | 0.053571 | 1.875 | 7.5 | 0.053571 | 1.875 | 6.6667 | 0.047619 | 1.6667 | 1848 | 0.059524 | 1.1 | 38.5 | 1.1476 | 40.1667 | CS2 | 0 | 0.059524 | 0 | 0 | 1.1476 | 40.1667 | CS2 | 0 | 0.059524 | 0 | 0 | 1.1476 | 40.1667 | CS2 | 616 | 0.17857 | 1.1 | 38.5 | 1.1476 | 40.1667 | CS2 | 0 |  | 1.1476 | 40.1667 | 1.1476 | 40.1667 | CS2 | 0 | 0 | 0 | 0 | 1.1476 | 40.1667 | CS2 | 0 | 0 | 0 | 0 | 1.1476 | 40.1667 | CS2 | 100.8 | 0.079365 | 0.08 | 2.8 | 1.2276 | 42.9667 | CS2 | 100.8 | 0.079365 | 0.08 | 2.8 | 1.2276 | 42.9667 | CS2 | 1546.8 | 0.079365 | 1.2276 | 42.9667 | 1.2276 | 42.9667 | CS2 | 105.84 | 0.079365 | 0.084 | 2.94 | 1.3116 | 45.9067 | CS2 | 0 | 0.079365 |  | 0 | 1.3116 | 45.9067 | CS2 | 0 | 0.079365 |  | 0 | 1.3116 | 45.9067 | CS2 | 35.28 | 0.2381 | 0.084 | 2.94 | 1.3116 | 45.9067 | CS2 | 51.66 | 0.31746 | 0.164 | 5.74 | 1.3116 | 45.9067 | CS2 | 413.16 | 0.31746 | 1.3116 | 45.9067 | 1.3116 | 45.9067 | CS2
|  | Procurement | No | 1 | 10 | 6.33 | 1 | 0.63 | 6.3 | 0 | 0.37 | 10 | 0.037 | 0.37 | 7.5 | 0.02775 | 0.2775 | 7.5 | 0.02775 | 0.2775 | 8.3333 | 0.030833 | 0.30833 | 356.7568 | 0.030833 | 0.11 | 1.1 | 0.14083 | 1.4083 | CS2 | 0 | 0.030833 | 0 | 0 | 0.14083 | 1.4083 | CS2 | 0 | 0.030833 | 0 | 0 | 0.14083 | 1.4083 | CS2 | 118.9189 | 0.0925 | 0.11 | 1.1 | 0.14083 | 1.4083 | CS2 | 0 |  | 0.14083 | 1.4083 | 0.14083 | 1.4083 | CS2 | 0 | 0 | 0 | 0 | 0.14083 | 1.4083 | CS2 | 0 | 0 | 0 | 0 | 0.14083 | 1.4083 | CS2 | 97.2973 | 0.041111 | 0.04 | 0.4 | 0.18083 | 1.8083 | CS2 | 97.2973 | 0.041111 | 0.04 | 0.4 | 0.18083 | 1.8083 | CS2 | 439.8649 | 0.041111 | 0.18083 | 1.8083 | 0.18083 | 1.8083 | CS2 | 102.1622 | 0.041111 | 0.042 | 0.42 | 0.22283 | 2.2283 | CS2 | 0 | 0.041111 |  | 0 | 0.22283 | 2.2283 | CS2 | 0 | 0.041111 |  | 0 | 0.22283 | 2.2283 | CS2 | 34.0541 | 0.12333 | 0.042 | 0.42 | 0.22283 | 2.2283 | CS2 | 49.8649 | 0.16444 | 0.082 | 0.82 | 0.22283 | 2.2283 | CS2 | 135.5068 | 0.16444 | 0.22283 | 2.2283 | 0.22283 | 2.2283 | CS2
|  | Construction | No | 3 | 40 | 0 | 3 | 0 | 0 | 3 | 6 | 2.5 | 0.15 | 2 | 5 | 0.3 | 4 | 6 | 0.36 | 4.8 | 4.5 | 0.27 | 3.6 | 0 | 0.5 | 0 | 0 | 0.27 | 3.6 | CS2 | 0 | 0.5 | 0 | 0 | 0.27 | 3.6 | CS2 | 0 | 0.5 | 0 | 0 | 0.27 | 3.6 | CS2 | 0 | 1.5 | 0 | 0 | 0.27 | 3.6 | CS2 | 0 |  | 0.27 | 3.6 | 0.27 | 3.6 | CS2 | 0 | 0.25 | 0 | 0 | 0.27 | 3.6 | CS2 | 0 | 0.66667 | 0 | 0 | 0.27 | 3.6 | CS2 | 30 | 0.66667 | 0.2 | 2.6667 | 0.47 | 6.2667 | CS2 | 12.6316 | 1.5833 | 0.2 | 2.6667 | 0.47 | 6.2667 | CS2 | 29.6842 | 1.5833 | 0.47 | 6.2667 | 0.47 | 6.2667 | CS2 | 31.5 | 0.66667 | 0.21 | 2.8 | 0.68 | 9.0667 | CS2 | 0 | 0.66667 |  | 0 | 0.68 | 9.0667 | CS2 | 0 | 0.66667 |  | 0 | 0.68 | 9.0667 | CS2 | 10.5 | 2 | 0.21 | 2.8 | 0.68 | 9.0667 | CS2 | 11.4419 | 3.5833 | 0.41 | 5.4667 | 0.68 | 9.0667 | CS2 | 18.9767 | 3.5833 | 0.68 | 9.0667 | 0.68 | 9.0667 | CS2
|  | Training of users (50% are women) | No | 4 | 5 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 4 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2
|  | subtotal |  |  | 100 | 26.33 |  |  | 26.3 |  |  |  |  | 3.62 |  |  | 6.1525 |  |  | 6.9525 |  |  | 5.575 |  |  |  | 39.6 |  | 45.175 |  |  |  |  | 0 |  | 45.175 |  |  |  |  | 0 |  | 45.175 |  |  |  |  | 39.6 |  | 45.175 |  |  |  |  | 45.175 |  | 45.175 |  |  |  |  | 0 |  | 45.175 |  |  |  |  | 0 |  | 45.175 |  |  |  |  | 5.8667 |  | 51.0417 |  |  |  |  | 5.8667 |  | 51.0417 |  |  |  |  | 51.0417 |  | 51.0417 |  |  |  |  | 6.16 |  | 57.2017 |  |  |  |  | 0 |  | 57.2017 |  |  |  |  | 0 |  | 57.2017 |  |  |  |  | 6.16 |  | 57.2017 |  |  |  |  | 12.0267 |  | 57.2017 |  |  |  |  | 57.2017 |  | 57.2017
2.d.2 | 4 Engineering workshops made fully operational to provide agribusiness services | Identification and Initial Survey | No | 4 | 10 | 7.5 | 1 | 4 | 10 | 1 | 1 | 10 | 0.1 | 0.25 | 7.5 | 0.075 | 0.1875 | 10 | 0.1 | 0.25 | 9.1667 | 0.091667 | 0.22917 | 0 | 0 | 1 | 2.5 | 1.0917 | 2.7292 | CS2 | 0 | 0 | 0 | 0 | 1.0917 | 2.7292 | CS2 | 0 | 0 | 0 | 0 | 1.0917 | 2.7292 | CS2 | 0 | 0 | 1 | 2.5 | 1.0917 | 2.7292 | CS2 | 0 |  | 1.0917 | 2.7292 | 1.0917 | 2.7292 | CS2 | 0 | 0 | 0 | 0 | 1.0917 | 2.7292 | CS2 | 0 | 0 | 0 | 0 | 1.0917 | 2.7292 | CS2 | 99 | 0.11111 | 0.11 | 0.275 | 1.2017 | 3.0042 | CS2 | 99 | 0.11111 | 0.11 | 0.275 | 1.2017 | 3.0042 | CS2 | 1081.5 | 0.11111 | 1.2017 | 3.0042 | 1.2017 | 3.0042 | CS2 | 103.95 | 0.11111 | 0.1155 | 0.28875 | 1.3172 | 3.2929 | CS2 | 0 | 0.11111 |  | 0 | 1.3172 | 3.2929 | CS2 | 0 | 0.11111 |  | 0 | 1.3172 | 3.2929 | CS2 | 34.65 | 0.33333 | 0.1155 | 0.28875 | 1.3172 | 3.2929 | CS2 | 50.7375 | 0.44444 | 0.2255 | 0.56375 | 1.3172 | 3.2929 | CS2 | 296.3625 | 0.44444 | 1.3172 | 3.2929 | 1.3172 | 3.2929 | CS2
|  | DED & Tender file | No | 1 | 35 | 18.75 | 1 | 0.33429 | 11.7 | 1 | 1.6657 | 2.5 | 0.041643 | 1.4575 | 5 | 0.083286 | 2.915 | 5 | 0.083286 | 2.915 | 4.1667 | 0.069405 | 2.4292 | 100 | 1 | 1 | 35 | 1.0694 | 37.4292 | CS2 | 0 | 0 | 0 | 0 | 1.0694 | 37.4292 | CS2 | 0 | 0 | 0 | 0 | 1.0694 | 37.4292 | CS2 | 100 | 1 | 1 | 35 | 1.0694 | 37.4292 | CS2 | 0 |  | 1.0694 | 37.4292 | 1.0694 | 37.4292 | CS2 | 0 | 0 | 0 | 0 | 1.0694 | 37.4292 | CS2 | 0 | 0 | 0 | 0 | 1.0694 | 37.4292 | CS2 | 102.6587 | 0.18508 | 0.19 | 6.65 | 1.2594 | 44.0792 | CS2 | 102.6587 | 0.18508 | 0.19 | 6.65 | 1.2594 | 44.0792 | CS2 | 680.4674 | 0.18508 | 1.2594 | 44.0792 | 1.2594 | 44.0792 | CS2 | 107.7916 | 0.18508 | 0.1995 | 6.9825 | 1.4589 | 51.0617 | CS2 | 0 | 0.18508 |  | 0 | 1.4589 | 51.0617 | CS2 | 0 | 0.18508 |  | 0 | 1.4589 | 51.0617 | CS2 | 35.9305 | 0.55524 | 0.1995 | 6.9825 | 1.4589 | 51.0617 | CS2 | 52.6126 | 0.74032 | 0.3895 | 13.6325 | 1.4589 | 51.0617 | CS2 | 197.0648 | 0.74032 | 1.4589 | 51.0617 | 1.4589 | 51.0617 | CS2
|  | Procurement | No | 1 | 10 | 4 | 1 | 0.85 | 8.5 | 1 | 0 | 10 | 0 | 0 | 7.5 | 0 | 0 | 10 | 0 | 0 | 9.1667 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 1 | 10 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 100 | 1 | 1 | 10 | 1 | 10 | CS2 | 0 |  | 1 | 10 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 1 | 10 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 |  | 0 | 1 | 10 | CS2 | 0 | 0 |  | 0 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 0 | 0 | 1 | 10 | CS2 | 0 | 0 | 1 | 10 | 1 | 10 | CS2
|  | Construction | No | 3 | 40 | 0 | 0 | 0 | 0 | 3 | 3 | 2.5 | 0.075 | 1 | 5 | 0.15 | 2 | 5 | 0.15 | 2 | 4.1667 | 0.125 | 1.6667 | 0 | 0.25 | 0 | 0 | 0.125 | 1.6667 | CS2 | 0 | 0.25 | 0 | 0 | 0.125 | 1.6667 | CS2 | 0 | 0.25 | 0 | 0 | 0.125 | 1.6667 | CS2 | 0 | 0.75 | 0 | 0 | 0.125 | 1.6667 | CS2 | 0 |  | 0.125 | 1.6667 | 0.125 | 1.6667 | CS2 | 0 | 0.25 | 0 | 0 | 0.125 | 1.6667 | CS2 | 0 | 0.33333 | 0 | 0 | 0.125 | 1.6667 | CS2 | 60 | 0.33333 | 0.2 | 2.6667 | 0.325 | 4.3333 | CS2 | 21.8182 | 0.91667 | 0.2 | 2.6667 | 0.325 | 4.3333 | CS2 | 35.4545 | 0.91667 | 0.325 | 4.3333 | 0.325 | 4.3333 | CS2 | 63 | 0.33333 | 0.21 | 2.8 | 0.535 | 7.1333 | CS2 | 0 | 0.33333 |  | 0 | 0.535 | 7.1333 | CS2 | 0 | 0.33333 |  | 0 | 0.535 | 7.1333 | CS2 | 21 | 1 | 0.21 | 2.8 | 0.535 | 7.1333 | CS2 | 21.3913 | 1.9167 | 0.41 | 5.4667 | 0.535 | 7.1333 | CS2 | 27.913 | 1.9167 | 0.535 | 7.1333 | 0.535 | 7.1333 | CS2
|  | Training of users (50% are women) | No | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 7.5 | 0 | 0 | 7.5 | 0 | 0 | 6.6667 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2
|  | subtotal |  |  | 100 | 30.25 |  |  | 30.2 |  |  |  |  | 2.7075 |  |  | 5.1025 |  |  | 5.165 |  |  | 4.325 |  |  |  | 37.5 |  | 41.825 |  |  |  |  | 10 |  | 51.825 |  |  |  |  | 0 |  | 51.825 |  |  |  |  | 47.5 |  | 51.825 |  |  |  |  | 51.825 |  | 51.825 |  |  |  |  | 0 |  | 51.825 |  |  |  |  | 0 |  | 51.825 |  |  |  |  | 9.5917 |  | 61.4167 |  |  |  |  | 9.5917 |  | 61.4167 |  |  |  |  | 61.4167 |  | 61.4167 |  |  |  |  | 10.0712 |  | 71.4879 |  |  |  |  | 0 |  | 71.4879 |  |  |  |  | 0 |  | 71.4879 |  |  |  |  | 10.0712 |  | 71.4879 |  |  |  |  | 19.6629 |  | 71.4879 |  |  |  |  | 71.4879 |  | 71.4879
|  | Total for all Outputs | [6 empty] | 99.48 |  |  |  |  | 28.0867 |  |  | 47.3794 |  |  | 58.9269 |  |  | 44.7976 |  |  |  | 87.2528 |  | 132.0504 |  |  |  |  | 17.397 |  | 149.4475 |  |  |  |  | 12.5336 |  | 161.9811 |  |  |  |  | 117.1834 |  | 161.9811 |  |  |  |  | 161.9811 |  | 161.9811 |  |  |  |  | 0.19874 |  | 162.1798 |  |  |  |  | 2.2989 |  | 164.4787 |  |  |  |  | 41.7721 |  | 206.2509 |  |  |  |  | 44.2698 |  | 206.2509 |  |  |  |  | 206.2509 |  | 206.2509 |  |  |  |  | 43.8607 |  | 250.1116 |  |  |  |  | 0 |  | 250.1116 |  |  |  |  | 0 |  | 250.1116 |  |  |  |  | 43.8607 |  | 250.1116 |  |  |  |  | 88.1305 |  | 250.1116 |  |  |  |  | 250.1116 |  | 250.1116
|  | Original as of July 2021 (Dead formulation) | [6 empty] | 99.48 |  |  |  |  | 25.895 |  |  | 43.7044 |  |  | 54.9852 |  |  | 41.5282 |  |  |  | 37.5195 |  | 79.0477 |  |  |  |  | 10.7304 |  | 89.778 |  |  |  |  | 8.9037 |  | 98.6817 |  |  |  |  | 57.1536 |  | 98.6817 |  |  |  |  | 98.6817 |  | 98.6817 |  |  |  |  | 0 |  | 98.6817 |  |  |  |  | 0 |  | 98.6817 |  |  |  |  | 0 |  | 98.6817 |  |  |  |  | 0 |  | 98.6817 |  |  |  |  | 98.6817 |  | 98.6817 |  |  |  |  | 0 |  | 98.6817 |  |  |  |  | 0 |  | 98.6817 |  |  |  |  | 0
|  | Deviation | [6 empty] | 0 |  |  |  |  | 2.1917 |  |  | 3.675 |  |  | 3.9417 | [6 empty] | 49.7333 | [6 empty] | 6.6667 | [6 empty] | 3.6299 | [20 empty] | 0.19874 | [6 empty] | 2.2989 | [6 empty] | 41.7721 | [20 empty] | 43.8607 | [6 empty] | 0 | [6 empty] | 0
Note on E17: User: Previous is event
Note on E44: User: Previous No.
Note on F17: User: Previous 6,000
Note on F25: User: Previous 10,000
Note on F26: User: Previous 10,000
Note on F27: User: Previous 10,000
Note on F28: User: Previous 10,000
Note on F29: User: Previous 10,000
Note on F33: Administrator: Actual is 146 villages (estimated). Actually, we have done 17 FWUCs is (323 members)= 93 villages and finished the budget. How to do more further (we are shortage of 9 FWUCs budget)?
Note on F47: User: Previous 3
Note on F48: User: Previous 3
Note on F53: User: Previous 3
Note on F54: User: Previous 3
Note on J25: User: Previous 1,500
Note on J26: User: Previous 2,500
Note on J27: User: Previous 2,000
Note on J28: User: Previous 250
Note on J29: User: Previous 250
Note on N25: User: Previous 3,000
Note on N26: User: Previous 3,000
Note on N27: User: Previous 3,000
Note on N28: User: Previous 3,000
Note on N29: User: Previous 3,000
Note on N47: User: Previous 1
Note on N48: User: Previous 1
Note on N55: User: Previous 4
in JV with SBK Research and Development
Implemented by

## Output 3
CFAVC OVERAL PROJECT IMPLEMENTATION PROGRESS
OUTPUT 3
Status : January though Deember 2021
ACTIVITY |  |  | SUBACTIVITY | UNIT | OVERALL TARGET | Sub- Weight (%) | AWP 2020 |  |  | 2021 |  | Progress Jan 2021 |  |  | Progress Feb 2021 |  |  | Progress Mar 2021 |  |  | Progress Q1 2021 |  |  | Progress Apr. 2021 | [6 empty] | Progress May 2021 | [6 empty] | Progress Jun. 2021 | [6 empty] | Progress Q2. 2021 | [6 empty] | Progress First Six-monthly 2021 | [6 empty] | Progress Jul. 2021 | [6 empty] | Progress Aug. 2021 | [6 empty] | Progress Sept. 2021 | [6 empty] | Progress Q3. 2021 | [6 empty] | Progress First Nine-monthly 2021 | [6 empty] | Progress Oct. 2021 | [6 empty] | Progress Nov. 2021 | [6 empty] | Progress Dec. 2021 | [6 empty] | Progress Q4. 2021 | [6 empty] | Progress Second Six-monthly 2021 | [6 empty] | Progress Annually 2021
[7 empty] | Plan | Realisation |  | AWP | AWP & Carry Over from 2020 | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Actual progress | Weighted Progress (%) | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff | Current Progress % | Target | Actual progress | Weighted Progress (%) | Cumulative Progress | CumulativeWeighted Progress | Responsible staff
[8 empty] | Nr | Physical %
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 12 | 13 | 14 | 12 | 13 | 14 | 12 | 13 | 14 | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14 |  | 12 |  | 13 | 14 |  | 14
3.a | 3.a | Good Agriculture Practice for tropical fruit endorsed | Policy on Climate Smart and Gender Responsive Agribusiness and PPP framework formulated including the 5 policies below, 1. Draft of Climate Smart and Gender Responsive Agrib-policy | Policy | 1 | 25 | 1 | 0.028 | 2.8 | 1 | 1.97 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.197 | 4.925 | 10 | 0.197 | 4.925 | 60.9137 | 0.16417 | 0.1 | 2.5 | 0.297 | 7.425 | CS2 | 60.9137 | 0.16417 | 0.1 | 2.5 | 7.525 | 188.125 | CS2 | 91.3706 | 0.16417 | 0.15 | 3.75 | 7.675 | 191.875 | CS2 | 71.066 | 0.4925 | 0.35 | 8.75 | 7.675 | 191.875 | CS2 | 99.4545 | 0.55 | 0.547 | 13.675 | 7.675 | 191.875 | CS2 | 6.0914 | 0.16417 | 0.01 | 0.25 | 7.685 | 192.125 | CS2 | 60.9137 | 0.16417 | 0.1 | 2.5 | 7.785 | 194.625 | CS2 | 100.5076 | 0.21889 | 0.22 | 5.5 | 8.005 | 200.125 | CS2 | 60.3046 | 0.54722 | 0.33 | 8.25 | 8.005 | 200.125 | CS2 | 0 |  | 0.877 | 21.925 | 8.005 | 200.125 | CS2 | 105.533 | 0.21889 | 0.231 | 5.775 | 8.236 | 205.9 | CS2 | 0 | 0.21889 |  | 0 | 8.236 | 205.9 | CS2 | 0 | 0.21889 |  | 0 | 8.236 | 205.9 | CS2 | 35.1777 | 0.65667 | 0.231 | 5.775 | 8.236 | 205.9 | CS2 | 46.599 | 1.2039 | 0.561 | 14.025 | 8.236 | 205.9 | CS2 | 63.1739 | 1.7539 | 1.108 | 27.7 | 8.236 | 205.9 | CS2
|  |  | 2. Draft CSA policy | Policy | 1 | 25 | 0.5 | 0.053 | 5.3 | 0.5 | 0.947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.7159 | 0.078917 | 0.1 | 2.5 | 0.1 | 2.5 | CS2 | 126.7159 | 0.078917 | 0.1 | 2.5 | 2.6 | 65 | CS2 | 63.358 | 0.078917 | 0.05 | 1.25 | 2.65 | 66.25 | CS2 | 105.5966 | 0.23675 | 0.25 | 6.25 | 2.65 | 66.25 | CS2 | 0 |  | 0.25 | 6.25 | 2.65 | 66.25 | CS2 | 0 | 0.08 | 0 | 0 | 2.65 | 66.25 | CS2 | 76.0296 | 0.078917 | 0.06 | 1.5 | 2.71 | 67.75 | CS2 | 104.5407 | 0.10522 | 0.11 | 2.75 | 2.82 | 70.5 | CS2 | 64.3601 | 0.26414 | 0.17 | 4.25 | 2.82 | 70.5 | CS2 | 0 |  | 0.42 | 10.5 | 2.82 | 70.5 | CS2 | 109.7677 | 0.10522 | 0.1155 | 2.8875 | 2.9355 | 73.3875 | CS2 | 0 | 0.10522 |  | 0 | 2.9355 | 73.3875 | CS2 | 0 | 0.10522 |  | 0 | 2.9355 | 73.3875 | CS2 | 36.5892 | 0.31567 | 0.1155 | 2.8875 | 2.9355 | 73.3875 | CS2 | 49.2406 | 0.57981 | 0.2855 | 7.1375 | 2.9355 | 73.3875 | CS2 | 92.3585 | 0.57981 | 0.5355 | 13.3875 | 2.9355 | 73.3875 | CS2
|  |  | 3. Draft guidance manual for climate neutrality and adaption for agribusiness operation; and 4. Draft IDP strategy for climate friendly agribusiness | Prakas | 1 | 25 | 0.5 | 0.069 | 6.9 | 0.5 | 0.931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128.8937 | 0.077583 | 0.1 | 2.5 | 0.1 | 2.5 | CS2 | 128.8937 | 0.077583 | 0.1 | 2.5 | 2.6 | 65 | CS2 | 64.4468 | 0.077583 | 0.05 | 1.25 | 2.65 | 66.25 | CS2 | 107.4114 | 0.23275 | 0.25 | 6.25 | 2.65 | 66.25 | CS2 | 0 |  | 0.25 | 6.25 | 2.65 | 66.25 | CS2 | 0 | 0.08 | 0 | 0 | 2.65 | 66.25 | CS2 | 77.3362 | 0.077583 | 0.06 | 1.5 | 2.71 | 67.75 | CS2 | 96.6702 | 0.10344 | 0.1 | 2.5 | 2.81 | 70.25 | CS2 | 61.2962 | 0.26103 | 0.16 | 4 | 2.81 | 70.25 | CS2 | 0 |  | 0.41 | 10.25 | 2.81 | 70.25 | CS2 | 101.5038 | 0.10344 | 0.105 | 2.625 | 2.915 | 72.875 | CS2 | 0 | 0.10344 |  | 0 | 2.915 | 72.875 | CS2 | 0 | 0.10344 |  | 0 | 2.915 | 72.875 | CS2 | 33.8346 | 0.31033 | 0.105 | 2.625 | 2.915 | 72.875 | CS2 | 46.3805 | 0.57136 | 0.265 | 6.625 | 2.915 | 72.875 | CS2 | 90.1356 | 0.57136 | 0.515 | 12.875 | 2.915 | 72.875 | CS2
|  |  | 5. Draft PPP framework formulated | Framework | 1 | 25 | 0.5 | 0.04 | 4 | 0.5 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0.096 | 2.4 | 10 | 0.096 | 2.4 | 250 | 0.08 | 0.2 | 5 | 0.296 | 7.4 | CS2 | 125 | 0.08 | 0.1 | 2.5 | 7.5 | 187.5 | CS2 | 62.5 | 0.08 | 0.05 | 1.25 | 7.55 | 188.75 | CS2 | 145.8333 | 0.24 | 0.35 | 8.75 | 7.55 | 188.75 | CS2 | 0 |  | 0.446 | 11.15 | 7.55 | 188.75 | CS2 | 0 | 0.08 | 0 | 0 | 7.55 | 188.75 | CS2 | 75 | 0.08 | 0.06 | 1.5 | 7.61 | 190.25 | CS2 | 103.125 | 0.10667 | 0.11 | 2.75 | 7.72 | 193 | CS2 | 63.75 | 0.26667 | 0.17 | 4.25 | 7.72 | 193 | CS2 | 0 |  | 0.616 | 15.4 | 7.72 | 193 | CS2 | 108.2812 | 0.10667 | 0.1155 | 2.8875 | 7.8355 | 195.8875 | CS2 | 0 | 0.10667 |  | 0 | 7.8355 | 195.8875 | CS2 | 0 | 0.10667 |  | 0 | 7.8355 | 195.8875 | CS2 | 36.0938 | 0.32 | 0.1155 | 2.8875 | 7.8355 | 195.8875 | CS2 | 48.6648 | 0.58667 | 0.2855 | 7.1375 | 7.8355 | 195.8875 | CS2 | 124.6875 | 0.58667 | 0.7315 | 18.2875 | 7.8355 | 195.8875 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 19 |  |  |  |  | 0 |  |  | 0 |  |  | 7.325 |  |  | 7.325 |  |  |  | 12.5 |  | 19.825 |  |  |  |  | 10 |  | 505.625 |  |  |  |  | 7.5 |  | 513.125 |  |  |  |  | 30 |  | 513.125 |  |  |  |  | 37.325 |  | 513.125 |  |  |  |  | 0.25 |  | 513.375 |  |  |  |  | 7 |  | 520.375 |  |  |  |  | 13.5 |  | 533.875 |  |  |  |  | 20.75 |  | 533.875 |  |  |  |  | 58.075 |  | 533.875 |  |  |  |  | 14.175 |  | 548.05 |  |  |  |  | 0 |  | 548.05 |  |  |  |  | 0 |  | 548.05 |  |  |  |  | 14.175 |  | 548.05 |  |  |  |  | 34.925 |  | 548.05 |  |  |  |  | 72.25 |  | 548.05
3.b | 3.b | Good Agriculture Practice for organic fertilizer endorsed | Guidance manual for climate neutrality and adaptation standards for agribusiness operation | Strategy | 1 | 20 | 0.5 | 0.04 | 4 | 1 | 1.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.589 | 0.1825 | 0.2 | 4 | 0.2 | 4 | CS2 | 0 | 0.1825 | 0 | 0 | 4 | 80 | CS2 | 54.7945 | 0.1825 | 0.1 | 2 | 4.1 | 82 | CS2 | 54.7945 | 0.5475 | 0.3 | 6 | 4.1 | 82 | CS2 | 0 |  | 0.3 | 6 | 4.1 | 82 | CS2 | 0 | 0.18 | 0 | 0 | 4.1 | 82 | CS2 | 57.5342 | 0.12167 | 0.07 | 1.4 | 4.17 | 83.4 | CS2 | 98.6301 | 0.16222 | 0.16 | 3.2 | 4.33 | 86.6 | CS2 | 49.5808 | 0.46389 | 0.23 | 4.6 | 4.33 | 86.6 | CS2 | 0 |  | 0.53 | 10.6 | 4.33 | 86.6 | CS2 | 103.5616 | 0.16222 | 0.168 | 3.36 | 4.498 | 89.96 | CS2 | 0 | 0.16222 |  | 0 | 4.498 | 89.96 | CS2 | 0 | 0.16222 |  | 0 | 4.498 | 89.96 | CS2 | 34.5205 | 0.48667 | 0.168 | 3.36 | 4.498 | 89.96 | CS2 | 41.8703 | 0.95056 | 0.398 | 7.96 | 4.498 | 89.96 | CS2 | 73.4307 | 0.95056 | 0.698 | 13.96 | 4.498 | 89.96 | CS2
|  |  | Climate-friendly become more widely utilized with eight of largest Cambodia millers/exporters being part of alliance | Rice miller | 8 | 15 | 0.5 | 0.4 | 5 | 2 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.175 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.175 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.175 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.525 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0.175 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.175 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.23333 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.58333 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0.23333 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.23333 |  | 0 | 0 | 0 | CS2 | 0 | 0.23333 |  | 0 | 0 | 0 | CS2 | 0 | 0.7 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.2833 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.2833 | 0 | 0 | 0 | 0 | CS2
|  |  | Standards on CamGAP tropical fruit formation | Standard | 1 | 20 | 0.5 | 0.045 | 4.5 | 0.5 | 0.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079583 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.079583 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.079583 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.23875 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.10611 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.10611 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0.10611 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.10611 |  | 0 | 0 | 0 | CS2 | 0 | 0.10611 |  | 0 | 0 | 0 | CS2 | 0 | 0.31833 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.42444 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.42444 | 0 | 0 | 0 | 0 | CS2
|  |  | Development of standards for organic fertilizer | Standard | 1 | 15 | 0.5 | 0.01 | 1 | 0.5 | 0.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0825 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.0825 | 0 | 0 | 0 | 0 | CS2 | 121.2121 | 0.0825 | 0.1 | 1.5 | 0.1 | 1.5 | CS2 | 40.404 | 0.2475 | 0.1 | 1.5 | 0.1 | 1.5 | CS2 | 0 |  | 0.1 | 1.5 | 0.1 | 1.5 | CS2 | 0 | 0.0825 | 0 | 0 | 0.1 | 1.5 | CS2 | 72.7273 | 0.0825 | 0.06 | 0.9 | 0.16 | 2.4 | CS2 | 100 | 0.11 | 0.11 | 1.65 | 0.27 | 4.05 | CS2 | 61.8182 | 0.275 | 0.17 | 2.55 | 0.27 | 4.05 | CS2 | 0 |  | 0.27 | 4.05 | 0.27 | 4.05 | CS2 | 105 | 0.11 | 0.1155 | 1.7325 | 0.3855 | 5.7825 | CS2 | 0 | 0.11 |  | 0 | 0.3855 | 5.7825 | CS2 | 0 | 0.11 |  | 0 | 0.3855 | 5.7825 | CS2 | 35 | 0.33 | 0.1155 | 1.7325 | 0.3855 | 5.7825 | CS2 | 47.1901 | 0.605 | 0.2855 | 4.2825 | 0.3855 | 5.7825 | CS2 | 63.719 | 0.605 | 0.3855 | 5.7825 | 0.3855 | 5.7825 | CS2
|  |  | Development of IDP strategies for climate friendly agribusiness | Strategy | 1 | 5 | 0 | 0 |  | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0.025 | [5 empty] | 0 | 0.025 | [5 empty] | 0 | 0.025 | 0 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | 0.025 | 0 |  |  |  |  | 0 | 0.025 | 0 |  |  |  |  | 0 | 0.033333 | 0 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | 0.033333 | 0 |  |  |  |  | 0 | 0.033333 | [5 empty] | 0 | 0.033333 | [5 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  |  | National standards on biodigester development | Standard | 1 | 5 | 0 | 0 |  | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0.025 | [5 empty] | 0 | 0.025 | [5 empty] | 80 | 0.025 | 0.02 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 40 | 0.025 | 0.01 |  |  |  |  | 0 | 0.025 | 0 |  |  |  |  | 0 | 0.033333 | 0 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | 0.033333 | 0 |  |  |  |  | 0 | 0.033333 | [5 empty] | 0 | 0.033333 | [5 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  |  | Socialize GAP Standards for tropical fruit | No | 2 | 20 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0.041667 | 0.2 | 2 | 0.2 | 2 | CS2 | 0 | 0.041667 | 0 | 0 | 2 | 20 | CS2 | 0 | 0.041667 | 0 | 0 | 2 | 20 | CS2 | 160 | 0.125 | 0.2 | 2 | 2 | 20 | CS2 | 0 |  | 0.2 | 2 | 2 | 20 | CS2 | 0 | 0 | 0 | 0 | 2 | 20 | CS2 | 0 | 0.041667 | 0 | 0 | 2 | 20 | CS2 | 0 | 0.055556 | 0 | 0 | 2 | 20 | CS2 | 0 | 0.097222 | 0 | 0 | 2 | 20 | CS2 | 0 |  | 0.2 | 2 | 2 | 20 | CS2 | 0 | 0.055556 | 0 | 0 | 2 | 20 | CS2 | 0 | 0.055556 |  | 0 | 2 | 20 | CS2 | 0 | 0.055556 |  | 0 | 2 | 20 | CS2 | 0 | 0.16667 | 0 | 0 | 2 | 20 | CS2 | 0 | 0.26389 | 0 | 0 | 2 | 20 | CS2 | 75.7895 | 0.26389 | 0.2 | 2 | 2 | 20 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 14.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  |  | 6 |  | 6 |  |  |  |  | 0 |  | 100 |  |  |  |  | 3.5 |  | 103.5 |  |  |  |  | 9.5 |  | 103.5 |  |  |  |  | 9.5 |  | 103.5 |  |  |  |  | 0 |  | 103.5 |  |  |  |  | 2.3 |  | 105.8 |  |  |  |  | 4.85 |  | 110.65 |  |  |  |  | 7.15 |  | 110.65 |  |  |  |  | 16.65 |  | 110.65 |  |  |  |  | 5.0925 |  | 115.7425 |  |  |  |  | 0 |  | 115.7425 |  |  |  |  | 0 |  | 115.7425 |  |  |  |  | 5.0925 |  | 115.7425 |  |  |  |  | 12.2425 |  | 115.7425 |  |  |  |  | 21.7425 |  | 115.7425
3.c | 3.c | 50 Staff from financial institutions trained in CSA and green finance | Assessment TNA on CSA and Green finance | No | 1 | 20 | 0.5 | 0.03 | 3 | 1 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.5 | 0 | 0 | 0 | 0 | CS2 | 33.3333 | 1.5 | 0.5 | 10 | 0.5 | 10 | CS2 | 11.1111 | 4.5 | 0.5 | 10 | 0.5 | 10 | CS2 | 0 |  | 0.5 | 10 | 0.5 | 10 | CS2 | 6.25 | 0.16 | 0.01 | 0.2 | 0.51 | 10.2 | CS2 | 30.6122 | 0.16333 | 0.05 | 1 | 0.56 | 11.2 | CS2 | 97.9592 | 0.16333 | 0.16 | 3.2 | 0.72 | 14.4 | CS2 | 45.2055 | 0.48667 | 0.22 | 4.4 | 0.72 | 14.4 | CS2 | 0 |  | 0.72 | 14.4 | 0.72 | 14.4 | CS2 | 102.8571 | 0.16333 | 0.168 | 3.36 | 0.888 | 17.76 | CS2 | 0 | 0.16333 |  | 0 | 0.888 | 17.76 | CS2 | 0 | 0.16333 |  | 0 | 0.888 | 17.76 | CS2 | 34.2857 | 0.49 | 0.168 | 3.36 | 0.888 | 17.76 | CS2 | 39.727 | 0.97667 | 0.388 | 7.76 | 0.888 | 17.76 | CS2 | 90.9215 | 0.97667 | 0.888 | 17.76 | 0.888 | 17.76 | CS2
|  |  | Develop training material for staff training in CSA | No | 1 | 20 | 0.5 | 0.03 | 3 | 1 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.245 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.245 | 0 | 0 | 0 | 0 | CS2 | 204.0816 | 0.245 | 0.5 | 10 | 0.5 | 10 | CS2 | 68.0272 | 0.735 | 0.5 | 10 | 0.5 | 10 | CS2 | 0 |  | 0.5 | 10 | 0.5 | 10 | CS2 | 0 | 0.245 | 0 | 0 | 0.5 | 10 | CS2 | 30.6122 | 0.16333 | 0.05 | 1 | 0.55 | 11 | CS2 | 97.9592 | 0.16333 | 0.16 | 3.2 | 0.71 | 14.2 | CS2 | 36.7347 | 0.57167 | 0.21 | 4.2 | 0.71 | 14.2 | CS2 | 0 |  | 0.71 | 14.2 | 0.71 | 14.2 | CS2 | 102.8571 | 0.16333 | 0.168 | 3.36 | 0.878 | 17.56 | CS2 | 0 | 0.16333 |  | 0 | 0.878 | 17.56 | CS2 | 0 | 0.16333 |  | 0 | 0.878 | 17.56 | CS2 | 34.2857 | 0.49 | 0.168 | 3.36 | 0.878 | 17.56 | CS2 | 35.6044 | 1.0617 | 0.378 | 7.56 | 0.878 | 17.56 | CS2 | 82.7002 | 1.0617 | 0.878 | 17.56 | 0.878 | 17.56 | CS2
|  |  | Develop training material for staff training in green finance | No | 1 | 20 | 0.5 | 0.035 | 3.5 | 0.5 | 0.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24125 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.24125 | 0 | 0 | 0 | 0 | CS2 | 207.2539 | 0.24125 | 0.5 | 10 | 0.5 | 10 | CS2 | 69.0846 | 0.72375 | 0.5 | 10 | 0.5 | 10 | CS2 | 0 |  | 0.5 | 10 | 0.5 | 10 | CS2 | 9.0909 | 0.11 | 0.01 | 0.2 | 0.51 | 10.2 | CS2 | 55.9585 | 0.10722 | 0.06 | 1.2 | 0.57 | 11.4 | CS2 | 102.5907 | 0.10722 | 0.11 | 2.2 | 0.68 | 13.6 | CS2 | 55.4795 | 0.32444 | 0.18 | 3.6 | 0.68 | 13.6 | CS2 | 0 |  | 0.68 | 13.6 | 0.68 | 13.6 | CS2 | 107.7202 | 0.10722 | 0.1155 | 2.31 | 0.7955 | 15.91 | CS2 | 0 | 0.10722 |  | 0 | 0.7955 | 15.91 | CS2 | 0 | 0.10722 |  | 0 | 0.7955 | 15.91 | CS2 | 35.9067 | 0.32167 | 0.1155 | 2.31 | 0.7955 | 15.91 | CS2 | 45.7352 | 0.64611 | 0.2955 | 5.91 | 0.7955 | 15.91 | CS2 | 123.1212 | 0.64611 | 0.7955 | 15.91 | 0.7955 | 15.91 | CS2
|  |  | Imlementation of training on green finance inCSA | Staff | 50 | 20 | 0.5 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2
|  |  | Implementation training in green finance | Staff | 50 | 20 | 0.5 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 |  | 0 | 11.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 30 |  | 30 |  |  |  |  | 30 |  | 30 |  |  |  |  | 30 |  | 30 |  |  |  |  | 0.4 |  | 30.4 |  |  |  |  | 3.2 |  | 33.6 |  |  |  |  | 8.6 |  | 42.2 |  |  |  |  | 12.2 |  | 42.2 |  |  |  |  | 42.2 |  | 42.2 |  |  |  |  | 9.03 |  | 51.23 |  |  |  |  | 0 |  | 51.23 |  |  |  |  | 0 |  | 51.23 |  |  |  |  | 9.03 |  | 51.23 |  |  |  |  | 21.23 |  | 51.23 |  |  |  |  | 51.23 |  | 51.23
3.d | 3.d | 30 agribusinesses trained in green finance and CSA | Assessment TNA on CSA and Green finance | TNA | 1 | 10 | 0.5 | 0.009 | 0.9 | 1 | 1.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2485 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.2485 | 0 | 0 | 0 | 0 | CS2 | 40.2414 | 0.2485 | 0.1 | 1 | 0.1 | 1 | CS2 | 13.4138 | 0.7455 | 0.1 | 1 | 0.1 | 1 | CS2 | 0 |  | 0.1 | 1 | 0.1 | 1 | CS2 | 0 | 0.2485 | 0 | 0 | 0.1 | 1 | CS2 | 0 | 0 | 0.05 | 0.5 | 0.15 | 1.5 | CS2 | 102.6157 | 0.16567 | 0.17 | 1.7 | 0.32 | 3.2 | CS2 | 53.1187 | 0.41417 | 0.22 | 2.2 | 0.32 | 3.2 | CS2 | 0 |  | 0.32 | 3.2 | 0.32 | 3.2 | CS2 | 107.7465 | 0.16567 | 0.1785 | 1.785 | 0.4985 | 4.985 | CS2 | 0 | 0.16567 |  | 0 | 0.4985 | 4.985 | CS2 | 0 | 0.16567 |  | 0 | 0.4985 | 4.985 | CS2 | 35.9155 | 0.497 | 0.1785 | 1.785 | 0.4985 | 4.985 | CS2 | 43.7351 | 0.91117 | 0.3985 | 3.985 | 0.4985 | 4.985 | CS2 | 54.7101 | 0.91117 | 0.4985 | 4.985 | 0.4985 | 4.985 | CS2
|  |  | Develop training material for staff training in CSA | no | 1 | 20 | 0.5 | 0.044 | 4.4 | 1 | 1.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24267 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.24267 | 0 | 0 | 0 | 0 | CS2 | 41.2088 | 0.24267 | 0.1 | 2 | 0.1 | 2 | CS2 | 13.7363 | 0.728 | 0.1 | 2 | 0.1 | 2 | CS2 | 0 |  | 0.1 | 2 | 0.1 | 2 | CS2 | 0 | 0.24267 | 0 | 0 | 0.1 | 2 | CS2 | 0 | 0 | 0.05 | 1 | 0.15 | 3 | CS2 | 98.9011 | 0.16178 | 0.16 | 3.2 | 0.31 | 6.2 | CS2 | 51.9231 | 0.40444 | 0.21 | 4.2 | 0.31 | 6.2 | CS2 | 0 |  | 0.31 | 6.2 | 0.31 | 6.2 | CS2 | 103.8462 | 0.16178 | 0.168 | 3.36 | 0.478 | 9.56 | CS2 | 0 | 0.16178 |  | 0 | 0.478 | 9.56 | CS2 | 0 | 0.16178 |  | 0 | 0.478 | 9.56 | CS2 | 34.6154 | 0.48533 | 0.168 | 3.36 | 0.478 | 9.56 | CS2 | 42.4825 | 0.88978 | 0.378 | 7.56 | 0.478 | 9.56 | CS2 | 53.7213 | 0.88978 | 0.478 | 9.56 | 0.478 | 9.56 | CS2
|  |  | Develop training material for staff training in green finance | no | 1 | 20 | 0.5 | 0.001 | 0.1 | 0.3 | 0.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066583 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.066583 | 0 | 0 | 0 | 0 | CS2 | 45.0563 | 0.066583 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 15.0188 | 0.19975 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 0 |  | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 0 | 0.066583 | 0 | 0 | 0.03 | 0.6 | CS2 | 75.0939 | 0.066583 | 0.05 | 1 | 0.08 | 1.6 | CS2 | 101.3767 | 0.088778 | 0.09 | 1.8 | 0.17 | 3.4 | CS2 | 63.0788 | 0.22194 | 0.14 | 2.8 | 0.17 | 3.4 | CS2 | 0 |  | 0.17 | 3.4 | 0.17 | 3.4 | CS2 | 106.4456 | 0.088778 | 0.0945 | 1.89 | 0.2645 | 5.29 | CS2 | 0 | 0.088778 |  | 0 | 0.2645 | 5.29 | CS2 | 0 | 0.088778 |  | 0 | 0.2645 | 5.29 | CS2 | 35.4819 | 0.26633 | 0.0945 | 1.89 | 0.2645 | 5.29 | CS2 | 48.0259 | 0.48828 | 0.2345 | 4.69 | 0.2645 | 5.29 | CS2 | 54.17 | 0.48828 | 0.2645 | 5.29 | 0.2645 | 5.29 | CS2
|  |  | Implementation of training on green finance in CSA | Staff | 30 | 20 | 0.5 | 0 | 0 | 15 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | CS2 | 0 | 5 | 0 | 0 | 0 | 0 | CS2 | 0 | 5 | 0 | 0 | 0 | 0 | CS2 | 0 | 15 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 |  | 0 | 0 | 0 | CS2 | 0 | 1.7222 |  | 0 | 0 | 0 | CS2 | 0 | 5.1667 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.8889 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.8889 | 0 | 0 | 0 | 0 | CS2
|  |  | Implement training in green finance | Staff | 30 | 30 | 0.5 | 0 | 0 | 15 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | CS2 | 0 | 5 | 0 | 0 | 0 | 0 | CS2 | 0 | 5 | 0 | 0 | 0 | 0 | CS2 | 0 | 15 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.7222 |  | 0 | 0 | 0 | CS2 | 0 | 1.7222 |  | 0 | 0 | 0 | CS2 | 0 | 5.1667 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.8889 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.8889 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 5.4 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 3.6 |  | 3.6 |  |  |  |  | 3.6 |  | 3.6 |  |  |  |  | 3.6 |  | 3.6 |  |  |  |  | 0 |  | 3.6 |  |  |  |  | 2.5 |  | 6.1 |  |  |  |  | 6.7 |  | 12.8 |  |  |  |  | 9.2 |  | 12.8 |  |  |  |  | 12.8 |  | 12.8 |  |  |  |  | 7.035 |  | 19.835 |  |  |  |  | 0 |  | 19.835 |  |  |  |  | 0 |  | 19.835 |  |  |  |  | 7.035 |  | 19.835 |  |  |  |  | 16.235 |  | 19.835 |  |  |  |  | 19.835 |  | 19.835
3.e | 3.e | 20,000 Households provided with information on climate risk-sharing instruments | Assessment of TNA on CSA and Green finance | TNA | 1 | 10 | 1 | 0.025 | 2.5 | 1 | 1.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16458 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.16458 | 0 | 0 | 0 | 0 | CS2 | 18.2278 | 0.16458 | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 6.0759 | 0.49375 | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 0 |  | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 0 | 0.16458 | 0 | 0 | 0.03 | 0.3 | CS2 | 36.4557 | 0.16458 | 0.06 | 0.6 | 0.09 | 0.9 | CS2 | 100.2532 | 0.21944 | 0.22 | 2.2 | 0.31 | 3.1 | CS2 | 51.038 | 0.54861 | 0.28 | 2.8 | 0.31 | 3.1 | CS2 | 0 |  | 0.31 | 3.1 | 0.31 | 3.1 | CS2 | 105.2658 | 0.21944 | 0.231 | 2.31 | 0.541 | 5.41 | CS2 | 0 | 0.21944 |  | 0 | 0.541 | 5.41 | CS2 | 0 | 0.21944 |  | 0 | 0.541 | 5.41 | CS2 | 35.0886 | 0.65833 | 0.231 | 2.31 | 0.541 | 5.41 | CS2 | 42.3383 | 1.2069 | 0.511 | 5.11 | 0.541 | 5.41 | CS2 | 44.8239 | 1.2069 | 0.541 | 5.41 | 0.541 | 5.41 | CS2
|  |  | Develop training material for staff training in CSA | Set | 1 | 20 | 0.5 | 0.02 | 2 | 1 | 1.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24667 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.24667 | 0 | 0 | 0 | 0 | CS2 | 12.1622 | 0.24667 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 4.0541 | 0.74 | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 0 |  | 0.03 | 0.6 | 0.03 | 0.6 | CS2 | 0 | 0.24667 | 0 | 0 | 0.03 | 0.6 | CS2 | 0 | 0 | 0.06 | 1.2 | 0.09 | 1.8 | CS2 | 97.2973 | 0.16444 | 0.16 | 3.2 | 0.25 | 5 | CS2 | 53.5135 | 0.41111 | 0.22 | 4.4 | 0.25 | 5 | CS2 | 0 |  | 0.25 | 5 | 0.25 | 5 | CS2 | 102.1622 | 0.16444 | 0.168 | 3.36 | 0.418 | 8.36 | CS2 | 0 | 0.16444 |  | 0 | 0.418 | 8.36 | CS2 | 0 | 0.16444 |  | 0 | 0.418 | 8.36 | CS2 | 34.0541 | 0.49333 | 0.168 | 3.36 | 0.418 | 8.36 | CS2 | 42.8993 | 0.90444 | 0.388 | 7.76 | 0.418 | 8.36 | CS2 | 46.2162 | 0.90444 | 0.418 | 8.36 | 0.418 | 8.36 | CS2
|  |  | Develop climate risk sharing mechanism /instrument | Set | 1 | 20 | 0.5 | 0 | 0 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.25 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.25 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.75 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0.25 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 102 | 0.16667 | 0.17 | 3.4 | 0.17 | 3.4 | CS2 | 40.8 | 0.41667 | 0.17 | 3.4 | 0.17 | 3.4 | CS2 | 0 |  | 0.17 | 3.4 | 0.17 | 3.4 | CS2 | 107.1 | 0.16667 | 0.1785 | 3.57 | 0.3485 | 6.97 | CS2 | 0 | 0.16667 |  | 0 | 0.3485 | 6.97 | CS2 | 0 | 0.16667 |  | 0 | 0.3485 | 6.97 | CS2 | 35.7 | 0.5 | 0.1785 | 3.57 | 0.3485 | 6.97 | CS2 | 38.0182 | 0.91667 | 0.3485 | 6.97 | 0.3485 | 6.97 | CS2 | 38.0182 | 0.91667 | 0.3485 | 6.97 | 0.3485 | 6.97 | CS2
|  |  | Awareness raising on weather and climate risk information sharing to communities | Household | 20000 | 50 | 0.5 | 0 | 0 | 10 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428.5714 | 0 | 0 | 0 | 0 | CS2 | 0 | 1428.5714 | 0 | 0 | 0 | 0 | CS2 | 0 | 1428.5714 | 0 | 0 | 0 | 0 | CS2 | 0 | 4285.7143 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 1.75 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1667 | 0 | 0 | 0 | 0 | CS2 | 0 | 2.9167 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1667 | 0 | 0 | 0 | 0 | CS2 | 0 | 1.1667 |  | 0 | 0 | 0 | CS2 | 0 | 1.1667 |  | 0 | 0 | 0 | CS2 | 0 | 3.5 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.4167 | 0 | 0 | 0 | 0 | CS2 | 0 | 6.4167 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 |  |  | 4.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0.9 |  | 0.9 |  |  |  |  | 0.9 |  | 0.9 |  |  |  |  | 0.9 |  | 0.9 |  |  |  |  | 0 |  | 0.9 |  |  |  |  | 1.8 |  | 2.7 |  |  |  |  | 8.8 |  | 11.5 |  |  |  |  | 10.6 |  | 11.5 |  |  |  |  | 11.5 |  | 11.5 |  |  |  |  | 9.24 |  | 20.74 |  |  |  |  | 0 |  | 20.74 |  |  |  |  | 0 |  | 20.74 |  |  |  |  | 9.24 |  | 20.74 |  |  |  |  | 19.84 |  | 20.74 |  |  |  |  | 20.74 |  | 20.74
3.f | 3.f | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | Implementation of TNA | No | 1 | 10 | 1 | 0.03 | 3 | 1 | 1.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32833 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.32833 | 0 | 0 | 0 | 0 | CS2 | 9.1371 | 0.32833 | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 3.0457 | 0.985 | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 0 |  | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 0 | 0 | 0 | 0 | 0.03 | 0.3 | CS2 | 0 | 0 |  | 0 | 0.03 | 0.3 | CS2 | 0 | 0.21889 | 0 | 0 | 0.03 | 0.3 | CS2 | 0 | 0.21889 | 0 | 0 | 0.03 | 0.3 | CS2 | 0 |  | 0.03 | 0.3 | 0.03 | 0.3 | CS2 | 0 | 0.21889 | 0 | 0 | 0.03 | 0.3 | CS2 | 0 | 0.21889 |  | 0 | 0.03 | 0.3 | CS2 | 0 | 0.21889 |  | 0 | 0.03 | 0.3 | CS2 | 0 | 0.65667 | 0 | 0 | 0.03 | 0.3 | CS2 | 0 | 0.87556 | 0 | 0 | 0.03 | 0.3 | CS2 | 3.4264 | 0.87556 | 0.03 | 0.3 | 0.03 | 0.3 | CS2
|  |  | Develop training material for staff training in green finance | No | 1 | 15 | 0.5 | 0.015 | 1.5 | 0.5 | 0.985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16417 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.16417 | 0 | 0 | 0 | 0 | CS2 | 18.2741 | 0.16417 | 0.03 | 0.45 | 0.03 | 0.45 | CS2 | 6.0914 | 0.4925 | 0.03 | 0.45 | 0.03 | 0.45 | CS2 | 0 |  | 0.03 | 0.45 | 0.03 | 0.45 | CS2 | 0 | 0 | 0 | 0 | 0.03 | 0.45 | CS2 | 0 | 0 |  | 0 | 0.03 | 0.45 | CS2 | 0 | 0.10944 | 0 | 0 | 0.03 | 0.45 | CS2 | 0 | 0.10944 | 0 | 0 | 0.03 | 0.45 | CS2 | 0 |  | 0.03 | 0.45 | 0.03 | 0.45 | CS2 | 0 | 0.10944 | 0 | 0 | 0.03 | 0.45 | CS2 | 0 | 0.10944 |  | 0 | 0.03 | 0.45 | CS2 | 0 | 0.10944 |  | 0 | 0.03 | 0.45 | CS2 | 0 | 0.32833 | 0 | 0 | 0.03 | 0.45 | CS2 | 0 | 0.43778 | 0 | 0 | 0.03 | 0.45 | CS2 | 6.8528 | 0.43778 | 0.03 | 0.45 | 0.03 | 0.45 | CS2
|  |  | Implementation of training on green finance in CSA | Persons | 20000 | 75 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714.2857 | 0 | 0 | 0 | 0 | CS2 | 0 | 714.2857 | 0 | 0 | 0 | 0 | CS2 | 0 | 714.2857 | 0 | 0 | 0 | 0 | CS2 | 0 | 2142.8571 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 | 0 |  | 0 | 0 | 0 | CS2 | 0 | 5555.5556 | 0 | 0 | 0 | 0 | CS2 | 0 | 5555.5556 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 | CS2 | 0 | 5555.5556 | 0 | 0 | 0 | 0 | CS2 | 0 | 5555.5556 |  | 0 | 0 | 0 | CS2 | 0 | 5555.5556 |  | 0 | 0 | 0 | CS2 | 0 | 16666.6667 | 0 | 0 | 0 | 0 | CS2 | 0 | 22222.2222 | 0 | 0 | 0 | 0 | CS2 | 0 | 22222.2222 | 0 | 0 | 0 | 0 | CS2
|  |  | Subtotal |  |  | 100 | 0.5 | 0 | 4.5 |  | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0.75 |  | 0.75 |  |  |  |  | 0.75 |  | 0.75 |  |  |  |  | 0.75 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0.75 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0 |  | 0.75 |  |  |  |  | 0.75 |  | 0.75
3.9 | 3.9 | sub-total Output 3 | Development of ICT | No | 1 | 55 | 1 | 0.0693 | 6.93 | 0.25 | 1.1807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14759 | 0 | 0 | 0 | 0 |  | 0 | 0.14759 | 0 | 0 | 0 | 0 |  | 135.5128 | 0.14759 | 0.2 | 11 | 0.2 | 11 |  | 45.1709 | 0.44276 | 0.2 | 11 | 0.2 | 11 | CS2 | 0 |  | 0.2 | 11 | 0.2 | 11 |  | 0 | 0.13119 | 0 | 0 | 0.2 | 11 |  | 0 | 0 |  | 0 | 0.2 | 11 |  | 99.0938 | 0.13119 | 0.13 | 7.15 | 0.33 | 18.15 |  | 49.5469 | 0.26238 | 0.13 | 7.15 | 0.33 | 18.15 | CS2 | 0 |  | 0.33 | 18.15 | 0.33 | 18.15 |  | 104.0484 | 0.13119 | 0.1365 | 7.5075 | 0.4665 | 25.6575 |  | 0 | 0.13119 |  | 0 | 0.4665 | 25.6575 |  | 0 | 0.13119 |  | 0 | 0.4665 | 25.6575 |  | 34.6828 | 0.39357 | 0.1365 | 7.5075 | 0.4665 | 25.6575 | CS2 | 40.6284 | 0.65594 | 0.2665 | 14.6575 | 0.4665 | 25.6575 | CS2 | 71.1188 | 0.65594 | 0.4665 | 25.6575 | 0.4665 | 25.6575
|  |  | Purchase of equipment | No | 1 | 25 | 1 | 0 | 0 | 0.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 |  | 0 | 0.25 | 0 | 0 | 0 | 0 |  | 0 | 0.25 | 0 | 0 | 0 | 0 |  | 0 | 0.75 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0.16667 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.16667 | 0 | 0 | 0 | 0 |  | 0 | 0.33333 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0.16667 | 0 | 0 | 0 | 0 |  | 0 | 0.16667 |  | 0 | 0 | 0 |  | 0 | 0.16667 |  | 0 | 0 | 0 |  | 0 | 0.5 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.83333 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.83333 | 0 | 0 | 0 | 0
|  |  | Installation of the center | No | 1 | 20 | 1 | 0 | 0 | 0.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.14444 | 0 | 0 | 0 | 0 |  | 0 | 0.14444 | 0 | 0 | 0 | 0 | CS2 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0.14444 | 0 | 0 | 0 | 0 |  | 0 | 0.14444 |  | 0 | 0 | 0 |  | 0 | 0.14444 |  | 0 | 0 | 0 |  | 0 | 0.43333 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.57778 | 0 | 0 | 0 | 0 | CS2 | 0 | 0.57778 | 0 | 0 | 0 | 0
|  |  | Subtotal |  |  | 100 |  |  | 6.93 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 11 |  | 11 |  |  |  |  | 11 |  | 11 |  |  |  |  | 11 |  | 11 |  |  |  |  | 0 |  | 11 |  |  |  |  | 0 |  | 11 |  |  |  |  | 7.15 |  | 18.15 |  |  |  |  | 7.15 |  | 18.15 |  |  |  |  | 18.15 |  | 18.15 |  |  |  |  | 7.5075 |  | 25.6575 |  |  |  |  | 0 |  | 25.6575 |  |  |  |  | 0 |  | 25.6575 |  |  |  |  | 7.5075 |  | 25.6575 |  |  |  |  | 14.6575 |  | 25.6575 |  |  |  |  | 25.6575 |  | 25.6575
|  |  | Total for all Outputs | [5 empty] | 66.33 |  |  |  |  | 0 |  |  | 0 |  |  | 7.325 |  |  | 7.325 |  |  |  | 18.5 |  | 25.825 |  |  |  |  | 10 |  | 605.625 |  |  |  |  | 57.25 |  | 662.875 |  |  |  |  | 85.75 |  | 662.875 |  |  |  |  | 93.075 |  | 662.875 |  |  |  |  | 0.65 |  | 663.525 |  |  |  |  | 16.8 |  | 680.325 |  |  |  |  | 49.6 |  | 729.925 |  |  |  |  | 67.05 |  | 729.925 |  |  |  |  | 160.125 |  | 729.925 |  |  |  |  | 52.08 |  | 782.005 |  |  |  |  | 0 |  | 782.005 |  |  |  |  | 0 |  | 782.005 |  |  |  |  | 52.08 |  | 782.005 |  |  |  |  | 119.13 |  | 782.005 |  |  |  |  | 212.205 |  | 782.005
|  |  | Original as of July 2021 (Dead formulation) | [5 empty] | 66.33 |  |  |  |  | 0 |  |  | 0 |  |  | 3.9967 |  |  | 3.9967 |  |  |  | 16.8333 |  | 20.83 |  |  |  |  | 8.3333 |  | 438.5833 |  |  |  |  | 32.3333 |  | 470.9167 |  |  |  |  | 57.5 |  | 470.9167 |  |  |  |  | 61.4967 |  | 470.9167 |  |  |  |  | 6.8667 |  | 477.7833 |  |  |  |  | 0 |  | 477.7833 |  |  |  |  | 0 |  | 477.7833 |  |  |  |  | 6.8667 |  | 477.7833 |  |  |  |  | 68.3633 |  | 477.7833 |  |  |  |  | 0 |  | 477.7833 |  |  |  |  | 0 |  | 477.7833 |  |  |  |  | 0
|  |  | Deviation | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 3.3283 | [6 empty] | 1.6667 | [6 empty] | 1.6667 | [6 empty] | 24.9167 | [20 empty] | -6.2167 | [6 empty] | 16.8 | [6 empty] | 49.6 | [20 empty] | 52.08 | [6 empty] | 0 | [6 empty] | 0
Note on C9: Lenovo: Suggest to re-arrange sub-activities again to match with main activity
Note on C14: Lenovo: Suggest to re-arrange sub-activities again to match with main activity
Note on D5: Administrator: Based the dicussion with DTL/CS2 with National M&E Expert on 29 June 2021, he said that TL/CS2 requested to modify some main Activities under Output 3 as in red font, while its black font will be deleted.
Note on D9: User: Previous was "Review standards of CSA, GAP and SRP Agribusiness policy development)"
Note on D10: User: Previous "Formulate climate smart agribusiness policy "/Second was "(Contract farming policy development _as a component of agribusiness policy"
Note on D11: Lenovo: row 10 & 11 combine into 1 policy. Referred to Pollard, Climate smart agribusiness policy and gender responsive agribusiness policy is only one policy
Note on D14: User: Previous was "Identify Fruit for Developing GAP Standards"
Note on D15: User: Previous was "Develop GAP Standards for tropical Fruit"
Note on D16: User: Previous was "Secure Endorsement for GAP Standards for tropical fruit"
Note on E9: User: Previous is No
Note on E10: User: Previous do not have contract farming policy
Note on E11: User: Previous does not have development proclamation to support AC
Note on E12: User: Previous is not here, but under other colum
Note on E14: User: Previous is No.
Note on E15: User: Previous is No.
Note on E16: User: Previous is No.
Note on E17: User: Previous is No.
Note on E18: User: Previous is No.
Note on E19: User: Previous is No.
Note on E28: User: Previous is Assessment
Note on E29: User: User: Previous is Set
Note on E30: User: User: Previous is Set
Note on E34: User: Previous is Assessment
Note on F9: User: Previous 3
Note on F15: User: Previous 1
Note on G15: User: Previous 20
Note on G17: User: Previous 20
Note on G18: User: Previous 0
Note on G19: User: Previous 0
Note on I18: User: Previous 0
Note on I19: User: Previous 0
Note on M15: User: Previous 0.50
Note on M17: User: Previous 0.00
Note on M18: User: Previous is 0
Note on M19: User: Previous is 0
Note on M30: User: Previous 15.00
Note on N9: User: Previous 2
Note on AX43: User:  Follow-up with MEF on reviewing report of CEC (Consulting Evaluation Committee) on EOIs shortlisting for Consulting Service of, Information and Communication Technology (ICT) Platform for Climate Risk Management in Agribusiness Value Chains in Kampong Cham Province - Package CS4 (by Procurement team).
in JV with SBK Research and Development
Implemented by

## DMF PI 1st 6Ms Report 2021
CFAVC PROJECT's DMF PERFORMANCE INDICATORS PROGRESS REPORT (January - June 2021)
No. of indicators | M&E Indicator Codes | PAM's DMF Indicators Codes | MAFF's indicator Codes | DMF Performant Indicators | Definitions |  | Methods for Tracking | Time line | CS#/ Units | Ministries | Unit | Baseline | Target | [7 empty] | Assigned Weight (%) | Achievement in 2020 |  |  | First Six-Monthly (January - June ) Cumulative Progress in 2021 |  |  |  | Second Six-Monthly Cumulative Progress in 2021 |  |  |  | Cummulative Progress Tracking to date in 2020 - 2021
[6 empty] | Consultants | [15 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress
[13 empty] | Total | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | [12 empty] | Total Target | Total Actual Achieved | % Weight Progress
| OC |  |  | Outcome, Productive and resource efficient agribusiness value chains developed in project areas | [16 empty] | 100 |  | 2.0032 | 11.8291 |  | 14.9969 | 25.4428 |  |  | 2.9077 | 7.2823 |  |  | 19.9078 | 44.5542
1 | OC.1 | a. |  | By 2026 a. At least 15% increase in yields (2017 baseline: rice 2.7 tons, maize 4 tons, cassava 20 tons and mango 15 tons/ha). |  |  | a. MAFF agricultural census |  | CS 2 | MAFF | % |  | 15% | [12 empty] | MTR |  |  | 0 | MTR | #VALUE!
| OC.1.a.1 |  |  | Rice (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 2.7 | 3.105 | 0 | 2.7 | 2.8013 | 2.9025 | 3.0038 | 3.105 | [9 empty] | 1.4006
| OC.1.a.2 |  |  | Maize (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 4 | 4.6 | 0 | 4 | 4.15 | 4.3 | 4.45 | 4.6 | [9 empty] | 2.075
| OC.1.a.3 |  |  | Cassava (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 20 | 23 | 0 | 20 | 20.75 | 21.5 | 22.25 | 23 | [9 empty] | 10.375
| OC.1.a.3 |  |  | Mango (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 15 | 17.25 | 0 | 15 | 15.5625 | 16.125 | 16.6875 | 17.25 | [9 empty] | 7.7812
2 | OC.2 | b. |  | By 2026 b. GHG emissions reduced by 240,000 tons of CO2 (2017 baseline: 0 tons reduced due to the project). | Base on the biogas utilization calculation. |  | b. UNFCCC reports |  |  |  | Tone | 0 | 240000 | 0 | 0 | 0 | 80000 | 80000 | 80000 | [6 empty] | MTR |  |  | 0 | MTR | #VALUE!
3 | OC3 | c. |  | By 2026 c. At least 50 agribusinesses become more resource efficient in terms of water savings (5-10% efficiencies); energy savings (20%); and reduction in post-harvest losses (10%) (2017 baseline: 0). |  |  | c. PPMS reports |  | CS 2 | MAFF | % | 0 | 50 | 0 | 0 | 0 | 5 | 20 | 25 | [6 empty] | MTR |  |  | 0 | MTR | #VALUE!
| OC3.C.1 |  |  | Water saving (5-10% efficient) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [9 empty] | 1.25
| OC3.C.2 |  |  | Energy saving (20%) | Focus on the biogas utilization. |  |  |  | CS 2 | MAFF | % | 0 | 20 | 0 |  | 5 | 10 | 15 | 20 | [9 empty] | 2.5
| OC3.C.3 |  |  | Post harvesting losses (10%) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [9 empty] | 1.25
| OP.1 |  |  | Outputs. 1. Critical agribusiness value chain infrastructure improved and made climate resilient | [16 empty] | 65 |  |  | 7.4776 |  | 10.142 | 16.5232 |  |  | 1.7911 | 4.7531 |  |  | 11.9331 | 28.7539
4 | OP.1.1 | 1.a. |  | 1a. 27 irrigation and water management systems targeting 15,000 ha and 25,000 households (with at least 50,000 women) rehabilitated and made climate resilient (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 1 | MOWRAM | Woman | 0 | 27 | 2019: 0; 2020: 10; 2021: 9 | 15 | 10 | 10.06 | 1.509 | 4.5 | 30.6671 | 4.6001 | 28 Irrigation schemes were identified, of which 8 were conducted its sub-projects’ feasibilities studies, 10 schemes were conducted its topographical survey, 18 irrigation schemes were on the preparation of topographical survey, 5 schemes were conducted its DED, while 2 schemes were on preparation of DED (Pram Kompheak and O’Kamprok), 1 Trapping Run under progress of construction up to 95% completed, and 5 irrigation systems were under bid evaluation process, and only Trapeang Run, other 5 schemes were in the progress and signatures. After the feasibility studies, and topographical survey, 16,000 ha were covered. 5 schemes were conducted its DED, while 2 schemes were on preparation of DED (Pram Kompheak and O’Kamprok), Trappaing Run was under progress of construction up to 90% completed. To contribute to the above achievement, 7 field visits were conducted, with a total number of 161 participants, of which 55 participants were women. | 4.5 |  | 0% |  | 19 | 40.7271 | 610.9%
| OP.1.1a.1 |  |  | 27 irrigation and water management systems |  |  |  |  | CS 1 | MOWRAM | Irrigation System | 0 | 27 | 2019: 0; 2020: 10; 2021: 9; 2022: 8 |  | 10 | 17.1936 | 0.2065 | 4.5 |  |  |  | 4.5
| OP.1.1a.2 |  |  | 27 irrigation and water management systems targeting 15,000 ha |  |  |  |  | CS 1 | MOWRAM | Ha | 0 | 15000 | 2019: 0; 2020: 4050; 2021: 5333; 2022: 5617 |  | 4050 | 1399.5 | 1.866 | 2666.5 |  |  |  | 2666.5
| OP.1.1a.3 |  | No PP | 27 irrigation and water management systems targeting 25,000 households |  |  |  |  | CS 1 | MOWRAM | Household | 0 | 25000 | 2019: 0 |  |  |  |  | 0 |  |  |  | 0
5 | OP.1.2 | 1b. |  | 1b. 800 on-farm rainwater harvesting ponds commissioned (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 2 | MAFF | Pond | 0 | 800 | 0 | 80 | 280 | 290 | 150 | 0 |  | 5 |  | 4.13 | 0.2065 | 140 | 1.125 | 0.05625 | The activity does not undertake yet, still waiting for clear decision, which made by the government, for which Ministry will be responsible for implementation of this indicator? | 140 |  | 0% |  | 280 | 5.255 | 26.27%
6 | OP.1.3 | 1c. |  | 1c. At least 250 km of farm road networks upgraded to climate standards to improve connectivity of farms to cooperatives and markets (2017 baseline: 0). | Add next |  | MRD annual report |  | CS 1 | MRD | Km | 0 | 250 | 2019: 0; 2020: 67.95; 2021: 100.1; 2022: 81.95 | 15 |  | 14.05 | 2.1075 | 50.05 | 25.4028 | 3.8104 | The 2020 Road subprojects’ conducted of, its identifications, feasibility studies, topographic survey DED, Tender file, of which all 8 subprojects with 70.12 Km for 4 provinces. (Takeo 14.67 Km, Tboung Khmum 21.77 Km, Kampong Cham 14.60 Km and Kampot 20.07 Km) were completed. -- The 2021 Road subprojects identification of 20 subprojects with 100.77 Km for 4 provinces, which the feasibility is 60% progressed, topographic survey is 30% progressed, while the DED, and Tender file were not yet started. -- 2022 planned Road subprojects identified and selected 12 subprojects with 102.50 Km for 4 provinces but the feasibility study, topographic survey, DEC, and Tender file, were not yet started. -- Conducted Environmental Safeguards in Kampot province, with 20.07 Km, ADB provides NOL IEE/EMP on 9th July 2021. -- Conducted the Social safeguards in Takeo province with 14.67 Km, the subproject is classified as category B. The LARP is under revision by the consultant based on comments from ADB. It is re-submitted to ADB by 4th week of July 2021. -- Conducted the Social safeguards in Tboung Khmum province with 21.77 Km, the subproject is classified as category C. The DDR submitted to ADB on 29 March 2021 for review. The draft DDR is under revision by consultant based on the comments from the Third Party and it will be submitted to ADB by the 1st week of Aug 2021. -- Conducted the Social safeguards in Kampong Cham province with 14.60 Km, the subproject is classified as category B. The LARP needs to be prepared. The pegging and demarcation will be ready for DMS to be started in 2nd week of July 2021, the DRP will be prepared based on the DMS data has been completely done with the support from consultant team. -- Conducted the Social safeguards in Kampot province with 20.07 Km, the classification of category not yet decide. A joint field visit by GDR, CS5 and CS1 is carried out 3rd week of July 2021 to decide whether category B or C. -- Conduced the procurement process of subproject in Takeo province with 14.67 Km, the bid evaluation report (BER) is completed and to submit to ADB for NOL during 3rd week of July 2021. -- Conduced the procurement process of subproject in Tboung Khmum province with 21.77 Km, invitation to bid is advertised on the 2nd June 2021. Bid opening is conducted on the 2nd July 2021, BER preparation is in progress. -- Conduced the procurement process of subproject in Kampong Cham province, with 14.60 Km, the bid opening is conducted on the 2nd July 2021, BER preparation is in progress. -- Conduced the procurement process of subproject in Kampot province, with 20.07 Km, invitation to bid is scheduled to advertise during the 1st week of Aug 2021. -- To contribute to the above achievements during the reporting period, there 9 events were conducted, with a total number of 434 participants, of which 109 participants were women. Out of these 9 conducted events, there were 2 conducted events were the meetings, with a total number of 35 participants, of which 3 participants were women, and 7 conducted events more were the field visits, with a total number of 399 participants, of which 106 participants were women. | 50.05 |  | 0% |  | 100.1 | 39.4528 | 591.8%
7 | OP.1.4 | 1d. |  | 1d. 80 agricultural cooperatives* integrated adaptation measures in post-harvest infrastructure investments (2017 baseline: 5). | Add next | Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | AC | 5 | 80 | 0 | 20 | 35 | 25 | 0 | 0 |  | 15 |  | 15.06 | 2.259 | 17.5 | 39.8656 | 5.9798 | 35 ACs for supporting in 2021 were identified and completed feasibility report. DED and tender file preparation for 35 ACs support in 2021 were completed and submitted to PMU for further review and prior approval. Procurement for 20 ACs support in 2020 were floated out publicly and waiting for bidding evaluation report, constructor identification, however, the construction of 20 ACs don’t start activities yet. At least benefit to 16,500 people and the progress in tracking. | 17.5 |  | 0% |  | 35 | 54.9256 | 823.9%
8 | OP.1.5 | 1e. |  | 1e. Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples (2017 baseline: 700) and generate service income more than $75,000 (2017 baseline: $0). | Add next | Vong Sophorn/ Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | [10 empty] | 5 |  | 16 | 0.8 |  | 23.4 | 1.17 | Starting gradually progress and the progress including, - Prepared training program; - Prepared concept notes for green house construction and LAB-room renovation; - Submitted all prepared concept notes to PMU for further verify and prior approval. | 0 |  | #DIV/0! |  | 0 | 39.4 | #DIV/0!
| OP.1.5.1e.1 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples |  |  | PPMS annual reports |  | CS 2 | MAFF | Sample | 700 | 1500 | 0 | 0 | 0 | 900 | 1100 | 1500 | [5 empty] | 0 |  |  |  | 0
| OP.1.5.1e.2 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded generate service income more than $75,000 |  |  | PPMS annual reports |  | CS 2 | MAFF | USD | 0 | 75000 | 0 | 0 | 0 | 45000 | 55000 | 75000 | [5 empty] | 0 |  |  |  | 0
9 | OP.1.6 | 1f. |  | 1f. 12,000 additional biodigesters and 6,000 compost huts made operational, benefiting at least 80,000 persons, including at least 50% women, due to better household air quality (2017 baseline beneficiaries: 11,468 persons, including 5,721 women). | Add next | Phuong Dara | PPMS annual reports |  | CS 2 | MAFF | [16 empty] | 0.90658 | Look into below of its respective narrative contribution please. During the reporting period, to contribute to this indicator achievement there were 5 events conducted, with a total number of 120 participants, of which 49 participants were women. Out of these 5 conducted events, there were 4 conducted events were the field visits, with a total number of 99 participants, of which 42 participants were women, and 1 conducted event more was the field visits, with a total number of 21 participants, of which 7 participants were women. | 0 |  | #DIV/0!
| OP.1.6.1f.1 | 1f.1 |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Biodigesters | No BL | 12000 | 0 | 500 | 2500 | 4000 | 3500 | 1500 |  | 4 |  | 7.07 | 0.2828 | 1250 | 3.6731 | 14.69% | Completed first procurement for 500 biodigesters completed and waiting for BER approval and constructor’s identification; - Construction of 500 biodigesters do not undertake yet; - Started to identify new 750 biodigesters, planned for 2021. - A total of 1,250 families or 6,250 people (50% were women) were benefited from the program by 2021. | 1250 |  |  |  | 2500 | 10.7431 | 42.97%
|  |  |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 80000 | 0 | 3333.3333 | 16666.6667 | 26666.6667 | 23333.3333 | 10000 | [5 empty] | 8333.3333 |  |  |  | 8333.3333
| OP.1.6.1f.2 | 1f.2 |  | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Compost hut | No BL | 6000 | 0 | 250 | 1250 | 1600 | 1600 | 1300 |  | 4 |  | 7.47 | 0.2988 | 625 | 4.8482 | 0.19393 | Completed first procurement for 250 compost huts and waiting for BER approval and constructor’s identification; - Construction of 250 compost huts do not undertake yet; - Started to identify new 375 compost huts planned for 2021; A total of 625 families or 3,125 people (50% were women) will be benefited from the program by 2021. | 625 |  |  |  | 1250 | 12.3182 | 49.27%
|  |  | No PP | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 833.3333 | 4166.6667 | 5333.3333 | 5333.3333 | 4333.3333 | [5 empty] | 2083.3333 |  |  |  | 2083.3333
| OP.1.6.1f.3 | 1f.3 |  | 20,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  | Phuong Dara | Physical Progress |  | CS 2 | MAFF |  | No BL | 20000 | 0 | 2500 | 5000 | 9500 | 3000 | 0 |  | 2 |  | 0.7 | 0.014 | 2500 | 28.2864 | 0.56573 | It is on the progress. During the reporting period, to contribute to this indicator achievement there 15 events were conducted, with a total number of 246 participants, of which 42 participants were women. Out of these 15 conducted events, there were 5 conducted events were the trainings, with a total number of 81 participants, of which 11 participants were women, 6 conducted events were the meetings, with a total number of 117 participants, of which 16 participants were women, 1 conducted event was the field visit, with a total number of 20 participants, of which 7 participants were women, and 3 conducted event more was the field follow up, with a total number of 28 participants, of which 8 participants were women. | 2500 |  |  |  | 5000 | 28.9864 | 57.97%
| OP.1.6.1f.3 | 1f.3.1 | No PP | 20,000 people trained on biodigester use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 1250 | 2500 | 4750 | 1500 | 0 | [5 empty] | 1250 |  |  |  | 1250
| OP.1.6.1f.8 | 1f.3.2 | No PP | 20,000 people trained on compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Woman | 11468 | 20000 | 0 | 1250 | 2500 | 4750 | 1500 | 0 | [5 empty] | 1250 |  |  |  | 1250
| OP.2 |  |  | Outputs. 2. Climate smart agriculture and agribusiness promoted | [16 empty] | 20 |  | 2.0032 | 2.9565 |  | 3.0299 | 6.9481 | [6 empty] | 5.033 | 9.9046
10 | OP.2.1 | 2a. |  | 2a. Three additional climate resilient varieties of rice and maize released (2017 baseline: 0). | Add next | Sophath Heng | PPMS annual reports |  | CS 2 | MAFF | Variety | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  | 5 |  | 6.25 | 0.3125 | 0 | 7.1304 | 0.51694 | During first semester of 2021, this indicator was progressed narratively, but CARDI does not sign contract with IRRI yet. Anyhow during the reporting period, to contribute to this indicator narrative achievement, there 21 events were conducted, with a total number of 1,069 participants, of which 318 participants were women. Out of these 21 conducted events, there were 1 conducted event was the meeting, with a total number of 10 participants, of which 2 participants were women, 2 conducted events were the field visits, with a total number of 19 participants, of which 4 participants were women, 6 conducted events were the demonstrations, with a total number of 100 participants, of which 47 participants were women, 6 conducted events were the assessments, with a total number of 767 participants, of which 244 participants were women, 6 conducted events more were the feasibility studies, with a total number of 173 participants, of which 21 participants were women. | 0 |  | #DIV/0! |  | 0 | 13.3804 | #DIV/0!
| OP.2.1.2a.1 |  |  | Three additional climate resilient varieties of rice released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | [5 empty] | 0 |  | 0 |  | 0
| OP.2.1.2a.2 |  |  | Three additional climate resilient varieties of maize released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0 |  | 0 |  | 0
11 | OP.2.2 | 2b. |  | 2b. 40,000 farmers (of whom 16,000 are women) trained in CSA and agribusiness development skills, of which 50% are SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0). | Add next | Pon Han | PPMS annual reports |  | CS 2 | MAFF |  | No BL | 40000 | 0 | 2500 | 10000 | 9500 | 9000 | 9000 |  | 5 |  | 16.98 | 0.849 | 5000 | 15.1957 | 0.90512 | Look into below of its respective narrative contribution please. | 5000 |  | 0% |  | 10000 | 32.1757 | 175.4%
| OP.2.2.2b.1 |  |  | farmers (of whom 16,000 are women) trained in CSA | [6 empty] | Person | No BL | 20000 | 0 | 501 | 5000 | 5000 | 5000 | 4499 | [5 empty] | 2500 |  | 0.72292 | During first semester of 2021, the activity of the indicator does not progress, and CARDI does not sign contract with IRRI yet | 2500
| OP.2.2.2b.2 |  | No PP | farmers (of whom 16,000 are women) trained in Agribusiness Development Skills (ADS) | [6 empty] | Person | No BL | 20000 | 0 | 250 | 4937.5 | 4937.5 | 4937.5 | 4937.5 | [5 empty] | 2468.75 |  |  | During first semester of 2021, the activities of the indicator does not progress, and CARDI does not sign contract with IRRI yet. | 2468.75
| OP.2.2.2b.3 |  |  | farmers are trained on SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0) | [6 empty] | Person | 0 | 20000 | 0 | 875 | 4781.25 | 4781.25 | 4781.25 | 4781.25 | [5 empty] | 2390.625 |  | 0.1 | During first semester of 2021, the activities of the indicator does not progress, and CARDI does not sign contract with IRRI yet. | 2390.625
|  |  | Add more | farmers are trained on CAMGAP compliant | [7 empty] | No BL | 500 | 0 | 250 | 250 | 0 | 0 | 0 | [5 empty] | 125 |  | 0.69 | During first semester of 2021, the activities of the indicator does not progress, and CARDI does not sign contract with IRRI yet. | 125
|  |  | Add more | 20% of total 40,000 farmers are trained on Agricultural farm Machinery | [7 empty] | No BL | 8000 | 0 | 496 | 2376 | 2000 | 2000 | 1128 | [5 empty] | 1188 |  | 0.19737 | During first semester of 2021, the activities of the indicator does not progress, and CARDI does not sign contract with IRRI yet. | 1188
12 | OP.2.3 | 2c. |  | 2c. 27 FWUCs/FWUGs made operational and 500 FWUC/FWUG members (of which 30% women) developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM | Add next | Soeur Sophorn | PPMS annual reports |  | CS 2 | MAFF | FWUC | 0 | [14 empty] | 1.595 | Look into below of its respective narrative contribution please. | 0 |  | #DIV/0!
| OP.2.3.2c.1 | 2C1 |  | 27 FWUCs/FWUGs made operational and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM |  | Soeur Sophorn - CS2 |  |  | CS 2 | MAFF | FWUC | 0 | 27 | 0 | 10 | 8 | 9 | 0 | 0 |  | 3 |  | 12.1 | 0.363 | 4 | 26.1549 | 1.9151 | It is on the progress, the FWUCs establishment were delayed due to COVID-19 restriction. However, completed the establishment of 5 FWUCs of, Trapeang Run, Takouch, Kbal Teuk, Tuol Pring and Trapeang Tros, 50% of Prey Khdouch and Kraing Empil FWUCs were progressed, and 30% Pram Kompheak and O Kamprok were also progressed. Anyhow during the reporting period, to contribute to the indicator achievement, there 37 events were conducted, with a total number of 1,839 participants, of which 617 participants were women. Out of these 37 conducted events, there were 28 conducted events were the meetings, with a total number of 1,677 participants, of which 599 participants were women, 9 conducted events were the other events, with a total number of 162 participants, of which 18 participants were women. | 4 |  |  |  | 8 | 38.2549 | 227.8%
| OP.2.3.2c.2 | 2C2 |  | 500 FWUC/FWUG members developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 500 | 0 | 100 | 100 | 100 | 100 | 100 |  | 3 |  | 10 | 0.3 | 50 | 16.5 | 1.275 | Training program and training content developed. However, due to COVID-19 pandemic and community spread out, the training to FWUC’s representatives and members do not undertake yet. | 50 |  |  |  | 100 | 26.5 | 157.5%
13 | OP.2.4 | 2d. |  | 2d. 4 provincial agricultural development centers and 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). | Add next | Phai Sok Heng | PPMS annual reports |  | CS 2 | MAFF |  | 0 | 8 |  | 6 | 6 | 2 | 0 | 0 | [5 empty] | 3 | 3.504 | 1.168 | Progress in tracking, however, waiting till PADCs and MEWs constructed. | 3 |  | 0%
| OP.2.4.2d.1 | 2d1 |  | 4 provincial agricultural development centers made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | PADC | 0 | 4 | 2019: 0; 2020: 3; 2022: 1 | 2 |  | 26.3 | 0.526 | 1.5 | 45.175 | 1.1265 | Progress in tracking, however, waiting till PADCs constructed. | 1.5 |  |  |  | 3 | 71.475 | 165.2%
| OP.2.4.2d.2 | 2d2 |  | 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Workshop | 0 | 4 | 2019: 0; 2020: 3; 2022: 1 | 2 |  | 30.3 | 0.606 | 1.5 | 51.825 | 1.2095 | Progress in tracking, however, waiting till MEWs constructed. | 1.5 |  |  |  | 3 | 82.125 | 181.5%
| OP.3 |  |  | 3. Enabling environment for climate friendly agribusiness enhanced | [16 empty] | 15 |  |  | 1.395 |  | 1.825 | 1.9715 |  |  | 1.1167 | 2.5292 |  |  | 2.9417 | 5.8957
14 | OP.3.1.a | 3a. |  | 3a. Climate-smart and gender-responsive agribusiness policy for target commodities, including a PPP framework focusing on agribusinesses formulated (2017 baseline: 0).** | Add next | Hoeung Hun / Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | Policy |  | 6 | 0 | 0 | 1.9 | 1.9 | 1.6 | 0.5 |  | 2 |  | 19 | 0.38 | 0.95 | 37.325 | 0.7465 | Look into below of its respective narrative contribution please. Anyhow during the reporting period, to contribute to this indicator narrative achievement, there 38 events were conducted, with a total number of 969 participants, of which 336 participants were women. Out of these 38 conducted events, there were 38 conducted events were the meetings, with a total number of 969 participants, of which 336 participants were women. | 0.95 |  | 0% |  | 1.9 | 56.325 | 112.7%
| OP.3.1.3a.1 |  |  | Agribusiness and Gender responsive policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 2019: 0; 2021: 0.4; 2022: 0.4; 2023: 0.1 |  |  |  |  | 0.2 |  |  | Conducted technical meeting with TWG on the process of policy study and formulation. In the process of local consultant selection by procurement unit. | 0.2
| OP.3.1.3a.2 |  |  | CSA Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | it is on the progress. Reviewing relevant existing policy documents. | 0.15
| OP.3.1.3a.3 |  |  | Agro-Industry Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | This policy suggests and requested by the department of Agro-Industry, MAFF. The activities do not undertake yet, and it need to be discussed and agreed by the project. | 0.15
| OP.3.1.3a.4 |  |  | Contract Farming Inclusive Agribusiness Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | This policy suggests and requested by the department of Agro-Industry, MAFF. The activities do not undertake yet, and it need to be discussed and agreed by the project. | 0.15
| OP.3.1.3a.5 |  |  | Proclamation/Prakas Supporting AC’s Law |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | This policy requested by the Department of Agriculture Cooperative Promotion and Development/GDA, MAFF. The activities do not undertake yet, and it need to be discussed and agreed by the project. | 0.15
| OP.3.1.3a.6 |  |  | PPP-Initiative Agribusiness Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | Progress in tracking including, - Drafted ToR for feasibility study on selected commodities supports to national policy, however, the feasibility study still waiting for agreement, which commodities should conduct the study. - Drafted PPP framework and submitted to Department of Planning and Statistic for further reviewing and prior approval. | 0.15
15 | OP.3.2 | 3b. |  | 3b. CAMGAP for tropical fruit and organic fertilizers endorsed as national standard for tropical fruit and organic fertilizers (2017 baseline: 0). | Add next | Hoeung Hun / Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | Standard | 0 | 2 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2 |  | 2 |  | 14.5 | 0.29 | 0.3 | 9.5 | 0.19 | Look into below of its respective narrative contribution please. | 0.3 |  | 0% |  | 0.6 | 24 | 48%
| OP.3.3b.1 |  |  | CAMGAP for tropical fruit endorsed as national standard for tropical fruit (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | The activity does not undertake yet but it is some narratively progressed. | 0.15
| OP.3.3b.2 |  |  | CAMGAP for organic fertilizers endorsed as national standard for organic fertilizers (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  | The activity does not undertake yet but it is some narratively progressed | 0.15
16 | OP.3.3 | 3c. |  | 3c. 50 staff, including 30% women, from financial institutions trained in CSA and green finance (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF | Person | 0 | 50 | 0 | 0 | 15 | 20 | 15 | 0 |  | 2 |  | 11.5 | 0.23 | 7.5 | 30 | 0.6 | The activities do not undertake yet, due to the Specialist will be mobilized in early July 2021. | 7.5 |  | 0% |  | 15 | 41.5 | 83%
| OP.3.3C.1 |  |  | 50 staff, including 30% women, from financial institutions trained in CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 7.5 | 10 | 7.5 | 0 | [5 empty] | 3.75 |  |  | The activities do not undertake yet, due to the Specialist will be mobilized in early July 2021. | 3.75
| OP.3.3C.2 |  |  | 50 staff, including 30% women, from financial institutions trained in Green finance (2017 baseline:0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 7.5 | 10 | 7.5 | 0 | [5 empty] | 3.75 |  |  | The activities do not undertake yet, due to the Specialist will be mobilized in early July 2021 | 3.75
17 | OP.3.4 | 3d. |  | 3d. 30 agribusinesses, including 30% women-led and/or owned,*** trained on green finance and CSA (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF |  |  | 30 | 0 | 0 | 10 | 10 | 10 | 0 |  | 2 |  | 5.4 | 0.108 | 5 | 3.6 | 0.072 | The activities do not undertake yet, due to the Specialist will be mobilized in early July 2021. | 5 |  | 0% |  | 10 | 9 | 18%
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on Green finance (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 2.5 |  |  | The activities do not undertake yet, due to the Specialist will be mobilized in early July 2021. | 2.5
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Woman | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 2.5 |  |  | The activities do not undertake yet, due to the Specialist will be mobilized in early July 2021. | 2.5
18 | OP.3.5 | 3e. |  | 3e. 20,000 households, including 20,000 women, provided with information on climate risk sharing instruments (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | Household | 0 | 20000 | 0 | 0 | 5500 | 6000 | 6000 | 2500 |  | 2 |  | 4.5 | 0.09 | 2750 | 0.9 | 0.018 | Look into below of its respective narrative contribution please. | 2750 |  | 0% |  | 5500 | 5.4 | 10.8%
19 | OP.3.6 | 3f. |  | 3f. ICT platform for climate friendly agribusiness established in Kampong Cham province (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | ICT Platform | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 2 |  | 4.5 | 0.09 | 0.15 | 0.75 | 1.5% | Progress in tracking and CS4 under process of procurement. | 0.15 |  | 0% |  | 0.3 | 5.25 | 10.5%
| OP.3.7 | 3g | No DMF | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | Add next | [5 empty] | ICT Platform |  | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 3 |  | 6.9 | 0.207 |  | 11 | 0.33 | Progress in tacking and Waiting till CS4 mobilized.
[27 empty] | #DIV/0! |  | 0 |  | #DIV/0!
GENDER AND SOCIAL DIMENSIONS
Output 1: Critical agribusiness value chain infrastructure improved and made climate resilient
Gender Objectives. 1.1 Ensure critical agribusiness value chain infrastructure is responsive to the needs of women and men
20 |  | 1.1.1 |  | 1.1.1 (i) Women are 40% of participants– aggregate basis (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3; 30% female participation in similar activities currently); (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y4 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  | 1.1.1.i |  | (i) Women are 40% of participants– aggregate basis (point of reference: female population: |  |  |  |  | CS 1 | MAFF | % | No BL | 40 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Women are 54% of participants in subproject 1; |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 47% of participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 48% of participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 30% female participation in similar activities currently); |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  |  |  | 0
|  | 1.1.1.ii |  | (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems |  |  |  |  | CS 1 | MAFF | Person | No BL | 50000 | [11 empty] | 0 |  |  |  | 0
Gender Objectives. 1.2. Enhance income generating opportunities for women
21 |  | 1.2.1 |  | 1.2.1 At least 25% of workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y6 | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by skilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by unskilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  |  |  | 0
|  |  |  | Workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) |  |  |  |  | CS 1 | MAFF | % | No BL | 17-46 | [11 empty] | 0 |  |  |  | 0
22 |  | 1.2.2 |  | 1.2.2 At least 30% women FWUC members developed capacity to operate and maintain irrigation schemes. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
Gender Objectives. 1.3 Increase the uptake of biodigesters
23 |  | 1.3.1 |  | 1.3.1 At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y4 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 5721 | 40000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 |  |  |  | 0
24 |  | 1.3.2 |  | 1.3.2 Number and percentage of women active agents. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y4 | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Number of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | Percentage of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 |  |  |  | 0
Output 2: Climate smart agriculture and agribusiness promoted
Gender Objectives. 2.1 Strengthen women farmers’ (individual and member of cooperatives) involvement along climate- friendly agribusiness value chains
25 |  | 2.1.1 |  | 2.1.1 Number and % of women farmers involved | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Number of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | % of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 |  |  |  | 0
26 |  | 2.1.2 |  | For 2.1.2 (1) and (3): Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA and agribusiness development skills (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3 with almost all of them farming; 30% female participation in similar activities currently). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | [16 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA . |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in Agribusiness Development Skills |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 54% of total participants in subproject 1 |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 47% of total participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 48% of total participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 |  |  |  | 0
|  |  |  | 30% female participation in similar activities currently |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  |  |  | 0
27 |  |  |  | For 2.1.2 (2): (i) Number and percentage of women farmers trained in each event; (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y5 | [16 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Number of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | Woman | 0 | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Percentage of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | 40 | [11 empty] | 0 |  |  |  | 0
28 |  |  |  | 2.1.3 (i) Number and type of activities conducted; (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. | Focus on Agricultural Cooperatives with a majority of female members | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y2 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted; |  |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
Gender Objectives. 2.2 Ensure female staff benefit from capacity- building activities related to climate- friendly agribusiness value chains
29 |  | 2.2.1 |  | 2.2.1 25% at national level and 20% at local levels women participants (aggregate basis). | Add next | Kol Prapey / Peter J. |  | Q1 Y2 – Q4 Y6 | CS 1 |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | 25% at national level of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | Woman | No BL | 25 | [11 empty] | 0 |  |  |  | 0
|  |  |  | 20% at local levels of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | Woman | No BL | 20 | [11 empty] | 0 |  |  |  | 0
Output 3: Enabling environment for climate friendly agribusiness enhanced
Gender Objectives 3.1. Institutionalize gender mainstreaming in the climate- friendly agribusiness value chains sector
30 |  | 3.1.1 |  | 3.1.1 Report prepared with clear recommendations based on detailed gender analysis of the 4 value chains. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q3 Y1 | CS 1 | MAFF | Report | 0 | 10 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
31 |  | 3.1.2 |  | 3.1.2 Key recommendations from gender analysis of 4 targeted value chains integrated in the Agribusiness Policy ( CSA Policy, Agro-Industry Policy, Contract Farming Inclusive Agribusiness Policy, Proclamation/Prakas Supporting AC’s Law, PPP-Initiative Agribusiness Policy). (Baseline: NA) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q2 Y3 | CS 1 | MAFF | Recommendation | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
32 |  | 3.1.3 |  | 3.1.3 Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; number of people trained disaggregated by sex. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; (Baseline: 0) | To be determined during the reporting period, while the session completed. | [5 empty] | Session | 0 | # | [11 empty] | 0 |  |  |  | 0
|  |  |  | Number of people trained disaggregated by sex on gender equality in climate-friendly agribusiness value chains; (Baseline:0) | To be determined during the reporting period, while the session completed. | [5 empty] | Person | 0 | # | [11 empty] | 0 |  |  |  | 0
33 |  | 3.1.4 |  | 3.1.4 MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), the AC and the WFN are aware of the GAP activities | To be determined during the reporting period. | Kol Prapey / Peter J. | Project Recoding | Q2 Y2 – Q4 Y7 | CS 1 | MAFF | % | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
Gender Objectives 3.2 Enhance access to green finance for women involved in agribusiness value chains
34 |  | 3.2.1 |  | 3.2.1 (i)Number and type of activities conducted; (ii) types of communication channels and materials used; (iii) 15 female staff in financial institutions trained in CSA lending and green finance (or 30% of total staff trained are women); (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on green finance and CSA; (v) 20,000 women provided with information on climate risk sharing instruments. | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | CS 1 | MAFF |  | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted on climate risk sharing instruments. |  |  | Project Interim Recoding |  |  |  | Activity | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (ii) Types of communication channels and materials used on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Channel | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in CSA lending are women); |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in Green finance (or 30% of total staff trained) are women; |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on Green finance;. |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on CSA; |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (v) 20,000 women provided with information on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Woman | No BL | 20000 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[9 empty] | CS# |  | Units
[9 empty] | CS 1 |  | Person
[9 empty] | CS 2 |  | Km
[9 empty] | CS 3 |  | Ha
[9 empty] | CS 4 |  | %
[9 empty] | CS 5 |  | Pond
[9 empty] | MAFF |  | System
[9 empty] | MOWRAM |  | Kg
[9 empty] | MRD |  | Tone
[9 empty] | MEF |  | Tone/Ha
[9 empty] | Other |  | Woman
Household
AC
Sample
USD
Biodigesters
Compost hut
Variety
Irrigation System
FWUC
PADC
Workshop
Policy
Standard
No.
Assessment
Staff
Household
ICT Platform
Schemes
Document
Report
Recommendation
Session
Activity
Channel
Riel
Euro
Time
Piece
Set
LS
Book
Unit
Table
Laptop
Piece
Other
Note on D7: User: Several individual meetings with Mr. Vanarath - Head of DoP office/MAFF, and Mr. Mak Many - Head of DoP/MAFF, there is neither indicators codes related, nor database system.
Note on E10: XMG: PAM, p. 52, 53.
Note on E80: XMG: PAM, p. 47-50 Gender activities/actions, 1.1.1 Involve women and Women Farmers Network (WFN) representatives actively and meaningfully in each individual event for all consultations and planning activities related to improvement and climate resiliency of critical infrastructure supported by the project. - This would mean paying attention to the following aspects: convenient time, adequate venue, information sharing with visual aids/illustrations, having female facilitators, child supervision arrangements, etc.
Note on E88: XMG: Gender activities/actions, 1.2.1 Ensure women benefit from jobs created by the project related to infrastructure construction/rehabilitation as well as operation and maintenance. - This would mean that information about such employment opportunities will be communicated through adequate channels to reach out women in the communities. - Core labor standards will be complied with (equal pay for work of equal value, no child labor) for all civil works related to the project. - Other measures that are needed will be taken (e.g. child supervision arrangements even if informal) so that interested women can grasp such opportunities.
Note on E92: XMG: Gender activities/actions, 1.2.2 Provide skills enhancement for women in infrastructure related construction/rehabilitation (e.g. masonry skills for bio-digesters construction), and operation and maintenance (e.g. small-scale irrigation schemes).
Note on E94: XMG: Gender activities/actions, 1.3.1 As part of the promotion campaigns about biodigesters and other renewable energy solutions, raise awareness among women and men in the communities about the benefits for value chain improvement/climate change but also for greater gender equality (time saving, drudgery reduction, improved health).
Note on E98: XMG: Gender activities/actions, 1.3.2 Involve women as active agents in the promotion campaigns on the use of renewable energy solutions.
Note on E103: XMG: Gender Activities/Action, 2.1.1 Involve women farmers (and the WFN) actively in the selection and multiplication of climate resilient crops varieties and build on their local knowledge in this area.
Note on E106: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (1) agricultural extension and technical capacity-building activities including those related to climate change adaptation and mitigation;
Note on E113: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (2) trainings on how to operate and maintain a range of agricultural machinery; (3), management (including leadership, negotiation) and business skills trainings. - This would mean paying special attention to the following aspects: adequate venue, timing, duration, way that invitation is being done (not to head of household as is currently being done), use of visual aids and other illustrated materials, use of female facilitators/demonstrators and extension agents, child care arrangements even if informal, etc.
Note on E117: XMG: Gender Activities/Actions, 2.1.3 Strengthen linkages between women-led and/or owned farms/enterprises* and agribusiness industry For support provided to cooperatives: preferential support will be given to agricultural cooperatives with a majority of female members. .1.4 Work with the WFN to identify context-appropriate ways to address burden of household and care work for women farmers, especially female headed households, which prevents them to increasingly participate and move up along the value chains.
Note on E126: XMG: Gender Activities/Actions, 3.1.1 At project inception, refine the gender analysis for each of the 4 targeted value chains and develop a set of clear policy and program recommendations to strengthen women farmers’ involvement along the different value chains. Ensure that capacity is built within MAFF/ Gender & Children Project Support Unit (GCPSU) for gender responsive value chain analysis and develop methodology/guidelines that can be used in future analysis.
Note on E127: XMG: Gender Activities/Actions, 3.1.2 Integrate key recommendations from the above- mentioned gender analysis of value chains and key features of the MAFF Gender Policy into the Agribusiness policy and other related documents prepared under the project. - This would also mean that gender stakeholders (MAFF GCPSU representatives, gender focal points, and WFN) participate in policy committees and meetings.
Note on E128: XMG: Gender Activities/Actions, 3.1.3 Integrate a session on gender equality in climate- friendly agribusiness value chains (based on gender analysis report mentioned above) into the training and awareness raising activities for relevant project stakeholders (i.e. relevant departments in MAFF, agricultural extension agents, local leaders and government officials, GCPSU and Gender Focal Points, and WFN).
Note on E131: XMG: Gender Activities/Actions, 3.1.4 Actively involve the MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), and the WFN and the Agricultural Cooperatives as key partners in project implementation and monitoring, especially for the GAP activities. - This also entails partnering with the WFN as facilitators/resource persons for agricultural extension and technical capacity-building, awareness-raising and information sharing targeted at farmers including provision of market information. - WFN social media pages should be used as one of the ways to disseminate information to women farmers.
Note on E133: XMG: Gender Activities/Actions, 3.2.1 Raise awareness among women farmers/ cooperative members, women-led and/or owned enterprises, and female staff in financial institutions using adequate channels about existing credit facilities, green financing including crop insurance and required formalities to access these
Note on Q23: User: Take 1 out is Ko Eurt Irrigation system in Batheay district, KPC, with reason due to PDoWRAM is repairing under the MoWRAM budget.
Note on Y8: User: Linked from DMF sheet of Physical Progress.
Note on AB8: User: Linked from DMF sheet of Physical Progress.
Note on AF8: User: Linked from DMF sheet of Physical Progress.
in JV with SBK Research and Development
Implemented by

## DMF PI Q3 Report 2021
CFAVC PROJECT's DMF PERFORMANCE INDICATORS PROGRESS REPORT (July - September 2021)
No. of indicators | M&E Indicator Codes | PAM's DMF Indicators Codes | MAFF's indicator Codes | DMF Performant Indicators | Definitions |  | Methods for Tracking | Time line | CS#/ Units | Ministries | Unit | Baseline | Target | [7 empty] | Assigned Weight (%) | Achievement in 2020 |  |  | Third Quarter DMF's Indicators Progress, Jul. - Sept 2021 |  |  |  | 9 Months Accumulative Weight Progress (%) |  | Second Six-Monthly Cumulative Progress in 2021 |  |  |  | Cummulative Progress Tracking to date in 2020 - 2021
[6 empty] | Consultants | [15 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | [6 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress
[13 empty] | Total | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 |  |  |  |  | Total Target | Total Actual Achieved | % Overall Accumulative Weight Progress | Indicators Narrative Progress | [6 empty] | Total Target | Total Actual Achieved | % Weight Progress
| OC |  |  | Outcome, Productive and resource efficient agribusiness value chains developed in project areas | [16 empty] | 100 |  | 2.0032 | 11.8291 |  | 142.635 | 5.981 |  | 554.4315 | 31.4237 |  | 2.9077 | 7.2823 |  |  | 147.5459 | 25.0923
1 | OC.1 | a. |  | By 2026 a. At least 15% increase in yields (2017 baseline: rice 2.7 tons, maize 4 tons, cassava 20 tons and mango 15 tons/ha). |  |  | a. MAFF agricultural census |  | CS 2 | MAFF | % |  | 15% | [12 empty] | MTR |  | To be reported at least after the MTR assessment, or by the end of the project completion. | MTR |  | 0 | MTR | #VALUE!
| OC.1.a.1 |  |  | Rice (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 2.7 | 3.105 | 0 | 2.7 | 2.8013 | 2.9025 | 3.0038 | 3.105 | [11 empty] | 1.4006
| OC.1.a.2 |  |  | Maize (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 4 | 4.6 | 0 | 4 | 4.15 | 4.3 | 4.45 | 4.6 | [11 empty] | 2.075
| OC.1.a.3 |  |  | Cassava (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 20 | 23 | 0 | 20 | 20.75 | 21.5 | 22.25 | 23 | [11 empty] | 10.375
| OC.1.a.3 |  |  | Mango (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 15 | 17.25 | 0 | 15 | 15.5625 | 16.125 | 16.6875 | 17.25 | [11 empty] | 7.7812
2 | OC.2 | b. |  | By 2026 b. GHG emissions reduced by 240,000 tons of CO2 (2017 baseline: 0 tons reduced due to the project). | Base on the biogas utilization calculation. |  | b. UNFCCC reports |  |  |  | Tone | 0 | 240000 | 0 | 0 | 0 | 80000 | 80000 | 80000 | [6 empty] | MTR |  | To be reported at least after the MTR assessment, or by the end of the project completion. | MTR |  | 0 | MTR | #VALUE!
3 | OC3 | c. |  | By 2026 c. At least 50 agribusinesses become more resource efficient in terms of water savings (5-10% efficiencies); energy savings (20%); and reduction in post-harvest losses (10%) (2017 baseline: 0). |  |  | c. PPMS reports |  | CS 2 | MAFF | % | 0 | 50 | 0 | 0 | 0 | 5 | 20 | 25 | [6 empty] | MTR |  | To be reported at least after the MTR assessment, or by the end of the project completion. | MTR |  | 0 | MTR | #VALUE!
| OC3.C.1 |  |  | Water saving (5-10% efficient) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [11 empty] | 1.25
| OC3.C.2 |  |  | Energy saving (20%) | Focus on the biogas utilization. |  |  |  | CS 2 | MAFF | % | 0 | 20 | 0 |  | 5 | 10 | 15 | 20 | [11 empty] | 2.5
| OC3.C.3 |  |  | Post harvesting losses (10%) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [11 empty] | 1.25
| OP.1 | 1 |  | Outputs. 1. Critical agribusiness value chain infrastructure improved and made climate resilient | [16 empty] | 65 |  |  | 7.4776 |  | 30.7874 | 2.962 |  | 188.0556 | 19.4852 |  | 1.7911 | 4.7531 |  |  | 32.5784 | 15.1927
4 | OP.1.1 | 1.a. |  | 1a. 27 irrigation and water management systems targeting 15,000 ha and 25,000 households (with at least 50,000 women) rehabilitated and made climate resilient (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 1 | MOWRAM | Woman | 0 | 27 | 2019: 0; 2020: 10; 2021: 9 | 15 | 10 | 10.06 | 1.509 | 2.25 | 0.18519 | 0.027778 | During the reporting period, several achievements were made including, --- Following up with Civil Works Construction of Trapeang Run Irrigation Subprojects, to date the construction was progressed around 95%; --- Prepared BER for the CW14.1 Kampong Cham irrigation sub-projects (CFAVC-MOWRAM-KPC-CW14.1) and reviewing of the DED and Feasibility Study Reports; --- IEE report preparations for CFAVC-MOWRAM-KPC-CW14.1; --- Supported PMU-MOWRAM on preparation of Topographical Survey for the 18 irrigation subprojects; --- The bid invitation and bid opening for conducting topographical survey for the irrigation sub-projects planned in 2021 and in 2022; --- The construction works for the Tuol Pring reservoir irrigation subproject under contract package number: MOWRAM-CFAVC-TBM-CW13.1 has been started with the progress that bush clearance was fully done; --- The feasibility study and detailed engineering design have been progressed about 20% for the Takouch irrigation subproject under contract package number MOWRAM-CFAVC-KPT-CW12.1; | 30.8523 | 4.6278 | 4.5 |  | 0% |  | 16.75 | 10.2452 | 153.7%
| OP.1.1a.1 |  |  | 27 irrigation and water management systems |  |  |  |  | CS 1 | MOWRAM | Irrigation System | 0 | 27 | 2019: 0; 2020: 10; 2021: 9; 2022: 8 |  | 10 | 17.1936 | 0.2065 | 2.25 | 0.18519 | 0.027778 |  | 30.8523 | 4.6278 | 4.5
| OP.1.1a.2 |  |  | 27 irrigation and water management systems targeting 15,000 ha |  |  |  |  | CS 1 | MOWRAM | Ha | 0 | 15000 | 2019: 0; 2020: 4050; 2021: 5333; 2022: 5617 |  | 4050 | 1399.5 | 1.866 | 1333.25 | 0 | 0 |  | 571.4286 | 1.9048 | 2666.5
| OP.1.1a.3 |  | No PP | 27 irrigation and water management systems targeting 25,000 households |  |  |  |  | CS 1 | MOWRAM | Household | 0 | 25000 | 2019: 0 |  |  |  |  | 0 | ?? | ?? |  | ?? | ?? | 0
5 | OP.1.2 | 1b. |  | 1b. 800 on-farm rainwater harvesting ponds commissioned (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 2 | MAFF | Pond | 0 | 800 | 0 | 80 | 280 | 290 | 150 | 0 |  | 5 |  | 4.13 | 0.2065 | 70 | 0 | 0 | There is no activity progress during this quarter, because it is still waiting for government decision making for which Ministry will be responsible to implement?, as well asthe 15 drips irrigation systems. | 1.125 | 0.05625 | 140 |  | 0% |  | 210 | 4.13 | 20.65%
6 | OP.1.3 | 1c. |  | 1c. At least 250 km of farm road networks upgraded to climate standards to improve connectivity of farms to cooperatives and markets (2017 baseline: 0). | Add next |  | MRD annual report |  | CS 1 | MRD | Km | 0 | 250 | 2019: 0; 2020: 67.95; 2021: 100.1; 2022: 81.95 | 15 |  | 14.05 | 2.1075 | 25.025 | 16.4277 | 2.4642 | During the reporting period, several achievement were made including, --- Twenty road subprojects under contract package numbers: CW17a-CFAVC-MRD-KP-01-2021 (Package No.5), CW17a-CFAVC-MRD-KP-02-2021 (Package No.9), CW17a-CFAVC-MRD-KP-03-2021(Package No.9), CW17a-CFAVC-MRD-KP-04-2021 (Package No.5), CW17b-CFAVC-MRD-TK01-2021(Package No.10), CW17b-CFAVC-MRD-TK02-2021(Package No.6), CW17b-CFAVC-MRD-TK03-2021(Package No.6), CW17b-CFAVC-MRD-TK04-2021(Package No.10), CW17b-CFAVC-MRD-TK05-2021(Package No.10), CW17c-CFAVC-MRD-TBK-01-2021 (Package No.7), CW17c-CFAVC-MRD-TBK-02-2021 (Package No.7), CW17c-CFAVC-MRD-TBK-03-2021 (Package No.11), CW17c-CFAVC-MRD-TBK-04-2021 (Package No.7), CW17c-CFAVC-MRD-TBK-05-2021 (Package No.11), CW17c-CFAVC-MRD-TBK-06-2021 (Package No.11), CW17c-CFAVC-MRD-TBK-07-2021 (Package No.11), CW17d-CFAVC-MRD-KC-01-2021 (Package No.12), CW17d-CFAVC-MRD-KC-02-2021 (Package No.12), CW17d-CFAVC-MRD-KPC-03-2021 (Package No.8) and CW17d-CFAVC-MRD-KC-04-2021 (Package No.8) the topographical surveys have been progressed about 80% completed. --- The feasibility studies have been progresse about 70% completed and the detailed engineering designs have been progressed about 35% completed. -- Detailed engineering design were prepared for two road subprojects planned in 2020 under contract package numbers: CW17b-CFAVC-MRD-TK3-2020 (Lot 1) and CW17b-CFAVC-MRD-TK4-2020 (Lot 2); --- For the twenty road subprojects planned in 2021, their detailed engineering design during the reporting period have been progressed 35%. | 41.8305 | 6.2746 | 50.05 |  | 0% |  | 75.075 | 30.4777 | 457.2%
7 | OP.1.4 | 1d. |  | 1d. 80 agricultural cooperatives* integrated adaptation measures in post-harvest infrastructure investments (2017 baseline: 5). | Add next | Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | AC | 5 | 80 | 0 | 20 | 35 | 25 | 0 | 0 |  | 15 |  | 15.06 | 2.259 | 8.75 | 0.40625 | 0.060937 | Activities started progress and in tracking including, - Completed location selection; - Completed site survey; - Tender file completed; - Procurement completed; - Construction is started. | 40.2719 | 6.0408 | 17.5 |  | 0% |  | 26.25 | 15.4663 | 232%
8 | OP.1.5 | 1e. |  | 1e. Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples (2017 baseline: 700) and generate service income more than $75,000 (2017 baseline: $0). | Add next | Vong Sophorn/ Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | [10 empty] | 5 |  | 16 | 0.8 |  | 4.1556 | 0.20778 | Activity started in progress and on tracking including, - Prepared training program; - Re-assessed Lab-equipment; - Re-designed on lab-renovation drawing. | 27.5556 | 1.3778 | 0 |  | #DIV/0! |  | 0 | 20.1556 | #DIV/0!
| OP.1.5.1e.1 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples |  |  | PPMS annual reports |  | CS 2 | MAFF | Sample | 700 | 1500 | 0 | 0 | 0 | 900 | 1100 | 1500 | [5 empty] | 0 | [5 empty] | 0
| OP.1.5.1e.2 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded generate service income more than $75,000 |  |  | PPMS annual reports |  | CS 2 | MAFF | USD | 0 | 75000 | 0 | 0 | 0 | 45000 | 55000 | 75000 | [5 empty] | 0 | [5 empty] | 0
9 | OP.1.6 | 1f. |  | 1f. 12,000 additional biodigesters and 6,000 compost huts made operational, benefiting at least 80,000 persons, including at least 50% women, due to better household air quality (2017 baseline beneficiaries: 11,468 persons, including 5,721 women). | Add next | Phuong Dara | PPMS annual reports |  | CS 2 | MAFF | [16 empty] | 0.20139 | Activity started in progress and on tracking including, - Identify new eligible clients to purchasing biodigester planned in 2021; - Procurement for 500 biodigesters are still reviewing and comments from ADB. |  | 1.108 | 0 |  | #DIV/0!
| OP.1.6.1f.1 | 1f.1 |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Biodigesters | No BL | 12000 | 0 | 500 | 1250 | 4000 | 3500 | 1500 |  | 4 |  | 7.07 | 0.2828 | 312.5 | 0.18333 | 0.0073333 |  | 3.8564 | 0.15426 | 625 |  |  |  | 937.5 | 7.2533 | 29.01%
|  |  |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 80000 | 0 | 3333.3333 | 8333.3333 | 26666.6667 | 23333.3333 | 10000 | [5 empty] | 2083.3333 | [5 empty] | 4166.6667
| OP.1.6.1f.2 | 1f.2 |  | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Compost hut | No BL | 6000 | 0 | 250 | 625 | 1600 | 1600 | 1300 |  | 4 |  | 7.47 | 0.2988 | 156.25 | 0.27333 | 0.010933 | Activity in progress and on tracking including, - Identify new eligible clients to purchasing compost huts planned in 2021; - Procurement for 250 compost huts are still reviewing and comments from ADB. | 5.1215 | 0.20486 | 312.5 |  |  |  | 468.75 | 7.7433 | 30.97%
|  |  | No PP | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 833.3333 | 5000 | 5333.3333 | 5333.3333 | 4333.3333 | [5 empty] | 1250 | [5 empty] | 2500
| OP.1.6.1f.3 | 1f.3 |  | 20,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  | Phuong Dara | Physical Progress |  | CS 2 | MAFF |  | No BL | 20000 | 0 | 2500 | 5000 | 9500 | 3000 | 0 |  | 2 |  | 0.7 | 0.014 | 1250 | 9.156 | 0.18312 | Activity in progress and on tracking including, -Mentoring and coaching; - Publication of promotion and marketing materials; - Mentoring/coaching extension; - Training and capacity building; - Promotion and marketing; - Leaflets and information sharing. | 37.4424 | 0.74885 | 2500 |  |  |  | 3750 | 9.856 | 19.71%
| OP.1.6.1f.3 | 1f.3.1 | No PP | 20,000 people trained on biodigester use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 1250 | 2500 | 4750 | 1500 | 0 | [5 empty] | 625 | [5 empty] | 1250
| OP.1.6.1f.8 | 1f.3.2 | No PP | 20,000 people trained on compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Woman | 11468 | 20000 | 0 | 1250 | 2500 | 4750 | 1500 | 0 | [5 empty] | 625 | [5 empty] | 1250
| OP.2 | 2 |  | Outputs. 2. Climate smart agriculture and agribusiness promoted | [16 empty] | 20 |  | 2.0032 | 2.9565 |  | 44.7976 | 1.6064 |  | 206.2509 | 8.5545 | [5 empty] | 46.8008 | 4.5629
10 | OP.2.1 | 2a. |  | 2a. Three additional climate resilient varieties of rice and maize released (2017 baseline: 0). | Add next | Sophath Heng | PPMS annual reports |  | CS 2 | MAFF | Variety | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  | 5 |  | 6.25 | 0.3125 | 0 | 1.6042 | 0.079848 | This indicator was slightly started yet for the three varieties releazed and it is still waiting for signing contract with IRRI and its progress was narratively described by its respective sub-indicators below, | 8.7274 | 0.59679 | 0 |  | #DIV/0! |  | 0 | 7.8542 | #DIV/0!
| OP.2.1.2a.1 |  |  | Three additional climate resilient varieties of rice released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | [5 empty] | 0 |  | 0 | This sub-indicator was not started yet for the three varieties releazed and it is still waiting for signing contract with IRRI. Further, there some demenstrations were conducted including, --- 90 rice seed demo plots selected; --- 10 cassava seed demo plots selected; |  | 0 | 0
| OP.2.1.2a.2 |  |  | Three additional climate resilient varieties of maize released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0 |  | 0 | This sub-indicator was not started yet for the three varieties releazed and it is still waiting for signing contract with IRRI. |  | 0 | 0
11 | OP.2.2 | 2b. |  | 2b. 40,000 farmers (of whom 16,000 are women) trained in CSA and agribusiness development skills, of which 50% are SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0). | Add next | Pon Han | PPMS annual reports |  | CS 2 | MAFF |  | No BL | 40000 | 0 | 2500 | 19172 | 9500 | 9000 | 9000 |  | 5 |  | 16.98 | 0.849 | 4793 | 1.4533 | 1.0024 | This indicator was progress include, - Completing TOT training on CSA, SRP, CamGAP, BDS, and Farm mechanization, and conservation agriculture; - Farmer training program and schedule preparation. More specific by each its sub-indicators were below, | 35.2445 | 1.9076 | 9586 |  | 0% |  | 14379 | 18.4333 | 185.1%
| OP.2.2.2b.1 |  |  | farmers (of whom 16,000 are women) trained in CSA | [6 empty] | Person | No BL | 20000 | 0 | 501 | 5800 | 5000 | 5000 | 4499 | [5 empty] | 1450 |  | 0.11 | Activity in progress and on tracking including, - Prepared training program and scheduling; - Reviewed training materials. |  | 0.83292 | 2900
| OP.2.2.2b.2 |  | No PP | farmers (of whom 16,000 are women) trained in Agribusiness Development Skills (ADS) | [6 empty] | Person | No BL | 20000 | 0 | 250 | 7893 | 4937.5 | 4937.5 | 4937.5 | [5 empty] | 1973.25 |  |  | Activity in progress and on tracking including, - Reviewed training materials; - Prepared training program and scheduling. |  |  | 3946.5
| OP.2.2.2b.3 |  |  | farmers are trained on SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0) | [6 empty] | Person | 0 | 20000 | 0 | 875 | 5250 | 4781.25 | 4781.25 | 4781.25 | [5 empty] | 1312.5 |  | 0.302 | Activity in progress and on tracking including, - Prepared training program and scheduling; - Reviewed training materials. |  | 0.402 | 2625
|  |  | Add more | farmers are trained on CAMGAP compliant | [7 empty] | No BL | 500 | 0 | 250 | 120 | 0 | 0 | 0 | [5 empty] | 30 |  | 0.6 | Activity in progress and on tracking including, - Prepared training program and scheduling; - Reviewed training materials. |  | 1.29 | 60
|  |  | Add more | 20% of total 40,000 farmers are trained on Agricultural farm Machinery | [7 empty] | No BL | 8000 | 0 | 496 | 109 | 2000 | 2000 | 1128 | [5 empty] | 27.25 |  | 0.080526 | Activity in progress and on tracking including, - Reviewed training materials; - Prepared training program and scheduling. |  | 0.27789 | 54.5
12 | OP.2.3 | 2c. |  | 2c. 27 FWUCs/FWUGs made operational and 500 FWUC/FWUG members (of which 30% women) developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). | Add next | Soeur Sophorn | PPMS annual reports |  | CS 2 | MAFF | FWUC | 0 | [8 empty] | 6 | [5 empty] | 0.10749 | This indicator was greadually progressed with its respective sub-indicators narrative description as below, |  | 1.7025 | 0 |  | #DIV/0!
| OP.2.3.2c.1 | 2C1 |  | 27 FWUCs/FWUGs made operational and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM |  | Soeur Sophorn - CS2 |  |  | CS 2 | MAFF | FWUC | 0 | 27 | 0 | 10 | 18 | 9 | 0 | 0 |  | 3 |  | 12.1 | 0.363 | 4.5 | 18.8401 | 0.17297 | This sub-indicator progress and in tracking in term of, - Village meeting for FWUC establishment; - Villagers meeting for FWUC establishment and FWUC committee selection; - Established 3 FWUCs in Tboung Khmum province and registered. | 31.9207 | 2.088 | 9 |  |  |  | 13.5 | 30.9401 | 53.6%
| OP.2.3.2c.2 | 2C2 |  | 500 FWUC/FWUG members developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 500 | 0 | 100 | 200 | 100 | 100 | 100 |  | 3 |  | 10 | 0.3 | 50 | 13 | 0.042 | This sub-indicator in progress and tracking including, - Preparation training materials on operation; - Preparation of training materials on maintenance. | 17.9 | 1.317 | 100 |  |  |  | 150 | 23 | 34.2%
13 | OP.2.4 | 2d. |  | 2d. 4 provincial agricultural development centers (PADC) and 4 Mechnization engineering workshops (MEW) made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). | Add next | Phai Sok Heng | PPMS annual reports |  | CS 2 | MAFF |  | 0 | 8 |  | 6 | 6 | 2 | 0 | 0 | [5 empty] | 1.5 | 0.23187 | 0.15458 | This indicator was gradually progreesed, which its respective sub-indicators progresses have been narratively described as below, | #VALUE! | 1.3226 | 3 |  | 0%
| OP.2.4.2d.1 | 2d1 |  | 4 provincial agricultural development centers made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | PADC | 0 | 4 | 2019: 0; 2020: 3; 2021: 4; 2022: 1 | 2 |  | 26.3 | 0.526 | 0.75 | 5.575 | 0.11733 | The 4 PADCs were completed its procurement, the contractor won the bidding was Hout Chheoun Co.,Ltd and the contractor has been introduced to the 4 PDAFF's directors target provinces, as well as the intoroducion to the construction sides. It does hope that the 4 PADCs to start its construction in mid October 2021, while the Khmer Traditional Pchum Bin celebration is completed in early October 2021. | 51.0417 | 1.2438 | 1.5 |  |  |  | 2.25 | 31.875 | 64.33%
| OP.2.4.2d.2 | 2d2 |  | 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Workshop | 0 | 4 | 2019: 0; 2020: 3; 2021: 4; 2022: 1 | 2 |  | 30.3 | 0.606 | 0.75 | 4.325 | 0.19183 | The 4 MEW were completed its procurement, the contractor won the bidding was Hout Chheoun Co.,Ltd and the contractor has been introduced to the 4 PDAFF's directors target provinces, as well as the intoroducion to the construction sides. It does hope that the 4 MEWs to start its construction in mid October 2021, while the Khmer Traditional Pchum Bin celebration is completed in early October 2021. | 61.4167 | 1.4013 | 1.5 |  |  |  | 2.25 | 34.625 | 79.78%
| OP.3 | 3 |  | 3. Enabling environment for climate friendly agribusiness enhanced | [16 empty] | 15 |  |  | 1.395 |  | 67.05 | 1.4125 |  | 160.125 | 3.384 |  | 1.1167 | 2.5292 |  |  | 68.1667 | 5.3367
14 | OP.3.1.a | 3a. |  | 3a. Climate-smart and gender-responsive agribusiness policy for target commodities, including a PPP framework focusing on agribusinesses formulated (2017 baseline: 0).** | Add next | Hoeung Hun / Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | Policy |  | 4 | 0 | 0 | 1.3 | 1.3 | 1 | 0.3 |  | 2 |  | 19 | 0.38 | 0.325 | 20.75 | 0.415 | This indicator was gradually progressed with its respective narratively progress description as below, | 58.075 | 1.1615 | 0.65 |  | 0% |  | 0.975 | 39.75 | 79.5%
| OP.3.1.3a.1 |  |  | 1. Draft of Climate Smart and Gender Responsive Agrib-policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 2019: 0; 2021: 0.4; 2022: 0.4; 2023: 0.1 |  |  |  |  | 0.1 |  | 0.0825 | This sub-indicator is in progress and on tracking including the TOR development and reviewed by DTL, and Department of Planning and Statistic team, MAFF. |  | 0.21925 | 0.2
| OP.3.1.3a.2 |  |  | 2. Draft CSA policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.0425 | This sub-indicator is in progress and on tracking including the TOR drafted by DTL and Department of Planning and Statistic team, MAFF. |  | 0.105 | 0.15
| OP.3.1.3a.3 |  |  | 3. Draft guidance manual for climate neutrality and adaption for agribusiness operation; and 4. Draft IDP strategy for climate friendly agribusiness |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.04 | This sub-indicators are in progress and on tracking including the TOR drafted by DTL, and Department of Planning and Statistic, MAFF, as well as the National Standards and policy of biodigester. |  | 0.1025 | 0.15
| OP.3.1.3a.4 |  |  | 5. Draft PPP framework formulated |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.0425 | This sub-indicator is in progress and on tracking including the draft PPP framework development, which reviewed by DTL, and Department of Planning and Statistic team, MAFF, as well as the Conduct Feasibility study on crop commoditie. |  | 0.154 | 0.15
15 | OP.3.2 | 3b. |  | 3b. CAMGAP for tropical fruit and organic fertilizers endorsed as national standard for tropical fruit and organic fertilizers (2017 baseline: 0). | Add next | Hoeung Hun / Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | Standard | 0 | 2 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2 |  | 2 |  | 14.5 | 0.29 | 0.15 | 7.15 | 0.143 | This indicator was gradually progressed with its respective narratively progress description as below, | 16.65 | 0.333 | 0.3 |  | 0% |  | 0.45 | 21.65 | 43.3%
| OP.3.3b.1 |  |  | CAMGAP for tropical fruit endorsed as national standard for tropical fruit (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0 | This sub-indicator was in progress and on tracking including the r​​​​​​​​eviewed relevant documents, and existing CamGAP standard for tropical fruit. |  | 0 | 0.15
| OP.3.3b.2 |  |  | CAMGAP for organic fertilizers endorsed as national standard for organic fertilizers (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.0255 | This sub-indicator was in progress and on tracking including the r​​​​​​​​eviewed relevant documents, and existing standard for organic fertilizer. |  | 0.0405 | 0.15
16 | OP.3.3 | 3c. |  | 3c. 50 staff, including 30% women, from financial institutions trained in CSA and green finance (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF | Person | 0 | 50 | 0 | 0 | 25 | 20 | 15 | 0 |  | 2 |  | 11.5 | 0.23 | 6.25 | 12.2 | 0.244 | This indicator was in progress and on tracking including, - Reviewed relevant existing documents for both sub-indicators; - Drafting training materials for both sub-indicators. | 42.2 | 0.844 | 12.5 |  | 0% |  | 18.75 | 23.7 | 47.4%
| OP.3.3C.1 |  |  | 50 staff, including 30% women, from financial institutions trained in CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 12.5 | 10 | 7.5 | 0 | [5 empty] | 3.125 |  | 0 | This sub-indicator was in progress and on tracking including, - Reviewed relevant existing document; - Drafting training material. |  | 0 | 6.25
| OP.3.3C.2 |  |  | 50 staff, including 30% women, from financial institutions trained in Green finance (2017 baseline:0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 12.5 | 10 | 7.5 | 0 | [5 empty] | 3.125 |  | 0 | This sub-indicator was in progress and on tracking including, - Reviewed relevant existing document; - Drafting training material. |  | 0 | 6.25
17 | OP.3.4 | 3d. |  | 3d. 30 agribusinesses, including 30% women-led and/or owned,*** trained on green finance and CSA (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF |  |  | 30 | 0 | 0 | 10 | 10 | 10 | 0 |  | 2 |  | 5.4 | 0.108 | 2.5 | 9.2 | 0.184 | This indicator was in progress and on tracking including, - Reviewed relevant existing documents for both sub-indicators; - Drafting training materials for both sub-indicators. | 12.8 | 0.256 | 5 |  | 0% |  | 7.5 | 14.6 | 29.2%
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on Green finance (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 1.25 |  | 0 | This sub-indicator was in progress and on tracking including, - Reviewed relevant existing document; - Drafting training material. |  | 0 | 2.5
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Woman | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 1.25 |  | 0 | This sub-indicator was in progress and on tracking including, - Reviewed relevant existing document; - Drafting training material. |  | 0 | 2.5
18 | OP.3.5 | 3e. |  | 3e. 20,000 households, including 20,000 women, provided with information on climate risk sharing instruments (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | Household | 0 | 20000 | 0 | 0 | 10000 | 6000 | 6000 | 2500 |  | 2 |  | 4.5 | 0.09 | 2500 | 10.6 | 0.212 | This sub-indicator does not start yet, and it is still waiting for the arrival of the specialist. | 11.5 | 0.23 | 5000 |  | 0% |  | 7500 | 15.1 | 30.2%
19 | OP.3.6 | 3f. |  | 3f. ICT platform for climate friendly agribusiness established in Kampong Cham province (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | ICT Platform | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 2 |  | 4.5 | 0.09 | 0.075 | 0 | 0 | The EoI for recruitment of the consulting firms were floated in the ADB website and twelve consulting firms submitted their EoIs. The submitted EoIs were under the process of bid evaluation. | 0.75 | 0.015 | 0.15 |  | 0% |  | 0.225 | 4.5 | 9%
| OP.3.7 | 3g | No DMF | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | Add next | [5 empty] | ICT Platform |  | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 3 |  | 6.9 | 0.207 | 0.075 | 7.15 | 0.2145 |  | 18.15 | 0.5445
[27 empty] | #DIV/0! |  |  |  | 0 |  | #DIV/0!
GENDER AND SOCIAL DIMENSIONS
Output 1: Critical agribusiness value chain infrastructure improved and made climate resilient
Gender Objectives. 1.1 Ensure critical agribusiness value chain infrastructure is responsive to the needs of women and men
20 |  | 1.1.1 |  | 1.1.1 (i) Women are 40% of participants– aggregate basis (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3; 30% female participation in similar activities currently); (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y4 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  | 1.1.1.i |  | (i) Women are 40% of participants– aggregate basis (point of reference: female population: |  |  |  |  | CS 1 | MAFF | % | No BL | 40 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Women are 54% of participants in subproject 1; |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (i) Women are 47% of participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (i) Women are 48% of participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (i) Women are 30% female participation in similar activities currently); |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 | [5 empty] | 0
|  | 1.1.1.ii |  | (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems |  |  |  |  | CS 1 | MAFF | Person | No BL | 50000 | [11 empty] | 0 | [5 empty] | 0
Gender Objectives. 1.2. Enhance income generating opportunities for women
21 |  | 1.2.1 |  | 1.2.1 At least 25% of workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y6 | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by skilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by unskilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | [12 empty] | 0 | [5 empty] | 0
|  |  |  | Workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) |  |  |  |  | CS 1 | MAFF | % | No BL | 17-46 | [11 empty] | 0 | [5 empty] | 0
22 |  | 1.2.2 |  | 1.2.2 At least 30% women FWUC members developed capacity to operate and maintain irrigation schemes. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
Gender Objectives. 1.3 Increase the uptake of biodigesters
23 |  | 1.3.1 |  | 1.3.1 At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y4 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 5721 | 40000 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 | [5 empty] | 0
24 |  | 1.3.2 |  | 1.3.2 Number and percentage of women active agents. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y4 | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | Number of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 | [5 empty] | 0
|  |  |  | Percentage of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 | [5 empty] | 0
Output 2: Climate smart agriculture and agribusiness promoted
Gender Objectives. 2.1 Strengthen women farmers’ (individual and member of cooperatives) involvement along climate- friendly agribusiness value chains
25 |  | 2.1.1 |  | 2.1.1 Number and % of women farmers involved | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | Number of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 | [5 empty] | 0
|  |  |  | % of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 | [5 empty] | 0
26 |  | 2.1.2 |  | For 2.1.2 (1) and (3): Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA and agribusiness development skills (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3 with almost all of them farming; 30% female participation in similar activities currently). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | [16 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA . |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in Agribusiness Development Skills |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | Women are 54% of total participants in subproject 1 |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | Women are 47% of total participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | Women are 48% of total participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | 30% female participation in similar activities currently |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 | [5 empty] | 0
27 |  |  |  | For 2.1.2 (2): (i) Number and percentage of women farmers trained in each event; (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y5 | [16 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Number of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | Woman | 0 | ? | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (i) Percentage of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | ? | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | 40 | [11 empty] | 0 | [5 empty] | 0
28 |  |  |  | 2.1.3 (i) Number and type of activities conducted; (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. | Focus on Agricultural Cooperatives with a majority of female members | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y2 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted; |  |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 | [5 empty] | 0
Gender Objectives. 2.2 Ensure female staff benefit from capacity- building activities related to climate- friendly agribusiness value chains
29 |  | 2.2.1 |  | 2.2.1 25% at national level and 20% at local levels women participants (aggregate basis). | Add next | Kol Prapey / Peter J. |  | Q1 Y2 – Q4 Y6 | CS 1 |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | 25% at national level of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | Woman | No BL | 25 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | 20% at local levels of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | Woman | No BL | 20 | [11 empty] | 0 | [5 empty] | 0
Output 3: Enabling environment for climate friendly agribusiness enhanced
Gender Objectives 3.1. Institutionalize gender mainstreaming in the climate- friendly agribusiness value chains sector
30 |  | 3.1.1 |  | 3.1.1 Report prepared with clear recommendations based on detailed gender analysis of the 4 value chains. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q3 Y1 | CS 1 | MAFF | Report | 0 | 10 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
31 |  | 3.1.2 |  | 3.1.2 Key recommendations from gender analysis of 4 targeted value chains integrated in the Agribusiness Policy ( CSA Policy, Agro-Industry Policy, Contract Farming Inclusive Agribusiness Policy, Proclamation/Prakas Supporting AC’s Law, PPP-Initiative Agribusiness Policy). (Baseline: NA) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q2 Y3 | CS 1 | MAFF | Recommendation | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
32 |  | 3.1.3 |  | 3.1.3 Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; number of people trained disaggregated by sex. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; (Baseline: 0) | To be determined during the reporting period, while the session completed. | [5 empty] | Session | 0 | # | [11 empty] | 0 | [5 empty] | 0
|  |  |  | Number of people trained disaggregated by sex on gender equality in climate-friendly agribusiness value chains; (Baseline:0) | To be determined during the reporting period, while the session completed. | [5 empty] | Person | 0 | # | [11 empty] | 0 | [5 empty] | 0
33 |  | 3.1.4 |  | 3.1.4 MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), the AC and the WFN are aware of the GAP activities | To be determined during the reporting period. | Kol Prapey / Peter J. | Project Recoding | Q2 Y2 – Q4 Y7 | CS 1 | MAFF | % | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
Gender Objectives 3.2 Enhance access to green finance for women involved in agribusiness value chains
34 |  | 3.2.1 |  | 3.2.1 (i)Number and type of activities conducted; (ii) types of communication channels and materials used; (iii) 15 female staff in financial institutions trained in CSA lending and green finance (or 30% of total staff trained are women); (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on green finance and CSA; (v) 20,000 women provided with information on climate risk sharing instruments. | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | CS 1 | MAFF |  | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted on climate risk sharing instruments. |  |  | Project Interim Recoding |  |  |  | Activity | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (ii) Types of communication channels and materials used on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Channel | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in CSA lending are women); |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in Green finance (or 30% of total staff trained) are women; |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on Green finance;. |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on CSA; |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 | [5 empty] | 0
|  |  |  | (v) 20,000 women provided with information on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Woman | No BL | 20000 | [11 empty] | 0 |  | #DIV/0! |  |  |  | 0 |  | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[27 empty] | #DIV/0! | [5 empty] | #DIV/0!
[9 empty] | CS# |  | Units
[9 empty] | CS 1 |  | Person
[9 empty] | CS 2 |  | Km
[9 empty] | CS 3 |  | Ha
[9 empty] | CS 4 |  | %
[9 empty] | CS 5 |  | Pond
[9 empty] | MAFF |  | System
[9 empty] | MOWRAM |  | Kg
[9 empty] | MRD |  | Tone
[9 empty] | MEF |  | Tone/Ha
[9 empty] | Other |  | Woman
Household
AC
Sample
USD
Biodigesters
Compost hut
Variety
Irrigation System
FWUC
PADC
Workshop
Policy
Standard
No.
Assessment
Staff
Household
ICT Platform
Schemes
Document
Report
Recommendation
Session
Activity
Channel
Riel
Euro
Time
Piece
Set
LS
Book
Unit
Table
Laptop
Piece
Other
Note on D7: User: Several individual meetings with Mr. Vanarath - Head of DoP office/MAFF, and Mr. Mak Many - Head of DoP/MAFF, there is neither indicators codes related, nor database system.
Note on E10: XMG: PAM, p. 52, 53.
Note on E57: User: Noted that the previous mentioned as the sub-indicators are not in PAM but the belows are in PAM, which must be tracking including, 1- Draft of Climate Smart and Gender Responsive Agrib-policy 2- Draft of CSA policy 3- Draft of guidance manual for climate neutrality and adaption for agribusiness operation 4- Draft of IDP strategy for climate friendly agribusiness 5- Draft PPP framework formulated 6- National Standards and policy of biodigester (Mentioned by Mr. Hoeung Hun)
Note on E78: XMG: PAM, p. 47-50 Gender activities/actions, 1.1.1 Involve women and Women Farmers Network (WFN) representatives actively and meaningfully in each individual event for all consultations and planning activities related to improvement and climate resiliency of critical infrastructure supported by the project. - This would mean paying attention to the following aspects: convenient time, adequate venue, information sharing with visual aids/illustrations, having female facilitators, child supervision arrangements, etc.
Note on E86: XMG: Gender activities/actions, 1.2.1 Ensure women benefit from jobs created by the project related to infrastructure construction/rehabilitation as well as operation and maintenance. - This would mean that information about such employment opportunities will be communicated through adequate channels to reach out women in the communities. - Core labor standards will be complied with (equal pay for work of equal value, no child labor) for all civil works related to the project. - Other measures that are needed will be taken (e.g. child supervision arrangements even if informal) so that interested women can grasp such opportunities.
Note on E90: XMG: Gender activities/actions, 1.2.2 Provide skills enhancement for women in infrastructure related construction/rehabilitation (e.g. masonry skills for bio-digesters construction), and operation and maintenance (e.g. small-scale irrigation schemes).
Note on E92: XMG: Gender activities/actions, 1.3.1 As part of the promotion campaigns about biodigesters and other renewable energy solutions, raise awareness among women and men in the communities about the benefits for value chain improvement/climate change but also for greater gender equality (time saving, drudgery reduction, improved health).
Note on E96: XMG: Gender activities/actions, 1.3.2 Involve women as active agents in the promotion campaigns on the use of renewable energy solutions.
Note on E101: XMG: Gender Activities/Action, 2.1.1 Involve women farmers (and the WFN) actively in the selection and multiplication of climate resilient crops varieties and build on their local knowledge in this area.
Note on E104: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (1) agricultural extension and technical capacity-building activities including those related to climate change adaptation and mitigation;
Note on E111: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (2) trainings on how to operate and maintain a range of agricultural machinery; (3), management (including leadership, negotiation) and business skills trainings. - This would mean paying special attention to the following aspects: adequate venue, timing, duration, way that invitation is being done (not to head of household as is currently being done), use of visual aids and other illustrated materials, use of female facilitators/demonstrators and extension agents, child care arrangements even if informal, etc.
Note on E115: XMG: Gender Activities/Actions, 2.1.3 Strengthen linkages between women-led and/or owned farms/enterprises* and agribusiness industry For support provided to cooperatives: preferential support will be given to agricultural cooperatives with a majority of female members. .1.4 Work with the WFN to identify context-appropriate ways to address burden of household and care work for women farmers, especially female headed households, which prevents them to increasingly participate and move up along the value chains.
Note on E124: XMG: Gender Activities/Actions, 3.1.1 At project inception, refine the gender analysis for each of the 4 targeted value chains and develop a set of clear policy and program recommendations to strengthen women farmers’ involvement along the different value chains. Ensure that capacity is built within MAFF/ Gender & Children Project Support Unit (GCPSU) for gender responsive value chain analysis and develop methodology/guidelines that can be used in future analysis.
Note on E125: XMG: Gender Activities/Actions, 3.1.2 Integrate key recommendations from the above- mentioned gender analysis of value chains and key features of the MAFF Gender Policy into the Agribusiness policy and other related documents prepared under the project. - This would also mean that gender stakeholders (MAFF GCPSU representatives, gender focal points, and WFN) participate in policy committees and meetings.
Note on E126: XMG: Gender Activities/Actions, 3.1.3 Integrate a session on gender equality in climate- friendly agribusiness value chains (based on gender analysis report mentioned above) into the training and awareness raising activities for relevant project stakeholders (i.e. relevant departments in MAFF, agricultural extension agents, local leaders and government officials, GCPSU and Gender Focal Points, and WFN).
Note on E129: XMG: Gender Activities/Actions, 3.1.4 Actively involve the MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), and the WFN and the Agricultural Cooperatives as key partners in project implementation and monitoring, especially for the GAP activities. - This also entails partnering with the WFN as facilitators/resource persons for agricultural extension and technical capacity-building, awareness-raising and information sharing targeted at farmers including provision of market information. - WFN social media pages should be used as one of the ways to disseminate information to women farmers.
Note on E131: XMG: Gender Activities/Actions, 3.2.1 Raise awareness among women farmers/ cooperative members, women-led and/or owned enterprises, and female staff in financial institutions using adequate channels about existing credit facilities, green financing including crop insurance and required formalities to access these
Note on L42: User: Planned in 2021, - 90 demos for rice - 10 demos for cassava - 30 Field days
Note on Q23: User: Take 1 out is Ko Eurt Irrigation system in Batheay district, KPC, with reason due to PDoWRAM is repairing under the MoWRAM budget.
Note on Q33: User: Previous 2,500
Note on Q35: User: Previous 1250
Note on Q36: User: Previous 2,083
Note on Q37: User: Previous 5000
Note on Q44: User: Previous10,000
Note on Q45: User: Previous 5,000
Note on Q46: User: Previous 4938
Note on Q47: User: Previous 4,781
Note on Q48: User: Previous 250
Note on Q49: User: Previous 2,376
Note on Q51: User: Previous is 8
Note on Q52: User: Previous is 100
Note on Q65: User: Previous 15
Note on Q71: User: Previous 5,500
Note on Y8: User: Linked from DMF sheet of Physical Progress.
Note on AB9: User: Linked from DMF sheet of Physical Progress.
Note on AH8: User: Linked from DMF sheet of Physical Progress.
in JV with SBK Research and Development
Implemented by

## DMF PI Q4 Report 2021
CFAVC PROJECT's DMF PERFORMANCE INDICATORS PROGRESS REPORT (Oct - December 2021)
No. of indicators | M&E Indicator Codes | PAM's DMF Indicators Codes | MAFF's indicator Codes | DMF Performant Indicators | Definitions |  | Methods for Tracking | Time line | CS#/ Units | Ministries | Unit | Baseline | Target | [7 empty] | Assigned Weight (%) | Achievement in 2020 |  |  | Fourth Quarter DMF's Indicators Progress, Oct. - Dec 2021 |  |  |  | S2 Accumulative Weight Progress (%) |  | 12 Months Accumulative Weight Progress (%) | Second Six-Monthly Cumulative Progress in 2021 |  |  |  | Cummulative Progress Tracking to date in 2020 - 2021
[6 empty] | Consultants | [15 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | [7 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress
[13 empty] | Total | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 |  |  |  |  | Total Target | Total Actual Achieved | % Overall Accumulative Weight Progress | Indicators Narrative Progress | [7 empty] | Total Target | Total Actual Achieved | % Weight Progress
| OC |  |  | Outcome, Productive and resource efficient agribusiness value chains developed in project areas | [16 empty] | 100 |  | 2.0032 | 11.8291 |  | 142.635 | 4.4694 |  | 554.4315 | 10.4504 | 35.8932 |  | 2.9077 | 7.2823 |  |  | 147.5459 | 23.5808
1 | OC.1 | a. |  | By 2026 a. At least 15% increase in yields (2017 baseline: rice 2.7 tons, maize 4 tons, cassava 20 tons and mango 15 tons/ha). |  |  | a. MAFF agricultural census |  | CS 2 | MAFF | % |  | 15% | [12 empty] | MTR |  |  | MTR |  |  | 0 | MTR | #VALUE!
| OC.1.a.1 |  |  | Rice (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 2.7 | 3.105 | 0 | 2.7 | 2.8013 | 2.9025 | 3.0038 | 3.105 | [12 empty] | 1.4006
| OC.1.a.2 |  |  | Maize (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 4 | 4.6 | 0 | 4 | 4.15 | 4.3 | 4.45 | 4.6 | [12 empty] | 2.075
| OC.1.a.3 |  |  | Cassava (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 20 | 23 | 0 | 20 | 20.75 | 21.5 | 22.25 | 23 | [12 empty] | 10.375
| OC.1.a.3 |  |  | Mango (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 15 | 17.25 | 0 | 15 | 15.5625 | 16.125 | 16.6875 | 17.25 | [12 empty] | 7.7812
2 | OC.2 | b. |  | By 2026 b. GHG emissions reduced by 240,000 tons of CO2 (2017 baseline: 0 tons reduced due to the project). | Base on the biogas utilization calculation. |  | b. UNFCCC reports |  |  |  | Tone | 0 | 240000 | 0 | 0 | 0 | 80000 | 80000 | 80000 | [6 empty] | MTR |  |  | MTR |  |  | 0 | MTR | #VALUE!
3 | OC3 | c. |  | By 2026 c. At least 50 agribusinesses become more resource efficient in terms of water savings (5-10% efficiencies); energy savings (20%); and reduction in post-harvest losses (10%) (2017 baseline: 0). |  |  | c. PPMS reports |  | CS 2 | MAFF | % | 0 | 50 | 0 | 0 | 0 | 5 | 20 | 25 | [6 empty] | MTR |  |  | MTR |  |  | 0 | MTR | #VALUE!
| OC3.C.1 |  |  | Water saving (5-10% efficient) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [12 empty] | 1.25
| OC3.C.2 |  |  | Energy saving (20%) | Focus on the biogas utilization. |  |  |  | CS 2 | MAFF | % | 0 | 20 | 0 |  | 5 | 10 | 15 | 20 | [12 empty] | 2.5
| OC3.C.3 |  |  | Post harvesting losses (10%) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [12 empty] | 1.25
| OP.1 | 1 |  | Outputs. 1. Critical agribusiness value chain infrastructure improved and made climate resilient | [16 empty] | 65 |  |  | 7.4776 |  | 30.7874 | 1.7911 |  | 188.0556 | 4.7531 | 21.2763 |  | 1.7911 | 4.7531 |  |  | 32.5784 | 14.0218
4 | OP.1.1 | 1.a. |  | 1a. 27 irrigation and water management systems targeting 15,000 ha and 25,000 households (with at least 50,000 women) rehabilitated and made climate resilient (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 1 | MOWRAM | Woman | 0 | 27 | 2019: 0; 2020: 10; 2021: 9 | 15 | 10 | 10.06 | 1.509 | 2.25 | 0.18519 | 0 |  | 30.8523 | 0.027778 | 4.6278 | 4.5 |  | 0% |  | 16.75 | 10.2452 | 150.9%
| OP.1.1a.1 |  |  | 27 irrigation and water management systems |  |  |  |  | CS 1 | MOWRAM | Irrigation System | 0 | 27 | 2019: 0; 2020: 10; 2021: 9; 2022: 8 |  | 10 | 17.1936 | 0.2065 | 2.25 | 0.18519 | 0 |  | 30.8523 | 0.027778 | 4.6278 | 4.5
| OP.1.1a.2 |  |  | 27 irrigation and water management systems targeting 15,000 ha |  |  |  |  | CS 1 | MOWRAM | Ha | 0 | 15000 | 2019: 0; 2020: 4050; 2021: 5333; 2022: 5617 |  | 4050 | 1399.5 | 1.866 | 1333.25 | 0 | 0 |  | 571.4286 | 0 | 0.019048 | 2666.5
| OP.1.1a.3 |  | No PP | 27 irrigation and water management systems targeting 25,000 households |  |  |  |  | CS 1 | MOWRAM | Household | 0 | 25000 | 2019: 0 |  |  |  |  | 0 | ?? | ?? |  | ?? | ?? | ?? | 0
5 | OP.1.2 | 1b. |  | 1b. 800 on-farm rainwater harvesting ponds commissioned (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 2 | MAFF | Pond | 0 | 800 | 0 | 80 | 280 | 290 | 150 | 0 |  | 5 |  | 4.13 | 0.2065 | 70 | 0 | 0 |  | 1.125 | 0 | 0.05625 | 140 |  | 0% |  | 210 | 4.13 | 20.65%
6 | OP.1.3 | 1c. |  | 1c. At least 250 km of farm road networks upgraded to climate standards to improve connectivity of farms to cooperatives and markets (2017 baseline: 0). | Add next |  | MRD annual report |  | CS 1 | MRD | Km | 0 | 250 | 2019: 0; 2020: 67.95; 2021: 100.1; 2022: 81.95 | 15 |  | 14.05 | 2.1075 | 25.025 | 16.4277 | 1.3577 |  | 41.8305 | 3.8218 | 7.6322 | 50.05 |  | 0% |  | 75.075 | 30.4777 | 346.5%
7 | OP.1.4 | 1d. |  | 1d. 80 agricultural cooperatives* integrated adaptation measures in post-harvest infrastructure investments (2017 baseline: 5). | Add next | Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | AC | 5 | 80 | 0 | 20 | 35 | 25 | 0 | 0 |  | 15 |  | 15.06 | 2.259 | 8.75 | 0.40625 | 0.063984 |  | 40.2719 | 0.12492 | 6.1048 | 17.5 |  | 0% |  | 26.25 | 15.4663 | 232.3%
8 | OP.1.5 | 1e. |  | 1e. Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples (2017 baseline: 700) and generate service income more than $75,000 (2017 baseline: $0). | Add next | Vong Sophorn/ Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | [10 empty] | 5 |  | 16 | 0.8 |  | 4.1556 | 0.21817 |  | 27.5556 | 0.42594 | 1.5959 | 0 |  | #DIV/0! |  | 0 | 20.1556 | #DIV/0!
| OP.1.5.1e.1 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples |  |  | PPMS annual reports |  | CS 2 | MAFF | Sample | 700 | 1500 | 0 | 0 | 0 | 900 | 1100 | 1500 | [5 empty] | 0 | [6 empty] | 0
| OP.1.5.1e.2 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded generate service income more than $75,000 |  |  | PPMS annual reports |  | CS 2 | MAFF | USD | 0 | 75000 | 0 | 0 | 0 | 45000 | 55000 | 75000 | [5 empty] | 0 | [6 empty] | 0
9 | OP.1.6 | 1f. |  | 1f. 12,000 additional biodigesters and 6,000 compost huts made operational, benefiting at least 80,000 persons, including at least 50% women, due to better household air quality (2017 baseline beneficiaries: 11,468 persons, including 5,721 women). | Add next | Phuong Dara | PPMS annual reports |  | CS 2 | MAFF | [16 empty] | 0.050419 |  |  | 0.11755 | 0.41974 | 0 |  | #DIV/0!
| OP.1.6.1f.1 | 1f.1 |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Biodigesters | No BL | 12000 | 0 | 500 | 1250 | 4000 | 3500 | 1500 |  | 4 |  | 7.07 | 0.2828 | 312.5 | 0.18333 | 0.0056 |  | 3.8564 | 0.012933 | 0.15986 | 625 |  |  |  | 937.5 | 7.2533 | 28.84%
|  |  |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 80000 | 0 | 3333.3333 | 8333.3333 | 26666.6667 | 23333.3333 | 10000 | [5 empty] | 2083.3333 | [6 empty] | 4166.6667
| OP.1.6.1f.2 | 1f.2 |  | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Compost hut | No BL | 6000 | 0 | 250 | 625 | 1600 | 1600 | 1300 |  | 4 |  | 7.47 | 0.2988 | 156.25 | 0.27333 | 0.0084 |  | 5.1215 | 0.019333 | 0.21326 | 312.5 |  |  |  | 468.75 | 7.7433 | 30.72%
|  |  | No PP | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 833.3333 | 5000 | 5333.3333 | 5333.3333 | 4333.3333 | [5 empty] | 1250 | [6 empty] | 2500
| OP.1.6.1f.3 | 1f.3 |  | 20,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  | Phuong Dara | Physical Progress |  | CS 2 | MAFF |  | No BL | 20000 | 0 | 2500 | 5000 | 9500 | 3000 | 0 |  | 2 |  | 0.7 | 0.014 | 1250 | 9.156 | 0.13726 |  | 37.4424 | 0.32038 | 0.8861 | 2500 |  |  |  | 3750 | 9.856 | 15.13%
| OP.1.6.1f.3 | 1f.3.1 | No PP | 20,000 people trained on biodigester use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 1250 | 2500 | 4750 | 1500 | 0 | [5 empty] | 625 | [6 empty] | 1250
| OP.1.6.1f.8 | 1f.3.2 | No PP | 20,000 people trained on compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Woman | 11468 | 20000 | 0 | 1250 | 2500 | 4750 | 1500 | 0 | [5 empty] | 625 | [6 empty] | 1250
| OP.2 | 2 |  | Outputs. 2. Climate smart agriculture and agribusiness promoted | [16 empty] | 20 |  | 2.0032 | 2.9565 |  | 44.7976 | 1.5617 |  | 206.2509 | 3.1681 | 10.1162 | [5 empty] | 46.8008 | 4.5182
10 | OP.2.1 | 2a. |  | 2a. Three additional climate resilient varieties of rice and maize released (2017 baseline: 0). | Add next | Sophath Heng | PPMS annual reports |  | CS 2 | MAFF | Variety | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  | 5 |  | 6.25 | 0.3125 | 0 | 1.6042 | 0.054965 |  | 8.7274 | 0.13481 | 0.65175 | 0 |  | #DIV/0! |  | 0 | 7.8542 | #DIV/0!
| OP.2.1.2a.1 |  |  | Three additional climate resilient varieties of rice released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
| OP.2.1.2a.2 |  |  | Three additional climate resilient varieties of maize released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0
11 | OP.2.2 | 2b. |  | 2b. 40,000 farmers (of whom 16,000 are women) trained in CSA and agribusiness development skills, of which 50% are SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0). | Add next | Pon Han | PPMS annual reports |  | CS 2 | MAFF |  | No BL | 40000 | 0 | 2500 | 19172 | 9500 | 9000 | 9000 |  | 5 |  | 16.98 | 0.849 | 4793 | 1.4533 | 0.96547 |  | 35.2445 | 1.9679 | 2.873 | 9586 |  | 0% |  | 14379 | 18.4333 | 181.4%
| OP.2.2.2b.1 |  |  | farmers (of whom 16,000 are women) trained in CSA | [6 empty] | Person | No BL | 20000 | 0 | 501 | 5800 | 5000 | 5000 | 4499 | [5 empty] | 1450 |  | 0 |  |  | 0.0011 | 0.0083292 | 2900
| OP.2.2.2b.2 |  | No PP | farmers (of whom 16,000 are women) trained in Agribusiness Development Skills (ADS) | [6 empty] | Person | No BL | 20000 | 0 | 250 | 7893 | 4937.5 | 4937.5 | 4937.5 | [5 empty] | 1973.25 | [6 empty] | 3946.5
| OP.2.2.2b.3 |  |  | farmers are trained on SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0) | [6 empty] | Person | 0 | 20000 | 0 | 875 | 5250 | 4781.25 | 4781.25 | 4781.25 | [5 empty] | 1312.5 |  | 0.00252 |  |  | 0.00554 | 0.00654 | 2625
|  |  | Add more | farmers are trained on CAMGAP compliant | [7 empty] | No BL | 500 | 0 | 250 | 120 | 0 | 0 | 0 | [5 empty] | 30 |  | 0 |  |  | 0.006 | 0.0129 | 60
|  |  | Add more | 20% of total 40,000 farmers are trained on Agricultural farm Machinery | [7 empty] | No BL | 8000 | 0 | 496 | 109 | 2000 | 2000 | 1128 | [5 empty] | 27.25 |  | 0 |  |  | 0.00080526 | 0.0027789 | 54.5
12 | OP.2.3 | 2c. |  | 2c. 27 FWUCs/FWUGs made operational and 500 FWUC/FWUG members (of which 30% women) developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). | Add next | Soeur Sophorn | PPMS annual reports |  | CS 2 | MAFF | FWUC | 0 | [8 empty] | 6 | [5 empty] | 0.10831 |  |  | 0.2158 | 1.8108 | 0 |  | #DIV/0!
| OP.2.3.2c.1 | 2C1 |  | 27 FWUCs/FWUGs made operational and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM |  | Soeur Sophorn - CS2 |  |  | CS 2 | MAFF | FWUC | 0 | 27 | 0 | 10 | 18 | 9 | 0 | 0 |  | 3 |  | 12.1 | 0.363 | 4.5 | 18.8401 | 0.17252 |  | 31.9207 | 0.34549 | 2.2605 | 9 |  |  |  | 13.5 | 30.9401 | 53.55%
| OP.2.3.2c.2 | 2C2 |  | 500 FWUC/FWUG members developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 500 | 0 | 100 | 200 | 100 | 100 | 100 |  | 3 |  | 10 | 0.3 | 50 | 13 | 0.0441 |  | 17.9 | 0.0861 | 1.3611 | 100 |  |  |  | 150 | 23 | 34.41%
13 | OP.2.4 | 2d. |  | 2d. 4 provincial agricultural development centers (PADC) and 4 Mechnization engineering workshops (MEW) made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). | Add next | Phai Sok Heng | PPMS annual reports |  | CS 2 | MAFF |  | 0 | 8 |  | 6 | 6 | 2 | 0 | 0 | [5 empty] | 1.5 | 0.24347 | 0.16231 |  | 0 | 0.3169 | 1.4849 | 3 |  | 0%
| OP.2.4.2d.1 | 2d1 |  | 4 provincial agricultural development centers made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | PADC | 0 | 4 | 2019: 0; 2020: 3; 2021: 4; 2022: 1 | 2 |  | 26.3 | 0.526 | 0.75 | 5.575 | 0.1232 |  | 51.0417 | 0.24053 | 1.367 | 1.5 |  |  |  | 2.25 | 31.875 | 64.92%
| OP.2.4.2d.2 | 2d2 |  | 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Workshop | 0 | 4 | 2019: 0; 2020: 3; 2021: 4; 2022: 1 | 2 |  | 30.3 | 0.606 | 0.75 | 4.325 | 0.20142 |  | 61.4167 | 0.39326 | 1.6028 | 1.5 |  |  |  | 2.25 | 34.625 | 80.74%
| OP.3 | 3 |  | 3. Enabling environment for climate friendly agribusiness enhanced | [16 empty] | 15 |  |  | 1.395 |  | 67.05 | 1.1167 |  | 160.125 | 2.5292 | 4.5007 |  | 1.1167 | 2.5292 |  |  | 68.1667 | 5.0408
14 | OP.3.1.a | 3a. |  | 3a. Climate-smart and gender-responsive agribusiness policy for target commodities, including a PPP framework focusing on agribusinesses formulated (2017 baseline: 0).** | Add next | Hoeung Hun / Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | Policy |  | 4 | 0 | 0 | 1.3 | 1.3 | 1 | 0.3 |  | 2 |  | 19 | 0.38 | 0.325 | 20.75 | 0.2835 |  | 58.075 | 0.6985 | 1.445 | 0.65 |  | 0% |  | 0.975 | 39.75 | 66.35%
| OP.3.1.3a.1 |  |  | 1. Draft of Climate Smart and Gender Responsive Agrib-policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 2019: 0; 2021: 0.4; 2022: 0.4; 2023: 0.1 |  |  |  |  | 0.1 |  | 0.05775 |  |  | 0.14025 | 0.277 | 0.2
| OP.3.1.3a.2 |  |  | 2. Draft CSA policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.028875 |  |  | 0.071375 | 0.13387 | 0.15
| OP.3.1.3a.3 |  |  | 3. Draft guidance manual for climate neutrality and adaption for agribusiness operation; and 4. Draft IDP strategy for climate friendly agribusiness |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.02625 |  |  | 0.06625 | 0.12875 | 0.15
| OP.3.1.3a.4 |  |  | 5. Draft PPP framework formulated |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.028875 |  |  | 0.071375 | 0.18288 | 0.15
15 | OP.3.2 | 3b. |  | 3b. CAMGAP for tropical fruit and organic fertilizers endorsed as national standard for tropical fruit and organic fertilizers (2017 baseline: 0). | Add next | Hoeung Hun / Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | Standard | 0 | 2 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2 |  | 2 |  | 14.5 | 0.29 | 0.15 | 7.15 | 0.10185 |  | 16.65 | 0.24485 | 0.43485 | 0.3 |  | 0% |  | 0.45 | 21.65 | 39.18%
| OP.3.3b.1 |  |  | CAMGAP for tropical fruit endorsed as national standard for tropical fruit (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0 |  |  | 0 | 0 | 0.15
| OP.3.3b.2 |  |  | CAMGAP for organic fertilizers endorsed as national standard for organic fertilizers (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.075 |  | 0.017325 |  |  | 0.042825 | 0.057825 | 0.15
16 | OP.3.3 | 3c. |  | 3c. 50 staff, including 30% women, from financial institutions trained in CSA and green finance (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF | Person | 0 | 50 | 0 | 0 | 25 | 20 | 15 | 0 |  | 2 |  | 11.5 | 0.23 | 6.25 | 12.2 | 0.1806 |  | 42.2 | 0.4246 | 1.0246 | 12.5 |  | 0% |  | 18.75 | 23.7 | 41.06%
| OP.3.3C.1 |  |  | 50 staff, including 30% women, from financial institutions trained in CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 12.5 | 10 | 7.5 | 0 | [5 empty] | 3.125 |  | 0 |  |  | 0 | 0 | 6.25
| OP.3.3C.2 |  |  | 50 staff, including 30% women, from financial institutions trained in Green finance (2017 baseline:0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 12.5 | 10 | 7.5 | 0 | [5 empty] | 3.125 |  | 0 |  |  | 0 | 0 | 6.25
17 | OP.3.4 | 3d. |  | 3d. 30 agribusinesses, including 30% women-led and/or owned,*** trained on green finance and CSA (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF |  |  | 30 | 0 | 0 | 10 | 10 | 10 | 0 |  | 2 |  | 5.4 | 0.108 | 2.5 | 9.2 | 0.1407 |  | 12.8 | 0.3247 | 0.3967 | 5 |  | 0% |  | 7.5 | 14.6 | 24.87%
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on Green finance (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 1.25 |  | 0 |  |  | 0 | 0 | 2.5
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Woman | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 1.25 |  | 0 |  |  | 0 | 0 | 2.5
18 | OP.3.5 | 3e. |  | 3e. 20,000 households, including 20,000 women, provided with information on climate risk sharing instruments (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | Household | 0 | 20000 | 0 | 0 | 10000 | 6000 | 6000 | 2500 |  | 2 |  | 4.5 | 0.09 | 2500 | 10.6 | 0.1848 |  | 11.5 | 0.3968 | 0.4148 | 5000 |  | 0% |  | 7500 | 15.1 | 27.48%
19 | OP.3.6 | 3f. |  | 3f. ICT platform for climate friendly agribusiness established in Kampong Cham province (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | ICT Platform | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 2 |  | 4.5 | 0.09 | 0.075 | 0 | 0 |  | 0.75 | 0 | 0.015 | 0.15 |  | 0% |  | 0.225 | 4.5 | 9%
| OP.3.7 | 3g | No DMF | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | Add next | [5 empty] | ICT Platform |  | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 3 |  | 6.9 | 0.207 | 0.075 | 7.15 | 0.22523 |  | 18.15 | 0.43972 | 0.76972
[27 empty] | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
GENDER AND SOCIAL DIMENSIONS
Output 1: Critical agribusiness value chain infrastructure improved and made climate resilient
Gender Objectives. 1.1 Ensure critical agribusiness value chain infrastructure is responsive to the needs of women and men
20 |  | 1.1.1 |  | 1.1.1 (i) Women are 40% of participants– aggregate basis (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3; 30% female participation in similar activities currently); (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y4 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  | 1.1.1.i |  | (i) Women are 40% of participants– aggregate basis (point of reference: female population: |  |  |  |  | CS 1 | MAFF | % | No BL | 40 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Women are 54% of participants in subproject 1; |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (i) Women are 47% of participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (i) Women are 48% of participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (i) Women are 30% female participation in similar activities currently); |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 | [6 empty] | 0
|  | 1.1.1.ii |  | (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems |  |  |  |  | CS 1 | MAFF | Person | No BL | 50000 | [11 empty] | 0 | [6 empty] | 0
Gender Objectives. 1.2. Enhance income generating opportunities for women
21 |  | 1.2.1 |  | 1.2.1 At least 25% of workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y6 | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by skilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by unskilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | [12 empty] | 0 | [6 empty] | 0
|  |  |  | Workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) |  |  |  |  | CS 1 | MAFF | % | No BL | 17-46 | [11 empty] | 0 | [6 empty] | 0
22 |  | 1.2.2 |  | 1.2.2 At least 30% women FWUC members developed capacity to operate and maintain irrigation schemes. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
Gender Objectives. 1.3 Increase the uptake of biodigesters
23 |  | 1.3.1 |  | 1.3.1 At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y4 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 5721 | 40000 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 | [6 empty] | 0
24 |  | 1.3.2 |  | 1.3.2 Number and percentage of women active agents. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y4 | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | Number of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 | [6 empty] | 0
|  |  |  | Percentage of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 | [6 empty] | 0
Output 2: Climate smart agriculture and agribusiness promoted
Gender Objectives. 2.1 Strengthen women farmers’ (individual and member of cooperatives) involvement along climate- friendly agribusiness value chains
25 |  | 2.1.1 |  | 2.1.1 Number and % of women farmers involved | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | Number of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 | [6 empty] | 0
|  |  |  | % of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 | [6 empty] | 0
26 |  | 2.1.2 |  | For 2.1.2 (1) and (3): Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA and agribusiness development skills (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3 with almost all of them farming; 30% female participation in similar activities currently). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | [16 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA . |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in Agribusiness Development Skills |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | Women are 54% of total participants in subproject 1 |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | Women are 47% of total participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | Women are 48% of total participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | 30% female participation in similar activities currently |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 | [6 empty] | 0
27 |  |  |  | For 2.1.2 (2): (i) Number and percentage of women farmers trained in each event; (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y5 | [16 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Number of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | Woman | 0 | ? | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (i) Percentage of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | ? | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | 40 | [11 empty] | 0 | [6 empty] | 0
28 |  |  |  | 2.1.3 (i) Number and type of activities conducted; (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. | Focus on Agricultural Cooperatives with a majority of female members | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y2 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted; |  |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 | [6 empty] | 0
Gender Objectives. 2.2 Ensure female staff benefit from capacity- building activities related to climate- friendly agribusiness value chains
29 |  | 2.2.1 |  | 2.2.1 25% at national level and 20% at local levels women participants (aggregate basis). | Add next | Kol Prapey / Peter J. |  | Q1 Y2 – Q4 Y6 | CS 1 |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | 25% at national level of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | Woman | No BL | 25 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | 20% at local levels of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | Woman | No BL | 20 | [11 empty] | 0 | [6 empty] | 0
Output 3: Enabling environment for climate friendly agribusiness enhanced
Gender Objectives 3.1. Institutionalize gender mainstreaming in the climate- friendly agribusiness value chains sector
30 |  | 3.1.1 |  | 3.1.1 Report prepared with clear recommendations based on detailed gender analysis of the 4 value chains. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q3 Y1 | CS 1 | MAFF | Report | 0 | 10 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
31 |  | 3.1.2 |  | 3.1.2 Key recommendations from gender analysis of 4 targeted value chains integrated in the Agribusiness Policy ( CSA Policy, Agro-Industry Policy, Contract Farming Inclusive Agribusiness Policy, Proclamation/Prakas Supporting AC’s Law, PPP-Initiative Agribusiness Policy). (Baseline: NA) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q2 Y3 | CS 1 | MAFF | Recommendation | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
32 |  | 3.1.3 |  | 3.1.3 Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; number of people trained disaggregated by sex. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; (Baseline: 0) | To be determined during the reporting period, while the session completed. | [5 empty] | Session | 0 | # | [11 empty] | 0 | [6 empty] | 0
|  |  |  | Number of people trained disaggregated by sex on gender equality in climate-friendly agribusiness value chains; (Baseline:0) | To be determined during the reporting period, while the session completed. | [5 empty] | Person | 0 | # | [11 empty] | 0 | [6 empty] | 0
33 |  | 3.1.4 |  | 3.1.4 MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), the AC and the WFN are aware of the GAP activities | To be determined during the reporting period. | Kol Prapey / Peter J. | Project Recoding | Q2 Y2 – Q4 Y7 | CS 1 | MAFF | % | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
Gender Objectives 3.2 Enhance access to green finance for women involved in agribusiness value chains
34 |  | 3.2.1 |  | 3.2.1 (i)Number and type of activities conducted; (ii) types of communication channels and materials used; (iii) 15 female staff in financial institutions trained in CSA lending and green finance (or 30% of total staff trained are women); (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on green finance and CSA; (v) 20,000 women provided with information on climate risk sharing instruments. | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | CS 1 | MAFF |  | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted on climate risk sharing instruments. |  |  | Project Interim Recoding |  |  |  | Activity | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (ii) Types of communication channels and materials used on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Channel | No BL | # | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in CSA lending are women); |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in Green finance (or 30% of total staff trained) are women; |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on Green finance;. |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on CSA; |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 | [6 empty] | 0
|  |  |  | (v) 20,000 women provided with information on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Woman | No BL | 20000 | [11 empty] | 0 |  | #DIV/0! |  |  |  |  | 0 |  | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[27 empty] | #DIV/0! | [6 empty] | #DIV/0!
[9 empty] | CS# |  | Units
[9 empty] | CS 1 |  | Person
[9 empty] | CS 2 |  | Km
[9 empty] | CS 3 |  | Ha
[9 empty] | CS 4 |  | %
[9 empty] | CS 5 |  | Pond
[9 empty] | MAFF |  | System
[9 empty] | MOWRAM |  | Kg
[9 empty] | MRD |  | Tone
[9 empty] | MEF |  | Tone/Ha
[9 empty] | Other |  | Woman
Household
AC
Sample
USD
Biodigesters
Compost hut
Variety
Irrigation System
FWUC
PADC
Workshop
Policy
Standard
No.
Assessment
Staff
Household
ICT Platform
Schemes
Document
Report
Recommendation
Session
Activity
Channel
Riel
Euro
Time
Piece
Set
LS
Book
Unit
Table
Laptop
Piece
Other
Note on D7: User: Several individual meetings with Mr. Vanarath - Head of DoP office/MAFF, and Mr. Mak Many - Head of DoP/MAFF, there is neither indicators codes related, nor database system.
Note on E10: XMG: PAM, p. 52, 53.
Note on E57: User: Noted that the previous mentioned as the sub-indicators are not in PAM but the belows are in PAM, which must be tracking including, 1- Draft of Climate Smart and Gender Responsive Agrib-policy 2- Draft of CSA policy 3- Draft of guidance manual for climate neutrality and adaption for agribusiness operation 4- Draft of IDP strategy for climate friendly agribusiness 5- Draft PPP framework formulated 6- National Standards and policy of biodigester (Mentioned by Mr. Hoeung Hun)
Note on E78: XMG: PAM, p. 47-50 Gender activities/actions, 1.1.1 Involve women and Women Farmers Network (WFN) representatives actively and meaningfully in each individual event for all consultations and planning activities related to improvement and climate resiliency of critical infrastructure supported by the project. - This would mean paying attention to the following aspects: convenient time, adequate venue, information sharing with visual aids/illustrations, having female facilitators, child supervision arrangements, etc.
Note on E86: XMG: Gender activities/actions, 1.2.1 Ensure women benefit from jobs created by the project related to infrastructure construction/rehabilitation as well as operation and maintenance. - This would mean that information about such employment opportunities will be communicated through adequate channels to reach out women in the communities. - Core labor standards will be complied with (equal pay for work of equal value, no child labor) for all civil works related to the project. - Other measures that are needed will be taken (e.g. child supervision arrangements even if informal) so that interested women can grasp such opportunities.
Note on E90: XMG: Gender activities/actions, 1.2.2 Provide skills enhancement for women in infrastructure related construction/rehabilitation (e.g. masonry skills for bio-digesters construction), and operation and maintenance (e.g. small-scale irrigation schemes).
Note on E92: XMG: Gender activities/actions, 1.3.1 As part of the promotion campaigns about biodigesters and other renewable energy solutions, raise awareness among women and men in the communities about the benefits for value chain improvement/climate change but also for greater gender equality (time saving, drudgery reduction, improved health).
Note on E96: XMG: Gender activities/actions, 1.3.2 Involve women as active agents in the promotion campaigns on the use of renewable energy solutions.
Note on E101: XMG: Gender Activities/Action, 2.1.1 Involve women farmers (and the WFN) actively in the selection and multiplication of climate resilient crops varieties and build on their local knowledge in this area.
Note on E104: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (1) agricultural extension and technical capacity-building activities including those related to climate change adaptation and mitigation;
Note on E111: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (2) trainings on how to operate and maintain a range of agricultural machinery; (3), management (including leadership, negotiation) and business skills trainings. - This would mean paying special attention to the following aspects: adequate venue, timing, duration, way that invitation is being done (not to head of household as is currently being done), use of visual aids and other illustrated materials, use of female facilitators/demonstrators and extension agents, child care arrangements even if informal, etc.
Note on E115: XMG: Gender Activities/Actions, 2.1.3 Strengthen linkages between women-led and/or owned farms/enterprises* and agribusiness industry For support provided to cooperatives: preferential support will be given to agricultural cooperatives with a majority of female members. .1.4 Work with the WFN to identify context-appropriate ways to address burden of household and care work for women farmers, especially female headed households, which prevents them to increasingly participate and move up along the value chains.
Note on E124: XMG: Gender Activities/Actions, 3.1.1 At project inception, refine the gender analysis for each of the 4 targeted value chains and develop a set of clear policy and program recommendations to strengthen women farmers’ involvement along the different value chains. Ensure that capacity is built within MAFF/ Gender & Children Project Support Unit (GCPSU) for gender responsive value chain analysis and develop methodology/guidelines that can be used in future analysis.
Note on E125: XMG: Gender Activities/Actions, 3.1.2 Integrate key recommendations from the above- mentioned gender analysis of value chains and key features of the MAFF Gender Policy into the Agribusiness policy and other related documents prepared under the project. - This would also mean that gender stakeholders (MAFF GCPSU representatives, gender focal points, and WFN) participate in policy committees and meetings.
Note on E126: XMG: Gender Activities/Actions, 3.1.3 Integrate a session on gender equality in climate- friendly agribusiness value chains (based on gender analysis report mentioned above) into the training and awareness raising activities for relevant project stakeholders (i.e. relevant departments in MAFF, agricultural extension agents, local leaders and government officials, GCPSU and Gender Focal Points, and WFN).
Note on E129: XMG: Gender Activities/Actions, 3.1.4 Actively involve the MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), and the WFN and the Agricultural Cooperatives as key partners in project implementation and monitoring, especially for the GAP activities. - This also entails partnering with the WFN as facilitators/resource persons for agricultural extension and technical capacity-building, awareness-raising and information sharing targeted at farmers including provision of market information. - WFN social media pages should be used as one of the ways to disseminate information to women farmers.
Note on E131: XMG: Gender Activities/Actions, 3.2.1 Raise awareness among women farmers/ cooperative members, women-led and/or owned enterprises, and female staff in financial institutions using adequate channels about existing credit facilities, green financing including crop insurance and required formalities to access these
Note on L42: User: Planned in 2021, - 90 demos for rice - 10 demos for cassava - 30 Field days
Note on Q23: User: Take 1 out is Ko Eurt Irrigation system in Batheay district, KPC, with reason due to PDoWRAM is repairing under the MoWRAM budget.
Note on Q33: User: Previous 2,500
Note on Q35: User: Previous 1250
Note on Q36: User: Previous 2,083
Note on Q37: User: Previous 5000
Note on Q44: User: Previous10,000
Note on Q45: User: Previous 5,000
Note on Q46: User: Previous 4938
Note on Q47: User: Previous 4,781
Note on Q48: User: Previous 250
Note on Q49: User: Previous 2,376
Note on Q51: User: Previous is 8
Note on Q52: User: Previous is 100
Note on Q65: User: Previous 15
Note on Q71: User: Previous 5,500
Note on Y8: User: Linked from DMF sheet of Physical Progress.
Note on AB9: User: Linked from DMF sheet of Physical Progress.
Note on AI8: User: Linked from DMF sheet of Physical Progress.
in JV with SBK Research and Development
Implemented by

## GAP PI 1st 6Ms Report 2021-1
CFAVC PROJECT's GAP PERFORMANCE INDICATORS REPORT (January - June 2021)
No. of GAP indicators | M&E Indicator Codes | PAM's DMF Indicators Codes | MAFF's indicator Codes | GAP Performant Indicators | Definitions |  | Methods for Tracking | Time line | CS#/ Units | Ministries | Unit | Baseline | Target | [7 empty] | Assigned Weight (%) | Achievement in 2020 |  |  | First Six-Monthly (January - June ) Cumulative Progress in 2021 |  |  |  | Second Six-Monthly Cumulative Progress in 2021 |  |  |  | Cummulative Progress Tracking to date in 2020 - 2021
[6 empty] | Consultants | [15 empty] | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress | Total Target | Total Actual Achieved | % Cumulative Weight Progress | Indicators Narrative Progress
[13 empty] | Total | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | [12 empty] | Total Target | Total Actual Achieved | % Weight Progress
| OC |  |  | Outcome, Productive and resource efficient agribusiness value chains developed in project areas | [16 empty] | 100 |  | 2.0032 | 11.8291 |  | 14.9969 | 25.4428 |  |  | 2.9077 | 7.2823 |  |  | 19.9078 | 44.5542
1 | OC.1 | a. |  | By 2026 a. At least 15% increase in yields (2017 baseline: rice 2.7 tons, maize 4 tons, cassava 20 tons and mango 15 tons/ha). |  |  | a. MAFF agricultural census |  | CS 2 | MAFF | % |  | 15% | [12 empty] | MTR |  |  | 0 | MTR | #VALUE!
| OC.1.a.1 |  |  | Rice (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 2.7 | 3.105 | 0 | 2.7 | 2.8013 | 2.9025 | 3.0038 | 3.105 | [9 empty] | 1.4006
| OC.1.a.2 |  |  | Maize (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 4 | 4.6 | 0 | 4 | 4.15 | 4.3 | 4.45 | 4.6 | [9 empty] | 2.075
| OC.1.a.3 |  |  | Cassava (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 20 | 23 | 0 | 20 | 20.75 | 21.5 | 22.25 | 23 | [9 empty] | 10.375
| OC.1.a.3 |  |  | Mango (per ha) |  |  |  |  | CS 2 | MAFF | Tone/Ha | 15 | 17.25 | 0 | 15 | 15.5625 | 16.125 | 16.6875 | 17.25 | [9 empty] | 7.7812
2 | OC.2 | b. |  | By 2026 b. GHG emissions reduced by 240,000 tons of CO2 (2017 baseline: 0 tons reduced due to the project). | Base on the biogas utilization calculation. |  | b. UNFCCC reports |  |  |  | Tone | 0 | 240000 | 0 | 0 | 0 | 80000 | 80000 | 80000 | [6 empty] | MTR |  |  | 0 | MTR | #VALUE!
3 | OC3 | c. |  | By 2026 c. At least 50 agribusinesses become more resource efficient in terms of water savings (5-10% efficiencies); energy savings (20%); and reduction in post-harvest losses (10%) (2017 baseline: 0). |  |  | c. PPMS reports |  | CS 2 | MAFF | % | 0 | 50 | 0 | 0 | 0 | 5 | 20 | 25 | [6 empty] | MTR |  |  | 0 | MTR | #VALUE!
| OC3.C.1 |  |  | Water saving (5-10% efficient) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [9 empty] | 1.25
| OC3.C.2 |  |  | Energy saving (20%) | Focus on the biogas utilization. |  |  |  | CS 2 | MAFF | % | 0 | 20 | 0 |  | 5 | 10 | 15 | 20 | [9 empty] | 2.5
| OC3.C.3 |  |  | Post harvesting losses (10%) |  |  |  |  | CS 2 | MAFF | % | 0 | 10 | 0 |  | 2.5 | 5 | 7.5 | 10 | [9 empty] | 1.25
| OP.1 |  |  | Outputs. 1. Critical agribusiness value chain infrastructure improved and made climate resilient | [16 empty] | 65 |  |  | 7.4776 |  | 10.142 | 16.5232 |  |  | 1.7911 | 4.7531 |  |  | 11.9331 | 28.7539
4 | OP.1.1 | 1.a. |  | 1a. 27 irrigation and water management systems targeting 15,000 ha and 25,000 households (with at least 50,000 women) rehabilitated and made climate resilient (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 1 | MOWRAM | Woman | 0 | 27 | 2019: 0; 2020: 10; 2021: 9 | 15 | 10 | 10.06 | 1.509 | 4.5 | 3067% | 460% |  | 4.5 |  | 0% |  | 19 | 40.7271 | 610.9%
| OP.1.1a.1 |  |  | 27 irrigation and water management systems |  |  |  |  | CS 1 | MOWRAM | Irrigation System | 0 | 27 | 2019: 0; 2020: 10; 2021: 9; 2022: 8 |  | 10 | 17.1936 | 0.2065 | 4.5 |  |  |  | 4.5
| OP.1.1a.2 |  |  | 27 irrigation and water management systems targeting 15,000 ha |  |  |  |  | CS 1 | MOWRAM | Ha | 0 | 15000 | 2019: 0; 2020: 4050; 2021: 5333; 2022: 5617 |  | 4050 | 1399.5 | 1.866 | 2666.5 |  |  |  | 2666.5
| OP.1.1a.3 |  | No PP | 27 irrigation and water management systems targeting 25,000 households |  |  |  |  | CS 1 | MOWRAM | Household | 0 | 25000 | 2019: 0 |  |  |  |  | 0 |  |  |  | 0
5 | OP.1.2 | 1b. |  | 1b. 800 on-farm rainwater harvesting ponds commissioned (2017 baseline: 0). | Add next |  | PPMS annual reports |  | CS 2 | MAFF | Pond | 0 | 800 | 0 | 80 | 280 | 290 | 150 | 0 |  | 5 |  | 4.13 | 0.2065 | 140 | 112.5% | 5.625% |  | 140 |  | 0% |  | 280 | 5.255 | 26.27%
6 | OP.1.3 | 1c. |  | 1c. At least 250 km of farm road networks upgraded to climate standards to improve connectivity of farms to cooperatives and markets (2017 baseline: 0). | Add next |  | MRD annual report |  | CS 1 | MRD | Km | 0 | 250 | 2019: 0; 2020: 67.95; 2021: 100.1; 2022: 81.95 | 15 |  | 14.05 | 2.1075 | 50.05 | 2540% | 381% |  | 50.05 |  | 0% |  | 100.1 | 39.4528 | 591.8%
7 | OP.1.4 | 1d. |  | 1d. 80 agricultural cooperatives* integrated adaptation measures in post-harvest infrastructure investments (2017 baseline: 5). | Add next | Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | AC | 5 | 80 | 0 | 20 | 35 | 25 | 0 | 0 |  | 15 |  | 15.06 | 2.259 | 17.5 | 3987% | 598% |  | 17.5 |  | 0% |  | 35 | 54.9256 | 823.9%
8 | OP.1.5 | 1e. |  | 1e. Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples (2017 baseline: 700) and generate service income more than $75,000 (2017 baseline: $0). | Add next | Vong Sophorn/ Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | [10 empty] | 5 |  | 16 | 0.8 |  | 2340% | 117% |  | 0 |  | #DIV/0! |  | 0 | 39.4 | #DIV/0!
| OP.1.5.1e.1 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded to test 1500 samples |  |  | PPMS annual reports |  | CS 2 | MAFF | Sample | 700 | 1500 | 0 | 0 | 0 | 900 | 1100 | 1500 | [5 empty] | 0 |  |  |  | 0
| OP.1.5.1e.2 |  |  | Crop product quality and safety testing infrastructure in National Agricultural Laboratory upgraded generate service income more than $75,000 |  |  | PPMS annual reports |  | CS 2 | MAFF | USD | 0 | 75000 | 0 | 0 | 0 | 45000 | 55000 | 75000 | [5 empty] | 0 |  |  |  | 0
9 | OP.1.6 | 1f. |  | 1f. 12,000 additional biodigesters and 6,000 compost huts made operational, benefiting at least 80,000 persons, including at least 50% women, due to better household air quality (2017 baseline beneficiaries: 11,468 persons, including 5,721 women). | Add next | Phuong Dara | PPMS annual reports |  | CS 2 | MAFF | [16 empty] | 90.66% |  | 0 |  | #DIV/0!
| OP.1.6.1f.1 | 1f.1 |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Biodigesters | No BL | 12000 | 0 | 500 | 2500 | 4000 | 3500 | 1500 |  | 4 |  | 7.07 | 0.2828 | 1250 | 367.3% | 14.69% |  | 1250 |  |  |  | 2500 | 10.7431 | 42.97%
|  |  |  | 12,000 Bio-digesters made operational benefitting 80,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 80000 | 0 | 3333.3333 | 16666.6667 | 26666.6667 | 23333.3333 | 10000 | [5 empty] | 8333.3333 |  |  |  | 8333.3333
| OP.1.6.1f.2 | 1f.2 |  | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  | Physical Progress |  | CS 2 | MAFF | Compost hut | No BL | 6000 | 0 | 250 | 1250 | 1600 | 1600 | 1300 |  | 4 |  | 7.47 | 0.2988 | 625 | 484.8% | 19.39% |  | 625 |  |  |  | 1250 | 12.3182 | 49.27%
|  |  | No PP | 6,000 Compost-huts made operational benefiting 20,000 persons (50% are women) |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 833.3333 | 4166.6667 | 5333.3333 | 5333.3333 | 4333.3333 | [5 empty] | 2083.3333 |  |  |  | 2083.3333
| OP.1.6.1f.3 | 1f.3 |  | 40,000 people trained on biodigester and compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  | Phuong Dara | Physical Progress |  | CS 2 | MAFF |  | No BL | 40000 | 0 | 2500 | 10000 | 9500 | 9000 | 9000 |  | 2 |  | 0.7 | 0.014 | 5000 | 2829% | 56.57% |  | 5000 |  |  |  | 10000 | 28.9864 | 57.97%
| OP.1.6.1f.3 | 1f.3.1 | No PP | 20,000 people trained on biodigester use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Person | 11468 | 20000 | 0 | 1250 | 5000 | 4750 | 4500 | 4500 | [5 empty] | 2500 |  |  |  | 2500
| OP.1.6.1f.8 | 1f.3.2 | No PP | 20,000 people trained on compost hut use and management (50% are women) and one (1) national standard and policy of biodigester and bio-slurry developed |  |  |  |  | CS 2 | MAFF | Woman | 11468 | 20000 | 0 | 1250 | 5000 | 4750 | 4500 | 4500 | [5 empty] | 2500 |  |  |  | 2500
| OP.2 |  |  | Outputs. 2. Climate smart agriculture and agribusiness promoted | [16 empty] | 20 |  | 2.0032 | 2.9565 |  | 3.0299 | 6.9481 | [6 empty] | 5.033 | 9.9046
10 | OP.2.1 | 2a. |  | 2a. Three additional climate resilient varieties of rice and maize released (2017 baseline: 0). | Add next | Sophath Heng | PPMS annual reports |  | CS 2 | MAFF | Variety | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  | 5 |  | 6.25 | 0.3125 | 0 | 7.1304 | 51.69% |  | 0 |  | #DIV/0! |  | 0 | 13.3804 | #DIV/0!
| OP.2.1.2a.1 |  |  | Three additional climate resilient varieties of rice released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | [5 empty] | 0 |  | 0% |  | 0
| OP.2.1.2a.2 |  |  | Three additional climate resilient varieties of maize released |  |  |  |  | CS 2 | MAFF | Variety | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0 |  | 0% |  | 0
11 | OP.2.2 | 2b. |  | 2b. 40,000 farmers (of whom 16,000 are women) trained in CSA and agribusiness development skills, of which 50% are SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0). | Add next | Pon Han | PPMS annual reports |  | CS 2 | MAFF |  | No BL | 40000 | 0 | 2500 | 10000 | 9500 | 9000 | 9000 |  | 5 |  | 16.98 | 0.849 | 5000 | 15.1957 | 90.51% |  | 5000 |  | 0% |  | 10000 | 32.1757 | 175.4%
| OP.2.2.2b.1 |  |  | farmers (of whom 16,000 are women) trained in CSA | [6 empty] | Person | No BL | 20000 | 0 | 501 | 5000 | 5000 | 5000 | 4499 | [5 empty] | 2500 |  | 72.29% |  | 2500
| OP.2.2.2b.2 |  | No PP | farmers (of whom 16,000 are women) trained in Agribusiness Development Skills (ADS) | [6 empty] | Person | No BL | 20000 | 0 | 250 | 4937.5 | 4937.5 | 4937.5 | 4937.5 | [5 empty] | 2468.75 |  |  |  | 2468.75
| OP.2.2.2b.3 |  |  | farmers are trained on SRP compliant with direct links to millers and exporters (2017 baseline for SRP compliance: 0) | [6 empty] | Person | 0 | 20000 | 0 | 875 | 4781.25 | 4781.25 | 4781.25 | 4781.25 | [5 empty] | 2390.625 |  | 10% |  | 2390.625
|  |  | Add more | farmers are trained on CAMGAP compliant | [7 empty] | No BL | 500 | 0 | 250 | 250 | 0 | 0 | 0 | [5 empty] | 125 |  | 69% |  | 125
|  |  | Add more | 20% of total 40,000 farmers are trained on Agricultural farm Machinery | [7 empty] | No BL | 8000 | 0 | 496 | 2376 | 2000 | 2000 | 1128 | [5 empty] | 1188 |  | 19.74% |  | 1188
12 | OP.2.3 | 2c. |  | 2c. 27 FWUCs/FWUGs made operational and 500 FWUC/FWUG members (of which 30% women) developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM | Add next | Soeur Sophorn | PPMS annual reports |  | CS 2 | MAFF | FWUC | 0 | [14 empty] | 159.5% |  | 0 |  | #DIV/0!
| OP.2.3.2c.1 | 2C1 |  | 27 FWUCs/FWUGs made operational and maintain their irrigation schemes (2017 baseline: 0). by MoWRAM |  | Soeur Sophorn - CS2 |  |  | CS 2 | MAFF | FWUC | 0 | 27 | 0 | 10 | 8 | 9 | 0 | 0 |  | 3 |  | 12.1 | 0.363 | 4 | 26.1549 | 191.5% |  | 4 |  |  |  | 8 | 38.2549 | 227.8%
| OP.2.3.2c.2 | 2C2 |  | 500 FWUC/FWUG members developed capacity to operate and maintain their irrigation schemes (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 500 | 0 | 100 | 100 | 100 | 100 | 100 |  | 3 |  | 10 | 0.3 | 50 | 16.5 | 127.5% |  | 50 |  |  |  | 100 | 26.5 | 157.5%
13 | OP.2.4 | 2d. |  | 2d. 4 provincial agricultural development centers and 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). | Add next | Phai Sok Heng | PPMS annual reports |  | CS 2 | MAFF |  | 0 | 8 |  | 6 | 6 | 2 | 0 | 0 | [5 empty] | 3 | 3.504 | 116.8% |  | 3 |  | 0%
| OP.2.4.2d.1 | 2d1 |  | 4 provincial agricultural development centers made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | PADC | 0 | 4 | 2019: 0; 2020: 3; 2022: 1 | 2 |  | 26.3 | 0.526 | 1.5 | 45.175 | 112.7% |  | 1.5 |  |  |  | 3 | 71.475 | 165.2%
| OP.2.4.2d.2 | 2d2 |  | 4 engineering workshops made fully operational to provide agribusiness services and strengthen farmer value chain linkages (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Workshop | 0 | 4 | 2019: 0; 2020: 3; 2022: 1 | 2 |  | 30.3 | 0.606 | 1.5 | 51.825 | 121% |  | 1.5 |  |  |  | 3 | 82.125 | 181.5%
| OP.3 |  |  | 3. Enabling environment for climate friendly agribusiness enhanced | [16 empty] | 15 |  |  | 1.395 |  | 1.825 | 1.9715 |  |  | 1.1167 | 2.5292 |  |  | 2.9417 | 5.8957
14 | OP.3.1.a | 3a. |  | 3a. Climate-smart and gender-responsive agribusiness policy for target commodities, including a PPP framework focusing on agribusinesses formulated (2017 baseline: 0).** | Add next | Hoeung Hun / Dy Kunthea | PPMS annual reports |  | CS 2 | MAFF | Policy |  | 6 | 0 | 0 | 1.9 | 1.9 | 1.6 | 0.5 |  | 2 |  | 19 | 0.38 | 0.95 | 37.325 | 74.65% |  | 0.95 |  | 0% |  | 1.9 | 56.325 | 112.7%
| OP.3.1.3a.1 |  |  | Agribusiness and Gender responsive policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 2019: 0; 2021: 0.4; 2022: 0.4; 2023: 0.1 |  |  |  |  | 0.2 |  |  |  | 0.2
| OP.3.1.3a.2 |  |  | CSA Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
| OP.3.1.3a.3 |  |  | Agro-Industry Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
| OP.3.1.3a.4 |  |  | Contract Farming Inclusive Agribusiness Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
| OP.3.1.3a.5 |  |  | Proclamation/Prakas Supporting AC’s Law |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
| OP.3.1.3a.6 |  |  | PPP-Initiative Agribusiness Policy |  |  |  |  | CS 2 | MAFF | Policy | 0 | 1 | 0 |  | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
15 | OP.3.2 | 3b. |  | 3b. CAMGAP for tropical fruit and organic fertilizers endorsed as national standard for tropical fruit and organic fertilizers (2017 baseline: 0). | Add next | Hoeung Hun / Mak Chanratana | PPMS annual reports |  | CS 2 | MAFF | Standard | 0 | 2 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2 |  | 2 |  | 14.5 | 0.29 | 0.3 | 9.5 | 19% |  | 0.3 |  | 0% |  | 0.6 | 24 | 48%
| OP.3.3b.1 |  |  | CAMGAP for tropical fruit endorsed as national standard for tropical fruit (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
| OP.3.3b.2 |  |  | CAMGAP for organic fertilizers endorsed as national standard for organic fertilizers (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Standard | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.15 |  |  |  | 0.15
16 | OP.3.3 | 3c. |  | 3c. 50 staff, including 30% women, from financial institutions trained in CSA and green finance (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF | Person | 0 | 50 | 0 | 0 | 15 | 20 | 15 | 0 |  | 2 |  | 11.5 | 0.23 | 7.5 | 30 | 60% |  | 7.5 |  | 0% |  | 15 | 41.5 | 83%
| OP.3.3C.1 |  |  | 50 staff, including 30% women, from financial institutions trained in CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 7.5 | 10 | 7.5 | 0 | [5 empty] | 3.75 |  |  |  | 3.75
| OP.3.3C.2 |  |  | 50 staff, including 30% women, from financial institutions trained in Green finance (2017 baseline:0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 25 | 0 | 0 | 7.5 | 10 | 7.5 | 0 | [5 empty] | 3.75 |  |  |  | 3.75
17 | OP.3.4 | 3d. |  | 3d. 30 agribusinesses, including 30% women-led and/or owned,*** trained on green finance and CSA (2017 baseline: 0). | Add next | Green Finance Specialist | PPMS annual reports |  | CS 2 | MAFF |  |  | 30 | 0 | 0 | 10 | 10 | 10 | 0 |  | 2 |  | 5.4 | 0.108 | 5 | 3.6 | 7.2% |  | 5 |  | 0% |  | 10 | 9 | 18%
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on Green finance (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Person | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 2.5 |  |  |  | 2.5
|  |  |  | 30 agribusinesses, including 30% women-led and/or owned,*** trained on CSA (2017 baseline: 0). |  |  |  |  | CS 2 | MAFF | Woman | 0 | 15 | 0 | 0 | 5 | 5 | 5 | 0 | [5 empty] | 2.5 |  |  |  | 2.5
18 | OP.3.5 | 3e. |  | 3e. 20,000 households, including 20,000 women, provided with information on climate risk sharing instruments (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | Household | 0 | 20000 | 0 | 0 | 5500 | 6000 | 6000 | 2500 |  | 2 |  | 4.5 | 0.09 | 2750 | 0.9 | 1.8% |  | 2750 |  | 0% |  | 5500 | 5.4 | 10.8%
19 | OP.3.6 | 3f. |  | 3f. ICT platform for climate friendly agribusiness established in Kampong Cham province (2017 baseline: 0). | Add next | CS 4 | PPMS annual reports |  | CS 2 | MAFF | ICT Platform | 0 | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 2 |  | 4.5 | 0.09 | 0.15 | 0.75 | 1.5% |  | 0.15 |  | 0% |  | 0.3 | 5.25 | 10.5%
| OP.3.7 | 3g | No DMF | Supporting Climate Risk Management through Information and Communication Technologies (ICT) | Add next | [5 empty] | ICT Platform |  | 1 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.1 |  | 3 |  | 6.9 | 0.207 |  | 11 | 33%
[27 empty] | #DIV/0! |  | 0 |  | #DIV/0!
GENDER AND SOCIAL DIMENSIONS
Output 1: Critical agribusiness value chain infrastructure improved and made climate resilient
Gender Objectives. 1.1 Ensure critical agribusiness value chain infrastructure is responsive to the needs of women and men
1 |  | 1.1.1 |  | 1.1.1 (i) Women are 40% of participants– aggregate basis (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3; 30% female participation in similar activities currently); (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y4 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  | 1.1.1.i |  | (i) Women are 40% of participants– aggregate basis (point of reference: female population: |  |  |  |  | CS 1 | MAFF | % | No BL | 40 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Women are 54% of participants in subproject 1; |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 47% of participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 48% of participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Women are 30% female participation in similar activities currently); |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  |  |  | 0
|  | 1.1.1.ii |  | (ii) At least 50,000 females benefiting from rehabilitated climate resilient irrigation and water management systems |  |  |  |  | CS 1 | MAFF | Person | No BL | 50000 | [11 empty] | 0 |  |  |  | 0
Gender Objectives. 1.2. Enhance income generating opportunities for women
2 |  | 1.2.1 |  | 1.2.1 At least 25% of workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 - Q4 Y6 | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by skilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 25% of workdays created will be filled by women disaggregated by unskilled and type of work. |  |  |  |  | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  |  |  | 0
|  |  |  | Workdays created will be filled by women disaggregated by skilled/unskilled and type of work (point of reference: women’s current involvement in similar infrastructure related work varying between 17% to 46%) |  |  |  |  | CS 1 | MAFF | % | No BL | 17-46 | [11 empty] | 0 |  |  |  | 0
3 |  | 1.2.2 |  | 1.2.2 At least 30% women FWUC members developed capacity to operate and maintain irrigation schemes. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
Gender Objectives. 1.3 Increase the uptake of biodigesters
4 |  | 1.3.1 |  | 1.3.1 At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y4 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters and compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 5721 | 40000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of biodigesters installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | At least 40,000 women (or 50% of total beneficiaries) are beneficiaries of compost huts installed (baseline: 5,721 women). |  |  |  |  | CS 1 | MAFF | Woman | 1430.25 | 10000 | [11 empty] | 0 |  |  |  | 0
5 |  | 1.3.2 |  | 1.3.2 Number and percentage of women active agents. | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y4 | CS 1 | MAFF | % | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Number of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | Percentage of women active agents. | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 |  |  |  | 0
Output 2: Climate smart agriculture and agribusiness promoted
Gender Objectives. 2.1 Strengthen women farmers’ (individual and member of cooperatives) involvement along climate- friendly agribusiness value chains
6 |  | 2.1.1 |  | 2.1.1 Number and % of women farmers involved | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Number of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | % of women farmers involved | How to measure this? |  |  |  | CS 1 | MAFF | % | No BL | ? | [11 empty] | 0 |  |  |  | 0
7 |  | 2.1.2 |  | For 2.1.2 (1) and (3): Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA and agribusiness development skills (point of reference: female population: 54% in subproject 1, 47% in subproject 2; and 48% in subproject 3 with almost all of them farming; 30% female participation in similar activities currently). | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | [16 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in CSA . |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 40% of total participants (aggregate basis) or at least 16,000 women farmers are trained in Agribusiness Development Skills |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 54% of total participants in subproject 1 |  |  |  |  | CS 1 | MAFF | % | No BL | 54 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 47% of total participants in subproject 2 |  |  |  |  | CS 1 | MAFF | % | No BL | 47 | [11 empty] | 0 |  |  |  | 0
|  |  |  | Women are 48% of total participants in subproject 3 |  |  |  |  | CS 1 | MAFF | % | No BL | 48 | [11 empty] | 0 |  |  |  | 0
|  |  |  | 30% female participation in similar activities currently |  |  |  |  | CS 1 | MAFF | % | No BL | 30 | [11 empty] | 0 |  |  |  | 0
8 |  | 2.1.2 |  | For 2.1.2 (2): (i) Number and percentage of women farmers trained in each event; (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y5 | [16 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Number of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | Woman | 0 | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (i) Percentage of women farmers trained in each event(baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (ii) women represent 40% of increased labor pool of individuals who can operate agricultural machinery over the baseline (baseline: 0). |  |  |  |  | CS 1 | MAFF | % | 0 | 40 | [11 empty] | 0 |  |  |  | 0
9 |  | 2.1.3 |  | 2.1.3 (i) Number and type of activities conducted; (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. | Focus on Agricultural Cooperatives with a majority of female members | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y2 |  |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted; |  |  |  |  | CS 1 | MAFF | Woman | No BL | ? | [11 empty] | 0 |  |  |  | 0
|  |  |  | (ii) at least 8,000 women farmers (or 50% of total women farmers trained) are SRP compliant with direct links to millers and exporters. |  |  |  |  | CS 1 | MAFF | Woman | No BL | 8000 | [11 empty] | 0 |  |  |  | 0
Gender Objectives. 2.2 Ensure female staff benefit from capacity- building activities related to climate- friendly agribusiness value chains
10 |  | 2.2.1 |  | 2.2.1 25% at national level and 20% at local levels women participants (aggregate basis). | Add next | Kol Prapey / Peter J. |  | Q1 Y2 – Q4 Y6 | CS 1 |  |  | No BL | [12 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | 25% at national level of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | % | No BL | 25 | [11 empty] | 0 |  |  |  | 0
|  |  |  | 20% at local levels of women participants (aggregate basis). |  |  |  |  | CS 1 | MAFF | % | No BL | 20 | [11 empty] | 0 |  |  |  | 0
Output 3: Enabling environment for climate friendly agribusiness enhanced
Gender Objectives 3.1. Institutionalize gender mainstreaming in the climate- friendly agribusiness value chains sector
11 |  | 3.1.1 |  | 3.1.1 Report prepared with clear recommendations based on detailed gender analysis of the 4 value chains. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q3 Y1 | CS 1 | MAFF | Report | 0 | 10 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
12 |  | 3.1.2 |  | 3.1.2 Key recommendations from gender analysis of 4 targeted value chains integrated in the Agribusiness Policy ( CSA Policy, Agro-Industry Policy, Contract Farming Inclusive Agribusiness Policy, Proclamation/Prakas Supporting AC’s Law, PPP-Initiative Agribusiness Policy). (Baseline: NA) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q2 Y3 | CS 1 | MAFF | Recommendation | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
13 |  | 3.1.3 |  | 3.1.3 Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; number of people trained disaggregated by sex. (Baseline: 0) | Add next | Kol Prapey / Peter J. | Project Recoding | Q4 Y1 – Q4 Y6 | CS 1 | MAFF | [14 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | Number of sessions provided on gender equality in climate-friendly agribusiness value chains; target groups; (Baseline: 0) | To be determined during the reporting period, while the session completed. | [5 empty] | Session | 0 | # | [11 empty] | 0 |  |  |  | 0
|  |  |  | Number of people trained disaggregated by sex on gender equality in climate-friendly agribusiness value chains; (Baseline:0) | To be determined during the reporting period, while the session completed. | [5 empty] | Person | 0 | # | [11 empty] | 0 |  |  |  | 0
14 |  | 3.1.4 |  | 3.1.4 MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), the AC and the WFN are aware of the GAP activities | To be determined during the reporting period. | Kol Prapey / Peter J. | Project Recoding | Q2 Y2 – Q4 Y7 | CS 1 | MAFF | % | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
Gender Objectives 3.2 Enhance access to green finance for women involved in agribusiness value chains
15 |  | 3.2.1 |  | 3.2.1 (i)Number and type of activities conducted; (ii) types of communication channels and materials used; (iii) 15 female staff in financial institutions trained in CSA lending and green finance (or 30% of total staff trained are women); (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on green finance and CSA; (v) 20,000 women provided with information on climate risk sharing instruments. | Add next | Kol Prapey / Peter J. | Project Recoding | Q1 Y2 – Q4 Y6 | CS 1 | MAFF |  | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (i) Number and type of activities conducted on climate risk sharing instruments. |  |  | Project Interim Recoding |  |  |  | Activity | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (ii) Types of communication channels and materials used on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Channel | No BL | # | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in CSA lending are women); |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (iii) 15 female staff in financial institutions trained in Green finance (or 30% of total staff trained) are women; |  |  | Project Recoding |  |  |  | Woman | No BL | 15 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on Green finance;. |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
|  |  |  | (iv) 10 (or 30% of total privately-owned enterprises trained) women-led and/or owned enterprises trained on CSA; |  |  | Project Recoding |  |  |  | Woman | No BL | 10 | [11 empty] | 0 |  |  |  | 0
|  |  |  | (v) 20,000 women provided with information on climate risk sharing instruments. |  |  | Project Recoding |  |  |  | Woman | No BL | 20000 | [11 empty] | 0 |  | #DIV/0! |  | 0 |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  | #DIV/0!
[9 empty] | CS# |  | Units
[9 empty] | CS 1 |  | Person
[9 empty] | CS 2 |  | Km
[9 empty] | CS 3 |  | Ha
[9 empty] | CS 4 |  | %
[9 empty] | CS 5 |  | Pond
[9 empty] | MAFF |  | System
[9 empty] | MOWRAM |  | Kg
[9 empty] | MRD |  | Tone
[9 empty] | MEF |  | Tone/Ha
[9 empty] | Other |  | Woman
Household
AC
Sample
USD
Biodigesters
Compost hut
Variety
Irrigation System
FWUC
PADC
Workshop
Policy
Standard
No.
Assessment
Staff
Household
ICT Platform
Schemes
Document
Report
Recommendation
Session
Activity
Channel
Riel
Euro
Time
Piece
Set
LS
Book
Unit
Table
Laptop
Piece
Other
Note on D7: User: Several individual meetings with Mr. Vanarath - Head of DoP office/MAFF, and Mr. Mak Many - Head of DoP/MAFF, there is neither indicators codes related, nor database system.
Note on E10: XMG: PAM, p. 52, 53.
Note on E80: XMG: PAM, p. 47-50 Gender activities/actions, 1.1.1 Involve women and Women Farmers Network (WFN) representatives actively and meaningfully in each individual event for all consultations and planning activities related to improvement and climate resiliency of critical infrastructure supported by the project. - This would mean paying attention to the following aspects: convenient time, adequate venue, information sharing with visual aids/illustrations, having female facilitators, child supervision arrangements, etc.
Note on E88: XMG: Gender activities/actions, 1.2.1 Ensure women benefit from jobs created by the project related to infrastructure construction/rehabilitation as well as operation and maintenance. - This would mean that information about such employment opportunities will be communicated through adequate channels to reach out women in the communities. - Core labor standards will be complied with (equal pay for work of equal value, no child labor) for all civil works related to the project. - Other measures that are needed will be taken (e.g. child supervision arrangements even if informal) so that interested women can grasp such opportunities.
Note on E92: XMG: Gender activities/actions, 1.2.2 Provide skills enhancement for women in infrastructure related construction/rehabilitation (e.g. masonry skills for bio-digesters construction), and operation and maintenance (e.g. small-scale irrigation schemes).
Note on E94: XMG: Gender activities/actions, 1.3.1 As part of the promotion campaigns about biodigesters and other renewable energy solutions, raise awareness among women and men in the communities about the benefits for value chain improvement/climate change but also for greater gender equality (time saving, drudgery reduction, improved health).
Note on E98: XMG: Gender activities/actions, 1.3.2 Involve women as active agents in the promotion campaigns on the use of renewable energy solutions.
Note on E103: XMG: Gender Activities/Action, 2.1.1 Involve women farmers (and the WFN) actively in the selection and multiplication of climate resilient crops varieties and build on their local knowledge in this area.
Note on E106: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (1) agricultural extension and technical capacity-building activities including those related to climate change adaptation and mitigation;
Note on E113: XMG: Gender Activities/Action, 2.1.2 Involve women farmers and WFN representatives actively and meaningfully in each individual event for all capacity-building activities (trainings, demonstrations, study tours) supported by the project: (2) trainings on how to operate and maintain a range of agricultural machinery; (3), management (including leadership, negotiation) and business skills trainings. - This would mean paying special attention to the following aspects: adequate venue, timing, duration, way that invitation is being done (not to head of household as is currently being done), use of visual aids and other illustrated materials, use of female facilitators/demonstrators and extension agents, child care arrangements even if informal, etc.
Note on E117: XMG: Gender Activities/Actions, 2.1.3 Strengthen linkages between women-led and/or owned farms/enterprises* and agribusiness industry For support provided to cooperatives: preferential support will be given to agricultural cooperatives with a majority of female members. .1.4 Work with the WFN to identify context-appropriate ways to address burden of household and care work for women farmers, especially female headed households, which prevents them to increasingly participate and move up along the value chains.
Note on E126: XMG: Gender Activities/Actions, 3.1.1 At project inception, refine the gender analysis for each of the 4 targeted value chains and develop a set of clear policy and program recommendations to strengthen women farmers’ involvement along the different value chains. Ensure that capacity is built within MAFF/ Gender & Children Project Support Unit (GCPSU) for gender responsive value chain analysis and develop methodology/guidelines that can be used in future analysis.
Note on E127: XMG: Gender Activities/Actions, 3.1.2 Integrate key recommendations from the above- mentioned gender analysis of value chains and key features of the MAFF Gender Policy into the Agribusiness policy and other related documents prepared under the project. - This would also mean that gender stakeholders (MAFF GCPSU representatives, gender focal points, and WFN) participate in policy committees and meetings.
Note on E128: XMG: Gender Activities/Actions, 3.1.3 Integrate a session on gender equality in climate- friendly agribusiness value chains (based on gender analysis report mentioned above) into the training and awareness raising activities for relevant project stakeholders (i.e. relevant departments in MAFF, agricultural extension agents, local leaders and government officials, GCPSU and Gender Focal Points, and WFN).
Note on E131: XMG: Gender Activities/Actions, 3.1.4 Actively involve the MAFF GCPSU, the sub-national Gender Focal Points (Province, District, Commune), and the WFN and the Agricultural Cooperatives as key partners in project implementation and monitoring, especially for the GAP activities. - This also entails partnering with the WFN as facilitators/resource persons for agricultural extension and technical capacity-building, awareness-raising and information sharing targeted at farmers including provision of market information. - WFN social media pages should be used as one of the ways to disseminate information to women farmers.
Note on E133: XMG: Gender Activities/Actions, 3.2.1 Raise awareness among women farmers/ cooperative members, women-led and/or owned enterprises, and female staff in financial institutions using adequate channels about existing credit facilities, green financing including crop insurance and required formalities to access these
Note on Q23: User: Take 1 out is Ko Eurt Irrigation system in Batheay district, KPC, with reason due to PDoWRAM is repairing under the MoWRAM budget.
Note on Y8: User: Linked from DMF sheet of Physical Progress.
Note on AB8: User: Linked from DMF sheet of Physical Progress.
Note on AF8: User: Linked from DMF sheet of Physical Progress.
in JV with SBK Research and Development
Implemented by

## Curves (hidden)
N0 | Month | MAFF Cumulative (,000 USD) | MoWRAM Cumulative (,000 USD) | MRD Cumulative (,000 USD) | Unassigned Cumulative (,000 USD) | Monthly Budget Progress (,000 USD) | Cumulative Budget Progress (,000 USD) | Budget (%) | DMF (%) | IAs (%) | MEF (%) | Output 1 (%) | Output 2 (%) | Output 3 (%)
| Starting | [6 empty] | 0 | 0 | 0 | 0
1 | 2021-01-01 | 3585.8068 | 112.59 | 231.375 | 0 | 703.068 | 39297.7179 | 2.7 | 2.4889 | 12.2518 | 11.3931 | 3.1211 | 2.7075 | 0
2 | 2021-02-01 | 3605.5931 | 112.59 | 231.375 | 0 | 722854.27 | 3949.5581 | 2.7 | 3.6457 | 13.4085 | 12.5093 | 2.1442 | 5.1025 | 0
3 | 2021-03-01 | 3627.0181 | 112.59 | 231.375 | 0 | 744270.28 | 3970.9831 | 2.9 | 4.3113 | 17.7198 | 16.7218 | 3.1211 | 5.165 | 0
4 | 2021-04-01 | 3822.031 | 103.3686 | 89.1234 | 0 | 849898.42 | 4014.523 | 2.9 | 5.1005 | 22.8204 | 21.6901 | 8.48 | 37.5 | 0
5 | 2021-05-01 | 4003.8751 | 201.832 | 89.1234 | 0 | 1130206.53 | 4294.8305 | 3.1 | 3.4975 | 26.3179 | 24.9668 | 9.6 | 10 | 0
6 | 2021-06-01 | 4279.6505 | 201.832 | 89.1234 | 0 | 1405981.92 | 4570.6059 | 3.3 | 6.3988 | 32.7167 | 30.9168 | 1.82 | 0 | 11
| Total Target | [10 empty] | 100 | 100 | 100
Note on V8: MoWRAM: Updaed as of 31 Dec'20 only.